## Project Plan
EVM Mock Project Plan — Office Fit-Out
Mock EVM baseline: activity budgets are spread across planned weeks; weekly PV and cumulative PV roll up to BAC.
Activity | Type | Unit Quantity | Rate | Total Budget | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | Start Week | End Week
Project Management | Labor | 12 | 1500 | 18000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1 | 12
Site Survey & Mobilization | Labor | 1 | 8500 | 8500 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Design & Engineering | Labor | 8 | 2400 | 19200 | 6400 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3
Procurement - Materials | Material | 1 | 42000 | 42000 | 0 | 10500 | 10500 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5
Demolition & Prep | Labor | 6 | 2200 | 13200 | 0 | 4400 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4
Electrical Rough-In | Labor | 10 | 2600 | 26000 | 0 | 0 | 0 | 8666.6667 | 8666.6667 | 8666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6
HVAC Installation | Subcontractor | 1 | 36000 | 36000 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 9000 | 0 | 0 | 0 | 0 | 5 | 8
Partitions & Drywall | Subcontractor | 1 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 7000 | 7000 | 0 | 0 | 0 | 6 | 9
Flooring | Material | 650 | 55 | 35750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11916.6667 | 11916.6667 | 11916.6667 | 0 | 0 | 8 | 10
Fixtures & Furniture | Material | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 9 | 11
Testing / Commissioning | Labor | 4 | 2100 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 11 | 12
Handover & Closeout | Labor | 2 | 1800 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 12 | 12
EVM Roll-up |  |  |  |  | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12
Total (BAC) |  |  |  | 268650
Weekly PV |  |  |  |  | 16400 | 22800 | 22800 | 25066.6667 | 29666.6667 | 26166.6667 | 17500 | 29416.6667 | 30416.6667 | 23416.6667 | 15700 | 9300
Cumulative PV |  |  |  |  | 16400 | 39200 | 62000 | 87066.6667 | 116733.3333 | 142900 | 160400 | 189816.6667 | 220233.3333 | 243650 | 259350 | 268650
Current Week |  |  |  | 6
Earned Value (EV) |  |  |  |  | 15088 | 36064 | 57040 | 80101.3333 | 107394.6667 | 131468 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Cost (AC) |  |  |  |  | 16295.04 | 38949.12 | 61603.2 | 86509.44 | 115986.24 | 141985.44 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Status Marker |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 268650 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PV | Planned Value: authorized budget assigned to scheduled work.
EVM Metric | Formula / Status | RAG | Metric | Definition | wk1: Formula; wk2: Favorable; wk3: Unfavorable
BAC | 268650 |  | CPI | Cost Performance Index: cost efficiency of the project. | wk1: EV / AC; wk2: > 1 under budget; wk3: < 1 over budget
PV @ Current Week | 142900 |  | SPI | Schedule Performance Index: schedule efficiency of the project. | wk1: EV / PV; wk2: > 1 ahead of schedule; wk3: < 1 behind schedule
EV @ Current Week | 131468 |  | EAC | Estimate at Completion: forecast total cost at completion. | wk1: BAC / CPI; wk2: Lower than BAC is favorable; wk3: Higher than BAC is unfavorable
AC @ Current Week | 141985.44 |  | VAC | Variance at Completion: original budget less forecast completion cost. | wk1: BAC - EAC; wk2: Positive = under budget; wk3: Negative = over budget
CPI | 0.92593 | 🔴 Red | EV | Budgeted value of work actually performed. | wk1: Mocked as 92% of cumulative PV through status week
SPI | 0.92 | 🔴 Red | AC | Actual cost incurred for work performed. | wk1: Mocked as EV × 1.08 through status week
EAC | 290142 | 🔴 Red | PV | Authorized budget assigned to scheduled work. | wk1: Cumulative planned value through status week
VAC | -21492 | 🔴 Red | Status Week | Present time marker used in Gantt and S-curve. | wk1: Project Plan E22
Status | Over budget / Behind schedule | 🔴 Red | Note | EV/AC are mock assumptions so CPI/SPI/EAC/VAC can be demonstrated. | wk1: Edit EV/AC rows to reflect actuals.
SV | -11432 | 🟠 Amber
CV | -10517.44 | 🟠 Amber
Variance Note | SV -$11,432 / CV -$10,517 | 🔴 Red

## EVM Dashboard
EVM Dashboard — Gantt + Planned Value S-Curve
The Gantt grid and S-curve share the same weekly PV formulas; the red dotted marker indicates the present time / status week.
BAC |  |  | PV @ Current Week |  |  | % Planned Complete |  |  | Status Week |  |  | CPI / SPI
268650 |  |  | 142900 |  |  | 53.19% |  |  | 6 |  |  | 0.93 / 0.92
🔴 Red
Story in Brief
At status week 6, the baseline plan should have earned $142,900 of planned value, or 53.2% of the BAC. The bars below show which activities are scheduled before and after the status date, while the S-curve converts those same weekly bars into cumulative planned value.
Gantt Baseline with Present-Time Marker
Activity | Type | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12
Project Management | Labor | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Site Survey & Mobilization | Labor | ■
Design & Engineering | Labor | ■ | ■ | ■
Procurement - Materials | Material |  | ■ | ■ | ■ | ■
Demolition & Prep | Labor |  | ■ | ■ | ■
Electrical Rough-In | Labor |  |  |  | ■ | ■ | ■
HVAC Installation | Subcontractor |  |  |  |  | ■ | ■ | ■ | ■
Partitions & Drywall | Subcontractor | [5 empty] | ■ | ■ | ■ | ■
Flooring | Material | [7 empty] | ■ | ■ | ■
Fixtures & Furniture | Material | [8 empty] | ■ | ■ | ■
Testing / Commissioning | Labor | [10 empty] | ■ | ■
Handover & Closeout | Labor | [11 empty] | ■
Week | BAC | EAC | PV | EV | AC | VAC | Status Timeline | Data Label | SV | CV |  | Forecast / Variance
wk1 | 268650 | 290142 | 16400 | 15088 | 16295.04 | -21492 | 0 |  | #N/A | #N/A |  | Metric | Value / Meaning
wk2 | 268650 | 290142 | 39200 | 36064 | 38949.12 | -21492 | 0 |  | #N/A | #N/A |  | EAC | 🔴 Red $290,142 forecast total cost
wk3 | 268650 | 290142 | 62000 | 57040 | 61603.2 | -21492 | 0 |  | #N/A | #N/A |  | VAC | 🔴 Red -$21,492 BAC - EAC
wk4 | 268650 | 290142 | 87066.6667 | 80101.3333 | 86509.44 | -21492 | 0 |  | #N/A | #N/A |  | SV | 🟠 Amber -$11,432 EV - PV
wk5 | 268650 | 290142 | 116733.3333 | 107394.6667 | 115986.24 | -21492 | 0 |  | #N/A | #N/A |  | CV | 🟠 Amber -$10,517 EV - AC
wk6 | 268650 | 290142 | 142900 | 131468 | 141985.44 | -21492 | #N/A | Status wk6 | -11432 | -10517.44 |  | CPI | 🔴 Red 0.93 cost efficiency
wk7 | 268650 | 290142 | 160400 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A |  | SPI | 🔴 Red 0.92 schedule efficiency
wk8 | 268650 | 290142 | 189816.6667 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A |  | Status | 🔴 Red Over budget / Behind schedule
wk9 | 268650 | 290142 | 220233.3333 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A
wk10 | 268650 | 290142 | 243650 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A |  | RAG Legend | Rule of thumb
wk11 | 268650 | 290142 | 259350 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A |  | 🟢 Green | On track / favorable
wk12 | 268650 | 290142 | 268650 | #N/A | #N/A | -21492 | 0 |  | #N/A | #N/A |  | 🟠 Amber | Watch: within tolerance
[12 empty] | 🔴 Red | Action required
EVM Performance Metrics
Metric | Value | Interpretation | Formula / Meaning | RAG
CPI | 0.92593 | Over budget | EV / AC: >1 under budget, <1 over budget | 🔴 Red
SPI | 0.92 | Behind schedule | EV / PV: >1 ahead of schedule, <1 behind schedule | 🔴 Red
EAC | 290142 | Forecast over BAC | BAC / CPI forecast completion cost | 🔴 Red
VAC | -21492 | Negative variance | BAC - EAC: positive under budget, negative over budget | 🔴 Red
Status | Over budget / Behind schedule | Over budget / Behind schedule | Combined CPI/SPI interpretation | 🔴 Red
1 | wk1 | 16400 | 16400 |  | 6 | 0
2 | wk2 | 22800 | 39200 |  | 6 | 268650
3 | wk3 | 22800 | 62000
4 | wk4 | 25066.6667 | 87066.6667
5 | wk5 | 29666.6667 | 116733.3333
6 | wk6 | 26166.6667 | 142900
7 | wk7 | 17500 | 160400
8 | wk8 | 29416.6667 | 189816.6667
9 | wk9 | 30416.6667 | 220233.3333
10 | wk10 | 23416.6667 | 243650
11 | wk11 | 15700 | 259350
12 | wk12 | 9300 | 268650