## EVM Dashboard
OFFICE FIT-OUT - PROJECT CONTROLLING DASHBOARD
EVM Performance Status ¦ Tufte-Compliant Design ¦ Data-Ink Maximized
Status Date: | 2026-06-12 |  | Status Week: | 6 |  | Sector: | Corporate Real Estate
BUDGET AT COMPLETION (BAC) |  |  | PLANNED VALUE (PV) |  |  | ACTUAL COST (AC) |  |  | EARNED VALUE (EV)
COST VARIANCE (CV) |  |  | SCHEDULE VARIANCE (SV) |  |  | CPI (COST INDEX) |  |  | SPI (SCHEDULE INDEX)
ESTIMATE AT COMPLETION (EAC) |  |  | ESTIMATE TO COMPLETE (ETC) |  |  | VARIANCE AT COMPLETION (VAC) |  |  | PROJECT PROGRESS %
WBS Element Performance Breakdown
WBS ID | Activity Name | Type | Budget (BAC) | Planned Value (PV) | Actual Cost (AC) | Progress % | Earned Value (EV) | CV | SV | CPI | SPI | EAC | ETC | VAC | Status
WBS-01 | Project Management | Labor
WBS-02 | Site Survey & Mobilization | Labor
WBS-03 | Design & Engineering | Labor
WBS-04 | Procurement - Materials | Material
WBS-05 | Demolition & Prep | Labor
WBS-06 | Electrical Rough-In | Labor
WBS-07 | HVAC Installation | Subcontractor
WBS-08 | Partitions & Drywall | Subcontractor
WBS-09 | Flooring | Material
WBS-10 | Fixtures & Furniture | Material
WBS-11 | Testing / Commissioning | Labor
WBS-12 | Handover & Closeout | Labor
Total / Project Portfolio
Weekly Cumulative Performance Trends
Week | Week Date | Weekly PV | Cum PV | Weekly AC | Cum AC | Cum EV | CV | SV | CPI | SPI
1 | 2026-05-04
2 | 2026-05-11
3 | 2026-05-18
4 | 2026-05-25
5 | 2026-06-01
6 | 2026-06-08
7 | 2026-06-15
8 | 2026-06-22
9 | 2026-06-29
10 | 2026-07-06
11 | 2026-07-13
12 | 2026-07-20

## Dim_Project
Project_ID | Project_Name | Start_Date | End_Date | BAC | Sector
P101 | Office Fit-Out | 2026-05-04 | 2026-07-26 | 268650 | Corporate Real Estate

## Dim_WBS
WBS_ID | WBS_Code | Activity_Name | Type | Total_Budget
WBS-01 | 1 | Project Management | Labor | 18000
WBS-02 | 2 | Site Survey & Mobilization | Labor | 8500
WBS-03 | 3 | Design & Engineering | Labor | 19200
WBS-04 | 4 | Procurement - Materials | Material | 42000
WBS-05 | 5 | Demolition & Prep | Labor | 13200
WBS-06 | 6 | Electrical Rough-In | Labor | 26000
WBS-07 | 7 | HVAC Installation | Subcontractor | 36000
WBS-08 | 8 | Partitions & Drywall | Subcontractor | 28000
WBS-09 | 9 | Flooring | Material | 35750
WBS-10 | 10 | Fixtures & Furniture | Material | 30000
WBS-11 | 11 | Testing / Commissioning | Labor | 8400
WBS-12 | 12 | Handover & Closeout | Labor | 3600

## Dim_Resource
Resource_ID | Resource_Name | Role | Hourly_Rate
R01 | Project Manager | Management | 1500
R02 | Lead Engineer | Engineering | 2400
R03 | Electrician | Trades | 2600
R04 | Demolition Crew | Labor | 2200
R05 | Testing Engineer | QA | 2100
R06 | Closeout Specialist | QA | 1800
R07 | Materials Vendor | Vendor | 0
R08 | HVAC Contractor | Contractor | 0
R09 | Drywall Contractor | Contractor | 0
R10 | Flooring Supplier | Vendor | 0
R11 | Furniture Supplier | Vendor | 0

## Dim_Calendar
Date | Year | Month | Month_Name | Quarter | Week_Number | Is_Weekday
2026-05-04 | 2026 | 5 | May | 2 | 1 | 1
2026-05-05 | 2026 | 5 | May | 2 | 1 | 1
2026-05-06 | 2026 | 5 | May | 2 | 1 | 1
2026-05-07 | 2026 | 5 | May | 2 | 1 | 1
2026-05-08 | 2026 | 5 | May | 2 | 1 | 1
2026-05-09 | 2026 | 5 | May | 2 | 1 | 0
2026-05-10 | 2026 | 5 | May | 2 | 1 | 0
2026-05-11 | 2026 | 5 | May | 2 | 2 | 1
2026-05-12 | 2026 | 5 | May | 2 | 2 | 1
2026-05-13 | 2026 | 5 | May | 2 | 2 | 1
2026-05-14 | 2026 | 5 | May | 2 | 2 | 1
2026-05-15 | 2026 | 5 | May | 2 | 2 | 1
2026-05-16 | 2026 | 5 | May | 2 | 2 | 0
2026-05-17 | 2026 | 5 | May | 2 | 2 | 0
2026-05-18 | 2026 | 5 | May | 2 | 3 | 1
2026-05-19 | 2026 | 5 | May | 2 | 3 | 1
2026-05-20 | 2026 | 5 | May | 2 | 3 | 1
2026-05-21 | 2026 | 5 | May | 2 | 3 | 1
2026-05-22 | 2026 | 5 | May | 2 | 3 | 1
2026-05-23 | 2026 | 5 | May | 2 | 3 | 0
2026-05-24 | 2026 | 5 | May | 2 | 3 | 0
2026-05-25 | 2026 | 5 | May | 2 | 4 | 1
2026-05-26 | 2026 | 5 | May | 2 | 4 | 1
2026-05-27 | 2026 | 5 | May | 2 | 4 | 1
2026-05-28 | 2026 | 5 | May | 2 | 4 | 1
2026-05-29 | 2026 | 5 | May | 2 | 4 | 1
2026-05-30 | 2026 | 5 | May | 2 | 4 | 0
2026-05-31 | 2026 | 5 | May | 2 | 4 | 0
2026-06-01 | 2026 | 6 | June | 2 | 5 | 1
2026-06-02 | 2026 | 6 | June | 2 | 5 | 1
2026-06-03 | 2026 | 6 | June | 2 | 5 | 1
2026-06-04 | 2026 | 6 | June | 2 | 5 | 1
2026-06-05 | 2026 | 6 | June | 2 | 5 | 1
2026-06-06 | 2026 | 6 | June | 2 | 5 | 0
2026-06-07 | 2026 | 6 | June | 2 | 5 | 0
2026-06-08 | 2026 | 6 | June | 2 | 6 | 1
2026-06-09 | 2026 | 6 | June | 2 | 6 | 1
2026-06-10 | 2026 | 6 | June | 2 | 6 | 1
2026-06-11 | 2026 | 6 | June | 2 | 6 | 1
2026-06-12 | 2026 | 6 | June | 2 | 6 | 1
2026-06-13 | 2026 | 6 | June | 2 | 6 | 0
2026-06-14 | 2026 | 6 | June | 2 | 6 | 0
2026-06-15 | 2026 | 6 | June | 2 | 7 | 1
2026-06-16 | 2026 | 6 | June | 2 | 7 | 1
2026-06-17 | 2026 | 6 | June | 2 | 7 | 1
2026-06-18 | 2026 | 6 | June | 2 | 7 | 1
2026-06-19 | 2026 | 6 | June | 2 | 7 | 1
2026-06-20 | 2026 | 6 | June | 2 | 7 | 0
2026-06-21 | 2026 | 6 | June | 2 | 7 | 0
2026-06-22 | 2026 | 6 | June | 2 | 8 | 1
2026-06-23 | 2026 | 6 | June | 2 | 8 | 1
2026-06-24 | 2026 | 6 | June | 2 | 8 | 1
2026-06-25 | 2026 | 6 | June | 2 | 8 | 1
2026-06-26 | 2026 | 6 | June | 2 | 8 | 1
2026-06-27 | 2026 | 6 | June | 2 | 8 | 0
2026-06-28 | 2026 | 6 | June | 2 | 8 | 0
2026-06-29 | 2026 | 6 | June | 2 | 9 | 1
2026-06-30 | 2026 | 6 | June | 2 | 9 | 1
2026-07-01 | 2026 | 7 | July | 3 | 9 | 1
2026-07-02 | 2026 | 7 | July | 3 | 9 | 1
2026-07-03 | 2026 | 7 | July | 3 | 9 | 1
2026-07-04 | 2026 | 7 | July | 3 | 9 | 0
2026-07-05 | 2026 | 7 | July | 3 | 9 | 0
2026-07-06 | 2026 | 7 | July | 3 | 10 | 1
2026-07-07 | 2026 | 7 | July | 3 | 10 | 1
2026-07-08 | 2026 | 7 | July | 3 | 10 | 1
2026-07-09 | 2026 | 7 | July | 3 | 10 | 1
2026-07-10 | 2026 | 7 | July | 3 | 10 | 1
2026-07-11 | 2026 | 7 | July | 3 | 10 | 0
2026-07-12 | 2026 | 7 | July | 3 | 10 | 0
2026-07-13 | 2026 | 7 | July | 3 | 11 | 1
2026-07-14 | 2026 | 7 | July | 3 | 11 | 1
2026-07-15 | 2026 | 7 | July | 3 | 11 | 1
2026-07-16 | 2026 | 7 | July | 3 | 11 | 1
2026-07-17 | 2026 | 7 | July | 3 | 11 | 1
2026-07-18 | 2026 | 7 | July | 3 | 11 | 0
2026-07-19 | 2026 | 7 | July | 3 | 11 | 0
2026-07-20 | 2026 | 7 | July | 3 | 12 | 1
2026-07-21 | 2026 | 7 | July | 3 | 12 | 1
2026-07-22 | 2026 | 7 | July | 3 | 12 | 1
2026-07-23 | 2026 | 7 | July | 3 | 12 | 1
2026-07-24 | 2026 | 7 | July | 3 | 12 | 1
2026-07-25 | 2026 | 7 | July | 3 | 12 | 0
2026-07-26 | 2026 | 7 | July | 3 | 12 | 0

## Fact_Baseline_PV
Date | WBS_ID | Planned_Value
2026-05-04 | WBS-01 | 1500
2026-05-11 | WBS-01 | 1500
2026-05-18 | WBS-01 | 1500
2026-05-25 | WBS-01 | 1500
2026-06-01 | WBS-01 | 1500
2026-06-08 | WBS-01 | 1500
2026-06-15 | WBS-01 | 1500
2026-06-22 | WBS-01 | 1500
2026-06-29 | WBS-01 | 1500
2026-07-06 | WBS-01 | 1500
2026-07-13 | WBS-01 | 1500
2026-07-20 | WBS-01 | 1500
2026-05-04 | WBS-02 | 8500
2026-05-04 | WBS-03 | 6400
2026-05-11 | WBS-03 | 6400
2026-05-18 | WBS-03 | 6400
2026-05-11 | WBS-04 | 10500
2026-05-18 | WBS-04 | 10500
2026-05-25 | WBS-04 | 10500
2026-06-01 | WBS-04 | 10500
2026-05-11 | WBS-05 | 4400
2026-05-18 | WBS-05 | 4400
2026-05-25 | WBS-05 | 4400
2026-05-25 | WBS-06 | 8666.67
2026-06-01 | WBS-06 | 8666.67
2026-06-08 | WBS-06 | 8666.66
2026-06-01 | WBS-07 | 9000
2026-06-08 | WBS-07 | 9000
2026-06-15 | WBS-07 | 9000
2026-06-22 | WBS-07 | 9000
2026-06-08 | WBS-08 | 7000
2026-06-15 | WBS-08 | 7000
2026-06-22 | WBS-08 | 7000
2026-06-29 | WBS-08 | 7000
2026-06-22 | WBS-09 | 11916.67
2026-06-29 | WBS-09 | 11916.67
2026-07-06 | WBS-09 | 11916.66
2026-06-29 | WBS-10 | 10000
2026-07-06 | WBS-10 | 10000
2026-07-13 | WBS-10 | 10000
2026-07-13 | WBS-11 | 4200
2026-07-20 | WBS-11 | 4200
2026-07-20 | WBS-12 | 3600

## Fact_Actual_Costs
Date | WBS_ID | Resource_ID | Actual_Cost | Hours_Worked
2026-05-04 | WBS-01 | R01 | 320 | 0.21
2026-05-05 | WBS-01 | R01 | 320 | 0.21
2026-05-06 | WBS-01 | R01 | 320 | 0.21
2026-05-07 | WBS-01 | R01 | 320 | 0.21
2026-05-08 | WBS-01 | R01 | 320 | 0.21
2026-05-04 | WBS-02 | R04 | 1740 | 0.79
2026-05-05 | WBS-02 | R04 | 1740 | 0.79
2026-05-06 | WBS-02 | R04 | 1740 | 0.79
2026-05-07 | WBS-02 | R04 | 1740 | 0.79
2026-05-08 | WBS-02 | R04 | 1740 | 0.79
2026-05-04 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-05 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-06 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-07 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-08 | WBS-03 | R02 | 1199 | 0.5
2026-05-11 | WBS-01 | R01 | 320 | 0.21
2026-05-12 | WBS-01 | R01 | 320 | 0.21
2026-05-13 | WBS-01 | R01 | 320 | 0.21
2026-05-14 | WBS-01 | R01 | 320 | 0.21
2026-05-15 | WBS-01 | R01 | 320 | 0.21
2026-05-11 | WBS-03 | R02 | 1200 | 0.5
2026-05-12 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-03 | R02 | 1200 | 0.5
2026-05-14 | WBS-03 | R02 | 1200 | 0.5
2026-05-15 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-04 | R07 | 10500 | 0
2026-05-11 | WBS-05 | R04 | 910.82 | 0.41
2026-05-12 | WBS-05 | R04 | 910.82 | 0.41
2026-05-13 | WBS-05 | R04 | 910.82 | 0.41
2026-05-14 | WBS-05 | R04 | 910.82 | 0.41
2026-05-15 | WBS-05 | R04 | 910.8 | 0.41
2026-05-18 | WBS-01 | R01 | 320 | 0.21
2026-05-19 | WBS-01 | R01 | 320 | 0.21
2026-05-20 | WBS-01 | R01 | 320 | 0.21
2026-05-21 | WBS-01 | R01 | 320 | 0.21
2026-05-22 | WBS-01 | R01 | 320 | 0.21
2026-05-18 | WBS-03 | R02 | 1240 | 0.52
2026-05-19 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-03 | R02 | 1240 | 0.52
2026-05-21 | WBS-03 | R02 | 1240 | 0.52
2026-05-22 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-04 | R07 | 10200 | 0
2026-05-18 | WBS-05 | R04 | 930.82 | 0.42
2026-05-19 | WBS-05 | R04 | 930.82 | 0.42
2026-05-20 | WBS-05 | R04 | 930.82 | 0.42
2026-05-21 | WBS-05 | R04 | 930.82 | 0.42
2026-05-22 | WBS-05 | R04 | 930.8 | 0.42
2026-05-25 | WBS-01 | R01 | 320 | 0.21
2026-05-26 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-01 | R01 | 320 | 0.21
2026-05-28 | WBS-01 | R01 | 320 | 0.21
2026-05-29 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-04 | R07 | 10200 | 0
2026-05-25 | WBS-05 | R04 | 840 | 0.38
2026-05-26 | WBS-05 | R04 | 840 | 0.38
2026-05-27 | WBS-05 | R04 | 840 | 0.38
2026-05-28 | WBS-05 | R04 | 840 | 0.38
2026-05-29 | WBS-05 | R04 | 840 | 0.38
2026-05-25 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-26 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-27 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-28 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-29 | WBS-06 | R03 | 1781.24 | 0.69
2026-06-01 | WBS-01 | R01 | 320 | 0.21
2026-06-02 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-01 | R01 | 320 | 0.21
2026-06-04 | WBS-01 | R01 | 320 | 0.21
2026-06-05 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-04 | R07 | 10400 | 0
2026-06-01 | WBS-06 | R03 | 1760 | 0.68
2026-06-02 | WBS-06 | R03 | 1760 | 0.68
2026-06-03 | WBS-06 | R03 | 1760 | 0.68
2026-06-04 | WBS-06 | R03 | 1760 | 0.68
2026-06-05 | WBS-06 | R03 | 1760 | 0.68
2026-06-01 | WBS-07 | R08 | 1735.36 | 0
2026-06-02 | WBS-07 | R08 | 1735.36 | 0
2026-06-03 | WBS-07 | R08 | 1735.36 | 0
2026-06-04 | WBS-07 | R08 | 1735.36 | 0
2026-06-05 | WBS-07 | R08 | 1735.36 | 0
2026-06-08 | WBS-01 | R01 | 320 | 0.21
2026-06-09 | WBS-01 | R01 | 320 | 0.21
2026-06-10 | WBS-01 | R01 | 320 | 0.21
2026-06-11 | WBS-01 | R01 | 320 | 0.21
2026-06-12 | WBS-01 | R01 | 320 | 0.21
2026-06-08 | WBS-06 | R03 | 1700 | 0.65
2026-06-09 | WBS-06 | R03 | 1700 | 0.65
2026-06-10 | WBS-06 | R03 | 1700 | 0.65
2026-06-11 | WBS-06 | R03 | 1700 | 0.65
2026-06-12 | WBS-06 | R03 | 1700 | 0.65
2026-06-08 | WBS-07 | R08 | 1760 | 0
2026-06-09 | WBS-07 | R08 | 1760 | 0
2026-06-10 | WBS-07 | R08 | 1760 | 0
2026-06-11 | WBS-07 | R08 | 1760 | 0
2026-06-12 | WBS-07 | R08 | 1760 | 0
2026-06-08 | WBS-08 | R09 | 1419.84 | 0
2026-06-09 | WBS-08 | R09 | 1419.84 | 0
2026-06-10 | WBS-08 | R09 | 1419.84 | 0
2026-06-11 | WBS-08 | R09 | 1419.84 | 0
2026-06-12 | WBS-08 | R09 | 1419.84 | 0

## Fact_Physical_Progress
Date | WBS_ID | Physical_Progress_Pct
2026-05-08 | WBS-01 | 0.083333
2026-05-08 | WBS-02 | 1
2026-05-08 | WBS-03 | 0.265
2026-05-15 | WBS-01 | 0.16667
2026-05-15 | WBS-02 | 1
2026-05-15 | WBS-03 | 0.6
2026-05-15 | WBS-04 | 0.2
2026-05-15 | WBS-05 | 0.35182
2026-05-22 | WBS-01 | 0.25
2026-05-22 | WBS-02 | 1
2026-05-22 | WBS-03 | 1
2026-05-22 | WBS-04 | 0.45
2026-05-22 | WBS-05 | 0.45
2026-05-29 | WBS-01 | 0.33333
2026-05-29 | WBS-02 | 1
2026-05-29 | WBS-03 | 1
2026-05-29 | WBS-04 | 0.7
2026-05-29 | WBS-05 | 0.85
2026-05-29 | WBS-06 | 0.22236
2026-06-05 | WBS-01 | 0.41667
2026-06-05 | WBS-02 | 1
2026-06-05 | WBS-03 | 1
2026-06-05 | WBS-04 | 1
2026-06-05 | WBS-05 | 1
2026-06-05 | WBS-06 | 0.5
2026-06-05 | WBS-07 | 0.11096
2026-06-12 | WBS-01 | 0.5
2026-06-12 | WBS-02 | 1
2026-06-12 | WBS-03 | 1
2026-06-12 | WBS-04 | 1
2026-06-12 | WBS-05 | 1
2026-06-12 | WBS-06 | 0.7
2026-06-12 | WBS-07 | 0.4
2026-06-12 | WBS-08 | 0.24886