## Methodology Guide
CHRIS CROFT 12-STEP PROJECT METHOD
Integrated operating checklist from Twelve Steps.pdf and PM-Simplified.md
Story-in-Brief
The workbook now connects the control-tower metrics to Chris Croft’s practical 12-step project method: define scope, build the task plan, add contingency, control schedule/resources/risks, monitor Gantt and cost, then re-plan and review. For this portfolio, the strongest alignment is EVM cost monitoring and RAID control; the main watch area is resource leveling because overtime events are already visible in the audit sheet.
Step | Croft Step | Controller Interpretation | Workbook Evidence | Primary KPI | Current Integration Note
1 | Define the project | Confirm objectives, success criteria, scope, and cost/time/quality priority. | Projects table + dashboard narrative | BAC, Status, Manager | Needs explicit success criteria per project.
2 | List the tasks | Build a complete WBS with no omissions and no overlaps. | WBS_Performance table | WBS_ID, PlannedCost | Implemented via 14 WBS elements.
3 | Plan the running order | Sequence activities and identify dependencies before committing dates. | Schedule & Gantt | Start/End dates | Add predecessor logic for full CPM.
4 | Add contingency | Reserve budget/time for uncertainty and known risk exposure. | RAID + simulator | Active RAID count | Add quantified risk reserve if needed.
5 | Consider crashing | Evaluate extra cost to shorten critical-path activities. | Interactive Simulator | Crash days, penalty, benefit | Implemented as editable what-if.
6 | Make a Gantt chart | Show who does what when, including critical activities. | Schedule & Gantt | Duration, timeline marks | Month-level view included.
7 | Calculate resource requirements | Compare planned capacity against actual hours and bottlenecks. | CFO + Risk Audit | Hours, overtime events | Overtime audit flags 8 events.
8 | Assess risks and action plans | Maintain RAID log with probability, impact, mitigation, owner, status. | Contract & RAID Risk Audit | Active RAID, owner | 3 active RAID items visible.
9 | Monitor progress using Gantt | Track physical progress and schedule movement. | EVM Data + Gantt | Progress % | Physical progress drives EV.
10 | Monitor costs | Compare AC, EV, BAC and calculate CPI/EAC. | Control Tower + EVM Data | AC, EV, CPI, EAC | Portfolio CPI is 0.91.
11 | Readjust the plan | Use cost/schedule signals to trigger corrective action and reforecasting. | Simulator + dashboard | Simulated CPI/EAC | Use when CPI < 1 or overtime persists.
12 | Review | Capture lessons learned after delivery and feed estimates back into future projects. | Controller Playbook | Review cadence | Add post-project lessons log if needed.
Portfolio Alignment Snapshot
Control Area | Current Workbook Signal | Interpretation | Action Trigger
Cost control | 0.9103 | CPI below 1.00 shows cost inefficiency. | Investigate WBS CPI < 0.90.
Progress | 66.94% | EV/BAC shows portfolio physical progress. | Review if progress stalls while AC rises.
Resource pressure | 8 | Weekly overtime events indicate resource overload. | Level resources or re-sequence work.
Risk exposure | 3 | Active RAID items need mitigation ownership. | Escalate high-impact active items.
Corrective action | 0.96671 | Simulated CPI after savings/crash choices. | Run scenario before committing changes.
Project CFO / Executive Agent Overlay
SKILL.md adds an executive-CFO lens on top of the project-control method: profitability first, margin variance thresholds, cash-flow sensitivity, and concise board-level recommendations. In practice, this means the workbook should not stop at CPI/EAC diagnostics — it should translate each cost or schedule signal into margin-at-completion and cash-risk actions for leadership.
CFO Directive | Rule from SKILL.md | Workbook Implementation | Primary Location
Profitability First | Evaluate every cost/schedule movement by its impact on final profit margin. | Use EAC, BAC/contract value, and simulated CPI to frame margin-at-completion risk. | Control Tower Dashboard + Interactive Simulator
Variance Thresholds | Flag any project where projected Margin at Completion is >2 percentage points below baseline. | Add/maintain margin-at-completion once revenue/contract value is available. | 3S Model Blueprint + 3S Readiness Audit
Cash Flow Sensitivity | Compare billing milestones with timesheet/material outlays to avoid negative project cash balances. | Current workbook has cost timing but not billing milestones; this is a data gap. | CFO & Cost Share Audit + Source Data
Strategic Focus | Use concise, bulleted recommendations for board/investor summaries. | Executive narrative should state action required, owner, and financial consequence. | Control Tower Dashboard narrative
Live CFO Trigger Snapshot
Trigger | Live Signal | Threshold / Rule | Current Status | Recommended Executive Action
Cost efficiency | 0.9103 | CPI < 1.00 indicates cost pressure. | ⚠ Margin pressure | Action Required: review low-CPI WBS and protect margin.
Worst project CPI | 0.80728 | Project CPI below 0.95 signals margin deterioration risk. | ⚠ Reforecast required | Action Required: reforecast EAC and recovery plan.
Cash-out mix | 79.47% | Labor/material cost concentration drives funding risk. | ⚠ Labor-heavy outflow | Action Required: compare outlays to billing milestones.
Overtime pressure | 8 | Any overtime event >45h/week is capacity/cost risk. | ⚠ Capacity risk | Action Required: level resources or approve recovery cost.
Large procurement | 5 | High early materials can create cash-flow troughs. | ⚠ Procurement cash risk | Action Required: align procurement with milestone billing.

## Controller Playbook
PROJECT CONTROLLER PLAYBOOK
Role, cadence, KPI definitions, and decision rules from PM-Simplified.md
Operating Thesis
The controller translates project activity into decision-grade financial insight: EVM indices, EAC/ETC forecasting, resource burn, risk exposure, and scenario analysis. In the workbook, the controller should use the dashboard as the executive view, EVM Data as the calculation ledger, Risk Audit for exceptions, and the Simulator for corrective-action tradeoffs.
Cadence | Controller Activity | Workbook Location | Decision / Output | Escalation Rule
Weekly | Review overtime and capacity pressure | Contract & RAID Risk Audit | Resource leveling recommendation | Any resource >45h/week.
Weekly | Update physical progress evidence | EVM Data / Source Data | EV refresh and progress trend | Progress unchanged while cost increases.
Monthly | Close AC and material costs | CFO & Cost Share Audit | Cost-share and burn-rate update | Actual cost variance >5%.
Monthly | Reforecast EAC/ETC | EVM Data | Revised forecast and commentary | CPI <0.95 or EAC > BAC.
Stage gate | Present cost/schedule/risk pack | Control Tower Dashboard | Go / hold / re-plan recommendation | Red project status or high RAID.
Closeout | Capture lessons learned | Methodology Guide | Estimate calibration notes | Mandatory for completed projects.
KPI Definitions and Workbook Formula Logic
KPI | Definition | Workbook Formula Pattern | Management Meaning
AC | Actual cost incurred. | Labor Cost + Material Cost | What has been spent.
EV | Earned value from physical progress. | BAC * Latest Progress | Value of work earned.
CPI | Cost Performance Index. | EV / AC | <1.00 means over-spend vs earned work.
EAC Typical | Forecast final cost using cost efficiency. | BAC / CPI | Expected final cost if current efficiency continues.
Progress | Portfolio physical completion. | EV / BAC | How much baseline value has been earned.
Cost Share | Labor/material mix. | Category Cost / AC | Where cost is being consumed.
Role Split
Role | Primary Responsibility | Workbook Usage
Project Manager | Own scope, delivery, stakeholder decisions, and corrective action. | Reads dashboard signals and approves interventions.
Project Support / PMO | Maintain process, meeting records, data collection, and reporting cadence. | Keeps source data complete and timely.
Project Controller | Analyze cost, schedule, EVM, forecasts, risks, and scenarios. | Maintains EVM model and explains financial impact.
Project CFO Agent Operating Rules
The controller playbook now includes the Project CFO / Executive Agent rules from SKILL.md. These rules convert project-control analytics into leadership decisions: protect margin, flag >2pp margin deterioration once baseline margin exists, prevent negative project cash balances, and write board-ready action statements.
Rule | Controller Question | Required Workbook Evidence | Decision Output | Escalation Trigger
Profitability First | What is the effect on margin at completion? | EAC, contract value/revenue, cost variance | Margin recovery recommendation | Any EAC increase or CPI below 1.00.
>2pp Margin Variance | Is projected margin >2 percentage points below baseline? | Baseline margin and projected MAC | Executive red flag / recovery plan | MAC variance < -2pp.
Cash Flow Sensitivity | Do billing milestones cover timesheet/material outlays? | Billing schedule, labor/material cash timing | Funding-risk warning | Negative project cash balance forecast.
Strategic Focus | What action should leadership take now? | Owner, financial impact, mitigation | Board-ready bullet recommendation | Any red/amber KPI.
Board Brief Action Template
Board Brief Component | Required Wording | Workbook Source | Example for Current Portfolio
Headline | Action Required: [decision] due to [financial driver]. | Dashboard KPI + Risk Audit | Action Required: protect margin because portfolio CPI is below 1.00.
Financial Impact | Quantify AC, EV, EAC, CPI, cash exposure, or margin variance. | Control Tower Dashboard / EVM Data | AC $5.22M vs EV $4.75M; CPI 0.91.
Owner | Name the accountable project manager/controller. | Project_Summary / RAID owner | Owner depends on project/WBS flagged.
Recommendation | State approve / hold / renegotiate / re-sequence / recover. | Simulator + Controller Playbook | Run recovery scenario before approving additional spend.
Next Review | Set date or cadence for reforecast/checkpoint. | Controller cadence | Review weekly until CPI returns toward 1.00.

## Cover
Project Control Tower Refresh
Executive EVM dashboard rebuilt from attached CSV source files
Contents | Description | RAG Legend
Control Tower Dashboard | Executive portfolio KPIs, project/WBS breakdowns, and charts | Red | Action / escalation required | CPI < 0.90, high risk, missing/gap
Gantt Charts | Portfolio Gantt-of-Gantts and per-project WBS Gantt charts | Amber | Watch / manage closely | CPI 0.90–0.99, partial, active/planned
Methodology Guide | Chris Croft 12-step method plus Project CFO profitability overlay | Green | On track / complete | CPI ≥ 1.00, approved, present, closed
Controller Playbook | Controller cadence, KPI definitions, CFO operating rules, and board brief template | Grey | Not started / neutral | Planned or not applicable
Data Model Map | ERD relationships, integrity rules, and modern PM readiness audit
3S Readiness Audit | 3-statement readiness and gap assessment | Data Bars
3S Model Blueprint | Recommended IS/BS/CF build architecture and source mapping | Blue bars | Relative magnitude within comparable numeric columns | Costs, EV, progress, hours, procurement, simulator outputs
EVM Data | Live calculation model using structured source tables | Purpose | Scan highs/lows quickly without replacing RAG status colors | Bars are only applied to numeric comparison ranges
Schedule & Gantt | Project schedule and month-level Gantt view
CFO & Cost Share Audit | Cost-share and resource burn-rate audit | Visual Style Update
Contract & RAID Risk Audit | Overtime, procurement, and RAID exception audit | Tufte cleanup | Muted colors, reduced gridlines, no decorative frames | Dashboard + Gantt charts
Interactive Simulator | Editable what-if corrective action and crash simulator | Color meaning | Grey = plan/baseline, black = actual, blue = earned/progress | Red/amber reserved for RAG risk flags
Source Data | Imported CSV source tables

## Gantt Charts
PORTFOLIO & PROJECT GANTT CHARTS | Project | Start Offset | Duration Days | Start | End | Status
Portfolio-level Gantt-of-Gantts plus per-project WBS Gantts. WBS dates are planning estimates allocated within each project window by WBS planned-cost weight because source WBS start/end dates are not available. | PRJ-001 Composite Maritime Vessel Construction | 46023 | 181 | 2026-01-01 | 2026-06-30 | Completed
| PRJ-002 Patrol Vessel Carbon Mold Design | 46235 | 153 | 2026-08-01 | 2026-12-31 | Planned
| PRJ-003 Subsea Cable Installation Frame | 46143 | 184 | 2026-05-01 | 2026-10-31 | Active
| PRJ-004 Autonomous Workboat Hull Weldments | 46082 | 184 | 2026-03-01 | 2026-08-31 | Active
| PRJ-005 Defense Logistics Pontoon Build | 46054 | 181 | 2026-02-01 | 2026-07-31 | Active
| PRJ-006 Lightweight Composite Cargo Hatch | 46113 | 61 | 2026-04-01 | 2026-05-31 | Completed
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Project Management & Engineering | 46023 | 36 | 2026-01-01 | 2026-02-05 | 🔴 Overrun
| 2 Hull Fabrication & Assembly | 46059 | 72 | 2026-02-06 | 2026-04-18 | 🟡 Complete/Watch
| 3 Outfitting & Integration | 46131 | 48 | 2026-04-19 | 2026-06-05 | 🔴 Overrun
| 4 Sea Trials & Handover | 46179 | 25 | 2026-06-06 | 2026-06-30 | 🔴 Overrun
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Design & CFD Analysis | 46235 | 57 | 2026-08-01 | 2026-09-26 | ⚪ Planned
| 2 Material Procurement | 46292 | 96 | 2026-09-27 | 2026-12-31 | ⚪ Planned
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Structural Frame Engineering | 46143 | 61 | 2026-05-01 | 2026-06-30 | 🟢 On Track
| 2 Steel Fabrication | 46204 | 123 | 2026-07-01 | 2026-10-31 | 🔴 Overrun
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Engineering Drawings & Class Approval | 46082 | 46 | 2026-03-01 | 2026-04-15 | 🟢 Completed
| 2 Hull Welding & Assembly | 46128 | 138 | 2026-04-16 | 2026-08-31 | 🔴 Overrun
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Project Control & PM | 46054 | 36 | 2026-02-01 | 2026-03-08 | 🟢 Completed
| 2 Pontoon Assembly & Painting | 46090 | 145 | 2026-03-09 | 2026-07-31 | 🟡 Watch
| Task | Start Offset | Duration Days | Start | End | Status
| 1 Hatch Engineering & FEA | 46113 | 20 | 2026-04-01 | 2026-04-20 | 🟢 Completed
| 2 Molding & Testing | 46133 | 41 | 2026-04-21 | 2026-05-31 | 🟡 Complete/Watch
Gantt Assumption & Source Notes
Portfolio chart uses actual project dates from Schedule & Gantt. Individual project Gantts use WBS elements from EVM Data and allocate each WBS task sequentially across the project date range by planned-cost weight because WBS-level start/end dates are not present in the source data.
Visual Style Applied
Tufte-style cleanup applied: muted functional colors, reduced chart ink, no decorative frames, minimized gridlines, and hidden Gantt legends where the dummy start series adds no meaning.

## Control Tower Dashboard
⚓ PROJECT CONTROL TOWER DASHBOARD
Relational EVM & Analytical Controller Dashboard ¦ PRINCE2 Compliance ¦ Refreshed from 8 CSV sources
BUDGET (BAC) |  | ACTUAL COST (AC) |  | EARNED VALUE (EV) |  | CPI |  | PROGRESS |  | Metric | Value | Signal | Owner
7100000 |  | 5220810 |  | 4752500 |  | 0.9103 |  | 66.94% |  | Active RAID | 3 | Open risk exposure | Risk Audit
[10 empty] | Overtime Events | 8 | Capacity anomaly | Risk Audit
Executive Portfolio Summary | [9 empty] | Large Purchases | 5 | Procurement control | Risk Audit
The portfolio contains 6 projects with a total BAC of $7,100,000, actual cost of $5,220,810, and earned value of $4,752,500. Current CPI is 0.91, meaning the portfolio is earning about $0.91 for every $1.00 spent. The largest executive pressure is cost control: PRJ-001 is over budget, while three active projects remain below CPI 1.00. | [9 empty] | Labor Share | 79.47% | Cost mix | CFO
[10 empty] | Material Share | 20.53% | Cost mix | CFO
[10 empty] | Worst Project CPI | 0.80728 | Cost pressure | Executive
Portfolio Project Breakdown
Project ID | Project Name | Manager | BAC | AC | EV | CPI | Progress | Status
PRJ-001 | Composite Maritime Vessel Construction | Morten Hansen | 1500000 | 1848810 | 1492500 | 80.73% | 99.5% | 1858100.5025 | 🔴 Over Budget
PRJ-002 | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 800000 | 0 | 0 | 100% | 0% |  | ⚪ Planned
PRJ-003 | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 1200000 | 382500 | 360000 | 94.12% | 30% | 1275000 | 🔴 Overrun Warn
PRJ-004 | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 2000000 | 1476000 | 1400000 | 94.85% | 70% | 2108571.4286 | 🔴 Overrun Warn
PRJ-005 | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 1000000 | 927000 | 900000 | 97.09% | 90% | 1030000 | 🟡 Within Margins
PRJ-006 | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 600000 | 586500 | 600000 | 102.3% | 100% | 586500 | 🟢 Completed
WBS Element Performance Details
WBS Code | Element Name | BAC | AC | EV | CPI | Progress | EAC Typical | Status
1 | Project Management & Engineering | 300000 | 419230 | 292500 | 0.69771 | 97.5% | 42997949% | 🔴 Overrun
2 | Hull Fabrication & Assembly | 600000 | 620450 | 600000 | 0.96704 | 100% | 62045000% | 🟡 Complete/Watch
3 | Outfitting & Integration | 400000 | 540445 | 400000 | 0.74013 | 100% | 54044500% | 🔴 Overrun
4 | Sea Trials & Handover | 200000 | 268685 | 200000 | 0.74437 | 100% | 26868500% | 🔴 Overrun
1 | Design & CFD Analysis | 300000 | 0 | 0 | 1 | 0% |  | ⚪ Planned
2 | Material Procurement | 500000 | 0 | 0 | 1 | 0% |  | ⚪ Planned
1 | Structural Frame Engineering | 400000 | 332500 | 360000 | 1.0827 | 90% | 36944444% | 🟢 On Track
2 | Steel Fabrication | 800000 | 50000 | 0 | 0 | 0% |  | 🔴 Overrun
1 | Engineering Drawings & Class Approval | 500000 | 456000 | 500000 | 1.0965 | 100% | 45600000% | 🟢 Completed
2 | Hull Welding & Assembly | 1500000 | 1020000 | 900000 | 0.88235 | 60% | 170000000% | 🔴 Overrun
1 | Project Control & PM | 200000 | 187000 | 200000 | 1.0695 | 100% | 18700000% | 🟢 Completed
2 | Pontoon Assembly & Painting | 800000 | 740000 | 700000 | 0.94595 | 87.5% | 84571429% | 🟡 Watch
1 | Hatch Engineering & FEA | 200000 | 180500 | 200000 | 1.108 | 100% | 18050000% | 🟢 Completed
2 | Molding & Testing | 400000 | 406000 | 400000 | 0.98522 | 100% | 40600000% | 🟡 Complete/Watch

## Data Model Map
PROJECT CONTROLLING DATA MODEL MAP
ERD-driven source-table relationships and integrity rules from datamodel_erd.md
Relational Model Summary
The workbook follows the ERD pattern: Projects contain WBS elements; WBS elements receive resource assignments, timesheets, material costs, and physical-progress records; resources log hours; RAID items track risks/issues/dependencies. EVM is calculated by joining these tables at WBS level and rolling up to project and portfolio level. The modern-PM audit below extends this model with required gaps for PV/SPI, stage-gates, portfolio governance, stakeholder reporting, cash-flow/WIP, quality, and lessons learned.
Entity / Table | Primary Key | Key Foreign Keys | Purpose | Workbook Location
Projects | ProjectID | — | Project master, manager, BAC, dates, status | Source Data / Project_Summary
WBS_ELEMENTS | WBS_ID | ProjectID | Work package budget and planned hours | Source Data / WBS_Performance
Resources | ResourceID | — | People/roles/rates | Source Data / CFO Audit
Resource_Assignments | AssignmentID | WBS_ID, ResourceID | Planned resource allocation | Source Data
Timesheets | TimesheetID | WBS_ID, ResourceID | Actual labor hours | Source Data / WBS_Source_Summary
Material_Costs | PurchaseID | WBS_ID | Actual material/procurement cost | Source Data / Risk Audit
Physical_Progress | ProgressID | WBS_ID | Physical completion records driving EV | Source Data / EVM Data
RAID_Log | RiskID | — | Risks, assumptions, issues, dependencies | Source Data / Risk Audit
Integrity Rules
Rule | Relationship / Logic | Workbook Check
Projects to WBS | 1:N; each WBS element belongs to one project. | WBS ProjectID must exist in Projects.
Resources to timesheets | 1:N; each timesheet row has a valid resource. | Timesheet ResourceID must exist in Resources.
WBS to timesheets/materials/progress | 1:N; actuals and EV attach to WBS. | WBS_ID must exist in WBS table.
Labor cost | Actual Labor Cost = HoursWorked * HourlyRate. | WBS_Source_Summary LaborCost reconciles to timesheets.
Material cost | Actual material cost is summed by WBS. | Large purchases > $50k are flagged.
Earned value | EV = PlannedCost * PercentComplete. | WBS_Performance EV column.
Project rollup | Project AC/EV/CPI sums from WBS rows. | Project_Summary table.
Workbook Data Flow
Layer | Tables / Sheets | Output
Raw source | Source Data tables | CSV import layer
WBS calculation | EVM Data!WBS_Performance | AC, EV, CPI, EAC by WBS
Project rollup | EVM Data!Project_Summary | BAC, AC, EV, CPI by project
Executive reporting | Control Tower Dashboard | Portfolio KPIs and charts
Exception control | CFO / Risk Audit sheets | Overtime, procurement, RAID, cost share
Decision support | Interactive Simulator | Corrective-action scenario impact
Modern PM / Controlling Readiness Audit
Audit based on glossary.md, modern_pm.md, and PM-Simplified.md: the workbook has a strong EVM cost spine (BAC, AC, EV, CPI, EAC), source-table ERD, RAID log, and executive dashboard. The main modern-PM gaps are PV/SPI/schedule variance, stage-gate metadata, stakeholder-specific reporting slices, revenue/cash-flow/WIP fields, resource capacity baselines, quality KPIs, and quantified risk exposure. These gaps matter because modern project controlling combines EVM, hybrid/stage-gate governance, portfolio dashboards, margin/cash-flow views, and BI-ready data definitions.
Modern PM Requirement | Readiness | Evidence in Current Workbook | Data Model / Workbook Action
EVM core: BAC / AC / EV / CPI | Present | Dashboard and EVM Data include BAC, AC, EV, CPI and EAC. | Retain as core fact layer; add formal PV/SPI.
PV / SV / SPI schedule EVM | Gap | Glossary and modern_pm emphasize PV, SV = EV-PV, SPI = EV/PV. Workbook lacks PV baseline by date. | Add planned value curve by WBS/date and SPI in EVM Data.
Objective physical progress | Partial | Physical progress table exists and drives EV, but measurement method/acceptance criteria are not stored. | Add progress basis, milestone acceptance, and reported evidence fields.
EAC / ETC / VAC / TCPI | Partial | EAC exists; ETC/VAC/TCPI are not explicit portfolio metrics. | Add ETC=EAC-AC, VAC=BAC-EAC, TCPI=(BAC-EV)/(BAC-AC).
Hybrid / agile / stage-gate governance | Gap | Guidance recommends agile within stage-gate for complex projects; workbook has no phase/gate entities. | Add Stage, Gate, Decision, Gate Status, Approval Date fields.
Portfolio management / PPM | Partial | Portfolio dashboard compares projects, but prioritization/resource-capacity scoring is missing. | Add strategic priority, capacity demand, and portfolio rank.
Stakeholder reporting hierarchy | Partial | Executive dashboard exists; role-specific views for PL/PMO/CFO/team are not formalized. | Add stakeholder-to-KPI matrix and report cadence fields.
Resource utilization / capacity | Partial | Timesheets and overtime flags exist; planned availability/capacity baseline is missing. | Add weekly capacity per resource and utilization %.
Risk reserve / quantified exposure | Partial | RAID captures probability/impact qualitatively but not monetary exposure. | Add probability %, impact cost, exposure, reserve, due date.
Margin / revenue / cash-flow / WIP | Gap | Glossary highlights margin, revenue recognition, cash flow, WIP, DSO; workbook is cost/EVM only. | Add contract value, billing milestones, AR/WIP/cash flow fields.
Quality / rework KPIs | Gap | Modern PM expects quality/rework signals; workbook has no defect/rework data. | Add defect count, rework cost, acceptance status.
Lessons learned / continuous improvement | Gap | Guidance recommends retrospectives and learning loops; no lessons table exists. | Add lessons learned register by project/WBS.
KPI / Data Gaps to Close
KPI / Field | Full Name | Formula / Definition | Why It Matters
PV | Planned Value | PV = budgeted work scheduled by status date | Needed for SV and SPI.
SV | Schedule Variance | SV = EV - PV | Needed to distinguish cost pressure from schedule slip.
SPI | Schedule Performance Index | SPI = EV / PV | Modern schedule EVM thresholding.
ETC | Estimate to Complete | ETC = EAC - AC | Shows remaining funding need.
VAC | Variance at Completion | VAC = BAC - EAC | Forecast underrun/overrun at finish.
TCPI | To-Complete Performance Index | TCPI = (BAC - EV) / (BAC - AC) | Shows required future efficiency to hit budget.
WIP / Billing | Work performed vs invoiced | WIP = earned/recognized value - billed value | Needed for cash-flow risk and revenue recognition.
DSO | Days Sales Outstanding | AR / average daily sales | Needed for liquidity tracking.
Stakeholder Data Needs
Stakeholder | Reporting Cadence | Core Data Need | Current Gap / Action
Project Manager | Weekly project control | Milestones, critical path, RAID, CPI/SPI, recovery actions | Needs schedule baseline + risk action due dates.
Project Controller | Weekly/monthly controlling | AC, EV, PV, CPI, SPI, EAC, ETC, VAC, TCPI, margin | Needs PV/SPI and revenue/margin fields.
PMO / Project Support | Cadence and data quality | Data completeness, approvals, status logs, lessons learned | Needs data-quality and workflow status fields.
CFO / Executive | Monthly/board pack | Margin at completion, cash flow, WIP, risk reserve, portfolio rank | Needs contract value, billing, WIP and cash-flow schedule.
Project Team | Weekly execution view | Task status, blockers, resource load, quality issues | Needs task-level status/quality fields.

## 3S Readiness Audit
3-STATEMENT MODEL READINESS AUDIT
Audit of current project-control workbook against integrated IS / BS / CF model requirements
Executive Assessment
The current workbook is strong as an EVM/project-control model, but it is not yet a complete 3-statement financial model. It contains cost, earned value, resource, procurement, RAID, and scenario data that can feed parts of an Income Statement and operating forecast; however, it lacks full revenue recognition, Balance Sheet accounts, working-capital schedules, debt/equity schedules, tax/NOL logic, and Cash Flow Statement tie-outs. The readiness status is therefore 'PARTIAL — project-cost model ready, corporate 3-statement model not ready'.
Readiness Metric | Live Value | Status
Portfolio BAC | 7100000 | Available as project budget, not revenue.
Actual Cost | 5220810 | Available as operating/project cost base.
Earned Value | 4752500 | Available as EVM production value, not GAAP revenue.
Portfolio CPI | 0.9103 | Useful for forecast/EAC stress testing.
Progress | 66.94% | Useful for revenue/progress recognition proxy only if policy confirmed.
Statement Area | Required Component | Readiness | Workbook Evidence | Next Action
Income Statement | Revenue / Net Sales | Missing | No customer revenue, contract value, or revenue-recognition policy is in the workbook. | Add contract revenue schedule by project and period.
Income Statement | COGS / Direct Costs | Partial | Labor and material costs exist by WBS and project. | Map WBS actual/projected cost into cost of revenue.
Income Statement | Gross Profit / Margins | Missing | No revenue line means gross profit and margins cannot be calculated. | Add revenue and cost-of-revenue classification.
Income Statement | Operating Expenses | Missing | No SG&A, R&D, overhead, D&A, SBC, or other OpEx categories. | Add OpEx assumptions by period.
Income Statement | EBIT / EBITDA / Taxes / Net Income | Missing | No D&A, interest, tax, or income statement closeout. | Add D&A, debt/interest, tax/NOL schedules.
Balance Sheet | Cash | Missing | Simulator shows cost impact but no formal cash balance. | Add opening cash and CF-linked ending cash.
Balance Sheet | Working Capital | Missing | No AR, inventory, AP, DSO, DIO, DPO schedules. | Add WC schedule linked to revenue/COGS.
Balance Sheet | PP&E / D&A | Missing | No fixed asset roll-forward or depreciation schedule. | Add CapEx and depreciation schedule.
Balance Sheet | Debt / Equity | Missing | No debt balance, interest rate, repayment, equity, retained earnings. | Add debt and equity schedules.
Cash Flow Statement | CFO | Missing | No net income, non-cash addbacks, or WC movement. | Build CFO from IS + WC + D&A.
Cash Flow Statement | CFI | Missing | No CapEx or investing activities. | Add CapEx assumptions and PP&E linkage.
Cash Flow Statement | CFF | Missing | No debt/equity/dividend activity. | Add financing schedules.
Checks | BS Balance | Missing | No assets/liabilities/equity structure exists. | Add Assets - Liabilities - Equity check.
Checks | Cash Tie-Out | Missing | No CF ending cash or BS cash. | Add CF ending cash = BS cash check.
Checks | Formula Integrity | Partial | EVM formulas exist and no visible errors were previously verified. | Add statement-specific checks once IS/BS/CF are created.
Master 3-Statement Readiness Status
Check | Formula / Logic | Result
Formal IS/BS/CF tabs present | Income Statement, Balance Sheet, Cash Flow Statement tabs exist | FALSE
Project-control source data present | BAC, AC and EV are populated | TRUE
Overall readiness | Combines formal statement tabs and source-data availability | PARTIAL — EVM/cost data available; IS/BS/CF missing

## 3S Model Blueprint
3-STATEMENT MODEL BLUEPRINT
Recommended build path to convert the EVM workbook into an integrated Income Statement / Balance Sheet / Cash Flow model
Recommended Tab Architecture
Proposed Sheet | Purpose | Primary Inputs | Key Outputs | Build Priority
Assumptions | Scenario toggle, fiscal periods, revenue policy, tax rate, working-capital days, CapEx %, debt terms | User inputs / management assumptions | Drivers for IS/BS/CF | 1
Income Statement | Revenue, COGS, OpEx, D&A, EBIT, interest, tax, net income | Revenue schedule + WBS costs + assumptions | Net Income, EBITDA, margins | 2
Working Capital | AR, inventory, AP, DSO/DIO/DPO and ΔNWC | Revenue, COGS, WC day assumptions | ΔWC for CFO, BS current accounts | 3
PP&E / D&A | Gross PP&E, CapEx, accumulated depreciation, net PP&E | CapEx %, depreciation life | D&A, PP&E net | 4
Debt Schedule | Debt roll-forward, interest expense, repayments | Opening debt, rates, repayments | Interest expense, ending debt | 5
Balance Sheet | Assets, liabilities, equity, retained earnings | IS + WC + D&A + debt + CF | Balanced BS, cash, equity | 6
Cash Flow Statement | CFO, CFI, CFF, ending cash | IS + BS changes + schedules | Ending cash and FCF | 7
3S Checks | BS balance, cash tie-out, NI link, RE roll-forward, formula integrity | All model tabs | Master check status | 8
Current Workbook Data Mapping
Existing Workbook Source | Can Feed 3S Line Item | Limitation / Assumption Needed | Suggested Formula Logic
Project_Summary[BAC] | Backlog / contract budget / project budget | Not equivalent to GAAP revenue unless revenue policy is confirmed. | Revenue schedule should reference contract value and % complete rules.
WBS_Performance[Labor Cost] | Direct labor / cost of revenue | Need classification between COGS vs SG&A/engineering overhead. | Cost of Revenue = classified labor + materials.
WBS_Performance[Material Cost] | Material COGS / inventory consumption | Need inventory vs direct-expense policy. | COGS = material usage or purchases depending policy.
WBS_Performance[EV] | Progress / production value proxy | EV is not automatically revenue. | Revenue = contract value × recognized progress if policy allows.
WBS_Performance[EAC Typical] | Forecast project cost | Useful for cost forecast but not full financial statement. | Forecast COGS = EAC by project/WBS.
Weekly_Overtime | Labor risk / productivity pressure | Does not directly post to financial statements. | Use as margin risk driver or contingency flag.
RAID | Risk reserve / disclosure input | Requires quantified probability × impact to affect model. | Contingency = SUM(probability × impact).
Core 3S Checks to Add After Build
Check | Formula Pattern | Expected Result
Balance Sheet Balance | Total Assets - Total Liabilities - Total Equity | 0
Cash Tie-Out | CF Ending Cash - BS Cash | 0
Net Income Link | IS Net Income - CF Starting Net Income | 0
Retained Earnings | Prior RE + Net Income - Dividends - Ending RE | 0
Debt Tie-Out | Debt Schedule Ending Debt - BS Total Debt | 0
Formula Errors | COUNT of #REF!, #DIV/0!, #VALUE!, #NAME? across model ranges | 0
Formula Color Convention
Convention | Color | Meaning | Applied To
Blue font | #0000FF | Hardcoded input | Assumptions and historical data
Black font | #000000 | Calculation formula | Operating calculations
Purple font | #800080 | Same-sheet link | Line-item references
Green font | #008000 | Cross-sheet link | Statement and schedule links

## Schedule & Gantt
📅 PORTFOLIO GANTT & SCHEDULE
Project start/end dates from projects.csv with month-level timeline
Project ID | Project / Task | Start Date | End Date | Duration (Days) | Status | Manager | Critical? | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01
PRJ-001 | Composite Maritime Vessel Construction | 2026-01-01 | 2026-06-30 | 181 | Completed | Morten Hansen | Yes | ■ | ■ | ■ | ■ | ■ | ■
PRJ-002 | Patrol Vessel Carbon Mold Design | 2026-08-01 | 2026-12-31 | 153 | Planned | Morten Hansen | No
PRJ-003 | Subsea Cable Installation Frame | 2026-05-01 | 2026-10-31 | 184 | Active | Erik Johansen | No |  |  |  |  | ■ | ■
PRJ-004 | Autonomous Workboat Hull Weldments | 2026-03-01 | 2026-08-31 | 184 | Active | Astrid Nilsen | Yes |  |  | ■ | ■ | ■ | ■
PRJ-005 | Defense Logistics Pontoon Build | 2026-02-01 | 2026-07-31 | 181 | Active | Frank Ellingsen | Yes |  | ■ | ■ | ■ | ■ | ■
PRJ-006 | Lightweight Composite Cargo Hatch | 2026-04-01 | 2026-05-31 | 61 | Completed | Morten Hansen | No |  |  |  | ■ | ■

## CFO & Cost Share Audit
💼 CFO PROFITABILITY & COST SHARE AUDIT
Resource and material allocations, burn rates, and cost-share indicators
Cost-Share Breakdown
Category | Actual Cost (USD) | Share %
Labor Costs | 4148810 | 79.47%
Material & Procurement Costs | 1072000 | 20.53%
TOTAL ACTUAL COST | 5220810 | 100%
Resource Burn Rates
Resource Name | Role | Hourly Rate (USD) | Hours Logged | Total Cost Logged (USD)
Astrid Nilsen | Structural Welder | 700 | 4290.1143 | 3003080
Erik Johansen | Senior Design Engineer | 950 | 1228.5053 | 1167080
Lars Olsen | Marine Electrician | 750 | 498.8 | 374100
Morten Hansen | Project Manager | 1000 | 743.5 | 743500
Frank Ellingsen | Project Controller | 850 | 382.3 | 324955

## Contract & RAID Risk Audit
🚨 CONTRACT, RISK & ANOMALY AUDIT
Weekly overtime limits, high-value invoices, and active RAID registry
Overtime Audits (>45 Hours/Week)
WBS-013 | 1 | 180500 | 0
WBS-014 | 1 | 336000 | 70000
2026-11 | Erik Johansen | Senior Design Engineer | 480
2025-46 | Astrid Nilsen | Structural Welder | 461.5
2026-19 | Erik Johansen | Senior Design Engineer | 389.5
2026-08 | Frank Ellingsen | Project Controller | 133.3
2025-42 | Morten Hansen | Project Manager | 200
2026-13 | Astrid Nilsen | Structural Welder | 46.3
Large Procurement Audits (>$50,000)
Purchase Date | Invoice Number | Description | Cost (USD)
2026-03-25 | MAT-4001 | Consumables & Steel Plates | 250000
2026-03-01 | MAT-5001 | Paint & Marine Alloy Plates | 180000
2026-02-05 | INV-001 | Structural Composite Carbon Sheets | 150000
2026-05-02 | INV-007 | Twin Electric Inboard Engines | 130000
2025-11-01 | MAT-6001 | Composite Cutting Fiber | 70000
Active RAID Log Register
RAID ID | Category | Description | Impact | Probability | Mitigation Strategy | Owner | Status
R-001 | Risk | Delay in composite carbon sheet deliveries from overseas supplier | High | Medium | Pre-order early or source alternative local supplier | Morten Hansen | Active
I-001 | Issue | Astrid Nilsen welder overtime limit breached due to recovery fabrication schedule | Medium | High | Allocate junior welder to assist with low-priority tasks | Morten Hansen | Active
D-001 | Dependency | Sea trials (WBS 4.0) depend on DNV safety and compliance certification approval | High | High | Submit compliance paperwork 2 weeks in advance of handover date | Frank Ellingsen | Active

## Interactive Simulator
🎛️ WHAT-IF CORRECTIVE ACTION & CRASH SIMULATOR
Edit yellow input cells to simulate corrective actions, rate savings, and schedule crashing
Simulator Inputs (Editable)
Simulated Labor Rate Savings (%) | 5%
Simulated Material Price Savings (%) | 10%
Contract Delay Penalty (USD/Day) | 10000
Crash Schedule? (0=No, 5=Crash 5 Days, 10=Crash 10 Days) | 5
Simulation Results (Calculated)
Current Baseline BAC (USD) | 7100000
Current Actual Cost AC (USD) | 5220810
Current Earned Value EV (USD) | 4752500
Simulated Actual Cost (AC) USD | 4916169.5
Simulated CPI | 0.96671
Simulated Estimate At Completion (EAC) USD | 7344514.1399
Simulated Schedule Delay (Days) | 5
Simulated Liquidated Damages Penalty (USD) | 50000
Direct Schedule Crashing Cost (USD) | 10000
Net Crashing Trade-off Benefit (USD) | 40000

## EVM Data
EVM CALCULATION MODEL
Live formulas calculate AC, EV, CPI, EAC and statuses from Source Data tables
WBS_ID | ProjectID | WBS Code | Element Name | Project Name | Manager | BAC | Latest Progress | Labor Cost | Material Cost | AC | EV | CPI | EAC Typical | Status | WBS_ID | LatestProgress | LaborCost | MaterialCost | WBS_ID | LatestProgress | LaborCost | MaterialCost
WBS-001 | PRJ-001 | 1 | Project Management & Engineering | Composite Maritime Vessel Construction | Morten Hansen | 300000 | 97.5% | 419230 | 0 | 419230 | 292500 | 0.69771 | 429979.4872 | 🔴 Overrun | WBS-001 | 0.975 | 419230 | 0 | WBS-001 | 0.975 | 419230 | 0
WBS-002 | PRJ-001 | 2 | Hull Fabrication & Assembly | Composite Maritime Vessel Construction | Morten Hansen | 600000 | 100% | 374950 | 245500 | 620450 | 600000 | 0.96704 | 620450 | 🟡 Complete/Watch | WBS-002 | 1 | 374950 | 245500 | WBS-002 | 1 | 374950 | 245500
WBS-003 | PRJ-001 | 3 | Outfitting & Integration | Composite Maritime Vessel Construction | Morten Hansen | 400000 | 100% | 297445 | 243000 | 540445 | 400000 | 0.74013 | 540445 | 🔴 Overrun | WBS-003 | 1 | 297445 | 243000 | WBS-003 | 1 | 297445 | 243000
WBS-004 | PRJ-001 | 4 | Sea Trials & Handover | Composite Maritime Vessel Construction | Morten Hansen | 200000 | 100% | 235185 | 33500 | 268685 | 200000 | 0.74437 | 268685 | 🔴 Overrun | WBS-004 | 1 | 235185 | 33500 | WBS-004 | 1 | 235185 | 33500
WBS-005 | PRJ-002 | 1 | Design & CFD Analysis | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 300000 | 0% | 0 | 0 | 0 | 0 | 1 |  | ⚪ Planned | WBS-005 | 0 | 0 | 0 | WBS-005 | 0 | 0 | 0
WBS-006 | PRJ-002 | 2 | Material Procurement | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 500000 | 0% | 0 | 0 | 0 | 0 | 1 |  | ⚪ Planned | WBS-006 | 0 | 0 | 0 | WBS-006 | 0 | 0 | 0
WBS-007 | PRJ-003 | 1 | Structural Frame Engineering | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 400000 | 90% | 332500 | 0 | 332500 | 360000 | 1.0827 | 369444.4444 | 🟢 On Track | WBS-007 | 0.9 | 332500 | 0 | WBS-007 | 0.9 | 332500 | 0
WBS-008 | PRJ-003 | 2 | Steel Fabrication | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 800000 | 0% | 0 | 50000 | 50000 | 0 | 0 |  | 🔴 Overrun | WBS-008 | 0 | 0 | 50000 | WBS-008 | 0 | 0 | 50000
WBS-009 | PRJ-004 | 1 | Engineering Drawings & Class Approval | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 500000 | 100% | 456000 | 0 | 456000 | 500000 | 1.0965 | 456000 | 🟢 Completed | WBS-009 | 1 | 456000 | 0 | WBS-009 | 1 | 456000 | 0
WBS-010 | PRJ-004 | 2 | Hull Welding & Assembly | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 1500000 | 60% | 770000 | 250000 | 1020000 | 900000 | 0.88235 | 1700000 | 🔴 Overrun | WBS-010 | 0.6 | 770000 | 250000 | WBS-010 | 0.6 | 770000 | 250000
WBS-011 | PRJ-005 | 1 | Project Control & PM | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 200000 | 100% | 187000 | 0 | 187000 | 200000 | 1.0695 | 187000 | 🟢 Completed | WBS-011 | 1 | 187000 | 0 | WBS-011 | 1 | 187000 | 0
WBS-012 | PRJ-005 | 2 | Pontoon Assembly & Painting | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 800000 | 87.5% | 560000 | 180000 | 740000 | 700000 | 0.94595 | 845714.2857 | 🟡 Watch | WBS-012 | 0.875 | 560000 | 180000 | WBS-012 | 0.875 | 560000 | 180000
WBS-013 | PRJ-006 | 1 | Hatch Engineering & FEA | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 200000 | 100% | 180500 | 0 | 180500 | 200000 | 1.108 | 180500 | 🟢 Completed | WBS-013 | 1 | 180500 | 0 | WBS-013 | 1 | 180500 | 0
WBS-014 | PRJ-006 | 2 | Molding & Testing | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 400000 | 100% | 336000 | 70000 | 406000 | 400000 | 0.98522 | 406000 | 🟡 Complete/Watch | WBS-014 | 1 | 336000 | 70000 | WBS-014 | 1 | 336000 | 70000
[15 empty] | 2026-11 | Erik Johansen | Senior Design Engineer | 480
[15 empty] | 2025-46 | Astrid Nilsen | Structural Welder | 461.5
[15 empty] | 2026-19 | Erik Johansen | Senior Design Engineer | 389.5
[15 empty] | 2026-08 | Frank Ellingsen | Project Controller | 133.3
Project ID | Project Name | Project Manager | BAC | AC | EV | CPI | Progress | EAC Typical | Status | [5 empty] | 2025-42 | Morten Hansen | Project Manager | 200
PRJ-001 | Composite Maritime Vessel Construction | Morten Hansen | 1500000 | 1848810 | 1492500 | 0.80728 | 99.5% | 1858100.5025 | 🔴 Over Budget | [5 empty] | 2026-13 | Astrid Nilsen | Structural Welder | 46.3
PRJ-002 | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 800000 | 0 | 0 | 1 | 0% |  | ⚪ Planned
PRJ-003 | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 1200000 | 382500 | 360000 | 0.94118 | 30% | 1275000 | 🔴 Overrun Warn
PRJ-004 | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 2000000 | 1476000 | 1400000 | 0.94851 | 70% | 2108571.4286 | 🔴 Overrun Warn
PRJ-005 | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 1000000 | 927000 | 900000 | 0.97087 | 90% | 1030000 | 🟡 Within Margins
PRJ-006 | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 600000 | 586500 | 600000 | 1.023 | 100% | 586500 | 🟢 Completed

## Source Data
SOURCE DATA TABLES
Attached CSV files imported as structured tables for refreshable formulas
Projects
ProjectID | ProjectName | ProjectManager | BudgetAtCompletion_BAC | StartDate | EndDate | Status
PRJ-001 | Composite Maritime Vessel Construction | Morten Hansen | 1500000 | 2026-01-01 | 2026-06-30 | Completed
PRJ-002 | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 800000 | 2026-08-01 | 2026-12-31 | Planned
PRJ-003 | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 1200000 | 2026-05-01 | 2026-10-31 | Active
PRJ-004 | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 2000000 | 2026-03-01 | 2026-08-31 | Active
PRJ-005 | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 1000000 | 2026-02-01 | 2026-07-31 | Active
PRJ-006 | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 600000 | 2026-04-01 | 2026-05-31 | Completed
WBS
WBS_ID | ProjectID | WBS_Code | ElementName | PlannedCost | PlannedHours
WBS-001 | PRJ-001 | 1 | Project Management & Engineering | 300000 | 400
WBS-002 | PRJ-001 | 2 | Hull Fabrication & Assembly | 600000 | 1200
WBS-003 | PRJ-001 | 3 | Outfitting & Integration | 400000 | 800
WBS-004 | PRJ-001 | 4 | Sea Trials & Handover | 200000 | 300
WBS-005 | PRJ-002 | 1 | Design & CFD Analysis | 300000 | 300
WBS-006 | PRJ-002 | 2 | Steel Fabrication | 500000 | 800
WBS-007 | PRJ-003 | 1 | Structural Frame Engineering | 400000 | 500
WBS-008 | PRJ-003 | 2 | Material Procurement | 500000 | 200
WBS-009 | PRJ-003 | 3 | Deck Assembly | 300000 | 450
WBS-010 | PRJ-004 | 1 | Engineering Drawings & Class Approval | 500000 | 550
WBS-011 | PRJ-004 | 2 | Hull Welding & Assembly | 1500000 | 1800
WBS-012 | PRJ-005 | 1 | Project Control & PM | 200000 | 250
WBS-013 | PRJ-005 | 2 | Pontoon Assembly & Painting | 800000 | 1000
WBS-014 | PRJ-006 | 1 | Hatch Engineering & FEA | 200000 | 250
WBS-015 | PRJ-006 | 2 | Molding & Testing | 400000 | 600
Progress
ProgressID | WBS_ID | RecordDate | PercentComplete | ReportedBy
PRG-0001 | WBS-001 | 2026-01-07 | 0.039 | Frank Ellingsen
PRG-0002 | WBS-001 | 2026-01-14 | 0.078 | Frank Ellingsen
PRG-0003 | WBS-001 | 2026-01-21 | 0.117 | Frank Ellingsen
PRG-0004 | WBS-001 | 2026-01-28 | 0.156 | Frank Ellingsen
PRG-0005 | WBS-001 | 2026-02-04 | 0.195 | Frank Ellingsen
PRG-0006 | WBS-001 | 2026-02-11 | 0.234 | Frank Ellingsen
PRG-0007 | WBS-001 | 2026-02-18 | 0.273 | Frank Ellingsen
PRG-0008 | WBS-001 | 2026-02-25 | 0.312 | Frank Ellingsen
PRG-0009 | WBS-001 | 2026-03-04 | 0.351 | Frank Ellingsen
PRG-0010 | WBS-001 | 2026-03-11 | 0.39 | Frank Ellingsen
PRG-0011 | WBS-001 | 2026-03-18 | 0.429 | Frank Ellingsen
PRG-0012 | WBS-001 | 2026-03-25 | 0.468 | Frank Ellingsen
PRG-0013 | WBS-001 | 2026-04-01 | 0.507 | Frank Ellingsen
PRG-0014 | WBS-001 | 2026-04-08 | 0.546 | Frank Ellingsen
PRG-0015 | WBS-001 | 2026-04-15 | 0.585 | Frank Ellingsen
PRG-0016 | WBS-001 | 2026-04-22 | 0.624 | Frank Ellingsen
PRG-0017 | WBS-001 | 2026-04-29 | 0.663 | Frank Ellingsen
PRG-0018 | WBS-001 | 2026-05-06 | 0.702 | Frank Ellingsen
PRG-0019 | WBS-001 | 2026-05-13 | 0.741 | Frank Ellingsen
PRG-0020 | WBS-001 | 2026-05-20 | 0.78 | Frank Ellingsen
PRG-0021 | WBS-001 | 2026-05-27 | 0.819 | Frank Ellingsen
PRG-0022 | WBS-001 | 2026-06-03 | 0.858 | Frank Ellingsen
PRG-0023 | WBS-001 | 2026-06-10 | 0.897 | Frank Ellingsen
PRG-0024 | WBS-001 | 2026-06-17 | 0.936 | Frank Ellingsen
PRG-0025 | WBS-001 | 2026-06-24 | 0.975 | Frank Ellingsen
PRG-0026 | WBS-002 | 2026-02-15 | 0.25 | Morten Hansen
PRG-0027 | WBS-002 | 2026-03-01 | 0.5 | Morten Hansen
PRG-0028 | WBS-002 | 2026-03-15 | 0.75 | Morten Hansen
PRG-0029 | WBS-002 | 2026-04-01 | 1 | Morten Hansen
PRG-0030 | WBS-003 | 2026-04-15 | 0.5 | Frank Ellingsen
PRG-0031 | WBS-003 | 2026-05-15 | 1 | Frank Ellingsen
PRG-0032 | WBS-004 | 2026-06-15 | 1 | Morten Hansen
PRG-0033 | WBS-007 | 2026-06-01 | 0.3 | Erik Johansen
PRG-0034 | WBS-007 | 2026-07-01 | 0.6 | Erik Johansen
PRG-0035 | WBS-007 | 2026-08-01 | 0.9 | Erik Johansen
PRG-0036 | WBS-010 | 2026-03-20 | 0.5 | Astrid Nilsen
PRG-0037 | WBS-010 | 2026-04-20 | 1 | Astrid Nilsen
PRG-0038 | WBS-011 | 2026-05-15 | 0.3 | Astrid Nilsen
PRG-0039 | WBS-011 | 2026-06-15 | 0.6 | Astrid Nilsen
PRG-0040 | WBS-012 | 2026-02-28 | 0.4 | Frank Ellingsen
PRG-0041 | WBS-012 | 2026-03-31 | 0.8 | Frank Ellingsen
PRG-0042 | WBS-012 | 2026-04-30 | 1 | Frank Ellingsen
PRG-0043 | WBS-013 | 2026-03-31 | 0.25 | Frank Ellingsen
PRG-0044 | WBS-013 | 2026-04-30 | 0.5 | Frank Ellingsen
PRG-0045 | WBS-013 | 2026-05-31 | 0.75 | Frank Ellingsen
PRG-0046 | WBS-013 | 2026-06-30 | 0.875 | Frank Ellingsen
PRG-0047 | WBS-014 | 2026-04-10 | 0.5 | Morten Hansen
PRG-0048 | WBS-014 | 2026-04-30 | 1 | Morten Hansen
PRG-0049 | WBS-015 | 2026-05-10 | 0.5 | Morten Hansen
PRG-0050 | WBS-015 | 2026-05-30 | 1 | Morten Hansen
PRG-0051 | WBS-009 | 2026-06-01 | 0.1 | Erik Johansen
PRG-0052 | WBS-009 | 2026-07-01 | 0.2 | Erik Johansen
PRG-0053 | WBS-011 | 2026-07-15 | 0.6 | Astrid Nilsen
PRG-0054 | WBS-013 | 2026-07-15 | 0.875 | Frank Ellingsen
PRG-0055 | WBS-006 | 2026-08-01 | 0 | Morten Hansen
PRG-0056 | WBS-008 | 2026-08-01 | 0 | Erik Johansen
PRG-0057 | WBS-005 | 2026-08-01 | 0 | Morten Hansen
Resources
ResourceID | ResourceName | Role | HourlyRate
RES-001 | Frank Ellingsen | Project Controller | 850
RES-002 | Morten Hansen | Project Manager | 1000
RES-003 | Erik Johansen | Senior Design Engineer | 950
RES-004 | Astrid Nilsen | Structural Welder | 700
RES-005 | Lars Olsen | Marine Electrician | 750
Timesheets
TimesheetID | ResourceID | WBS_ID | WorkDate | HoursWorked | ApprovalStatus
TS-0001 | RES-001 | WBS-001 | 2026-01-02 | 4.1 | Approved
TS-0002 | RES-001 | WBS-001 | 2026-01-09 | 3.5 | Approved
TS-0003 | RES-001 | WBS-001 | 2026-01-16 | 3.8 | Approved
TS-0004 | RES-001 | WBS-001 | 2026-01-23 | 3.7 | Approved
TS-0005 | RES-001 | WBS-001 | 2026-01-30 | 4.2 | Approved
TS-0006 | RES-001 | WBS-001 | 2026-02-06 | 3.9 | Approved
TS-0007 | RES-001 | WBS-001 | 2026-02-13 | 4 | Approved
TS-0008 | RES-001 | WBS-001 | 2026-02-20 | 3.6 | Approved
TS-0009 | RES-001 | WBS-001 | 2026-02-27 | 3.8 | Approved
TS-0010 | RES-001 | WBS-001 | 2026-03-06 | 4 | Approved
TS-0011 | RES-001 | WBS-001 | 2026-03-13 | 4.1 | Approved
TS-0012 | RES-001 | WBS-001 | 2026-03-20 | 3.9 | Approved
TS-0013 | RES-001 | WBS-001 | 2026-03-27 | 4 | Approved
TS-0014 | RES-001 | WBS-001 | 2026-04-03 | 3.8 | Approved
TS-0015 | RES-001 | WBS-001 | 2026-04-10 | 4.1 | Approved
TS-0016 | RES-001 | WBS-001 | 2026-04-17 | 3.9 | Approved
TS-0017 | RES-001 | WBS-001 | 2026-04-24 | 3.7 | Approved
TS-0018 | RES-001 | WBS-001 | 2026-05-01 | 4 | Approved
TS-0019 | RES-001 | WBS-001 | 2026-05-08 | 3.8 | Approved
TS-0020 | RES-001 | WBS-001 | 2026-05-15 | 4.1 | Approved
TS-0021 | RES-001 | WBS-001 | 2026-05-22 | 3.9 | Approved
TS-0022 | RES-001 | WBS-001 | 2026-05-29 | 4 | Approved
TS-0023 | RES-001 | WBS-001 | 2026-06-05 | 3.8 | Approved
TS-0024 | RES-001 | WBS-001 | 2026-06-12 | 4.1 | Approved
TS-0025 | RES-001 | WBS-001 | 2026-06-19 | 3.9 | Approved
TS-0026 | RES-001 | WBS-001 | 2026-06-26 | 4 | Approved
TS-B001 | RES-002 | WBS-001 | 2026-01-15 | 200 | Approved
TS-B002 | RES-003 | WBS-001 | 2026-02-15 | 106.4 | Approved
TS-B003 | RES-004 | WBS-002 | 2026-02-15 | 461.5 | Approved
TS-B004 | RES-004 | WBS-002 | 2026-03-15 | 842.8 | Approved
TS-B005 | RES-004 | WBS-002 | 2026-04-15 | 1150.1 | Approved
TS-B006 | RES-003 | WBS-002 | 2026-02-15 | 200 | Approved
TS-B007 | RES-005 | WBS-003 | 2026-04-15 | 498.8 | Approved
TS-B008 | RES-002 | WBS-003 | 2026-05-15 | 100 | Approved
TS-B009 | RES-001 | WBS-004 | 2026-06-15 | 133.3 | Approved
TS-B010 | RES-003 | WBS-006 | 2026-08-01 | 52.6316 | Approved
TS-B011 | RES-003 | WBS-007 | 2026-06-15 | 389.4737 | Approved
TS-B012 | RES-003 | WBS-010 | 2026-03-15 | 480 | Approved
TS-B013 | RES-004 | WBS-011 | 2026-04-15 | 1100 | Approved
TS-B014 | RES-002 | WBS-011 | 2026-04-15 | 0 | Approved
TS-B015 | RES-001 | WBS-012 | 2026-03-15 | 147.3 | Approved
TS-B016 | RES-004 | WBS-013 | 2026-04-15 | 735.7143 | Approved
TS-B017 | RES-002 | WBS-014 | 2026-04-15 | 180.5 | Approved
TS-B018 | RES-002 | WBS-015 | 2026-05-15 | 263 | Approved
Materials
PurchaseID | WBS_ID | PurchaseDate | Description | Quantity | UnitPrice | TotalActualCost
INV-001 | WBS-002 | 2026-02-05 | Structural Composite Carbon Sheets | 10 | 15000 | 150000
INV-002 | WBS-002 | 2026-02-12 | Epoxy Resin Infusion Kit | 20 | 2500 | 50000
INV-003 | WBS-002 | 2026-02-28 | Steel Support Beam Frames | 4 | 8000 | 32000
INV-004 | WBS-002 | 2026-03-10 | Additional Epoxies (Overrun material) | 5 | 2700 | 13500
INV-005 | WBS-003 | 2026-04-05 | Marine Cabin Electrical Wiring | 2 | 12000 | 24000
INV-006 | WBS-003 | 2026-04-15 | Cabin Interior Composite Panels | 12 | 3500 | 42000
INV-007 | WBS-004 | 2026-05-02 | Twin Electric Inboard Engines | 2 | 65000 | 130000
MAT-3001 | WBS-007 | 2026-05-10 | Cable Frame Steel Kits | 1 | 12500 | 12500
MAT-4001 | WBS-011 | 2026-03-25 | Consumables & Steel Plates | 1 | 250000 | 250000
MAT-5001 | WBS-013 | 2026-03-01 | Paint & Marine Alloy Plates | 1 | 180000 | 180000
MAT-5002 | WBS-013 | 2026-04-01 | Pontoon Brackets | 1 | 45000 | 45000
MAT-6001 | WBS-015 | 2025-11-01 | Composite Cutting Fiber | 1 | 70000 | 70000
MAT-6002 | WBS-015 | 2026-04-15 | Mold Release and Vacuum Bagging | 1 | 18000 | 18000
MAT-6003 | WBS-015 | 2026-05-05 | Rework Material | 1 | 55000 | 55000
RAID
RiskID | Type | Description | Impact | Probability | MitigationStrategy | Owner | Status
R-001 | Risk | Delay in composite carbon sheet deliveries from overseas supplier | High | Medium | Pre-order early or source alternative local supplier | Morten Hansen | Active
A-001 | Assumption | Subcontractor electrician rates remain fixed under contract | Medium | Low | Keep signed SLA agreements as references | Frank Ellingsen | Closed
I-001 | Issue | Astrid Nilsen welder overtime limit breached due to recovery fabrication schedule | Medium | High | Allocate junior welder to assist with low-priority tasks | Morten Hansen | Active
D-001 | Dependency | Sea trials (WBS 4.0) depend on DNV safety and compliance certification approval | High | High | Submit compliance paperwork 2 weeks in advance of handover date | Frank Ellingsen | Active