## Slide 1
Q2 2026 / EXECUTIVE REVIEW
Project Portfolio
Executive Review
Six projects. One portfolio view.
Clear decisions on cost, schedule, and risk.
FRANK ELLINGSEN
Portfolio status report
Q2
26
PORTFOLIO WINDOW
Q4 2025 — Q4 2026
Internal management review

## Slide 2
PORTFOLIO SCHEDULE
Six projects span Q4 2025–Q4 2026
02
SCHEDULE
STATUS / COMPLETE
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Chart: 
| PRJ-006 Cargo Hatch | PRJ-005 Logistics Pontoon | PRJ-004 Workboat Hull | PRJ-003 Subsea Frame | PRJ-002 Patrol Vessel | PRJ-001 Composite Vessel
Offset | 0 | 1.3 | 1.65 | 2.3 | 3.3 | 1
Schedule | 1.3 | 1.95 | 2 | 2 | 1.7 | 1.9
PRJ-001 Composite vessel
99.5% CRITICAL
PRJ-002 Patrol vessel
0% PLANNED
PRJ-003 Subsea frame
30% ON TRACK
PRJ-004 Workboat hull
70% ON TRACK
PRJ-005 Logistics pontoon
90% ON TRACK
PRJ-006 Cargo hatch
100% COMPLETE
Q2 REVIEW
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
2 / 11

## Slide 3
PORTFOLIO HEALTH
Portfolio earns $0.91 per $1 spent
03
PORTFOLIO CPI
0.91
Muted cost overrun
Earned value trails actual cost by $468K.
PROJECT MIX
3 active
2 completed · 1 planned
Chart: 
| Earned value | Actual cost | Baseline
USD millions | 4.7525 | 5.2208 | 7.1
USD MILLIONS
Cost control should focus on PRJ-001; the remaining portfolio is broadly stable.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
3 / 11

## Slide 4
PRJ-001 · VESSEL CONSTRUCTION
PRJ-001 overrun requires a contractor reset
04
CRITICAL
ACTUAL COST
$1.85M
vs. $1.50M baseline
COST PERFORMANCE INDEX
0.81
Value delivery is below plan.
Chart: 
| Complete | Remaining
Progress | 99.5 | 0.5
99.5%
COMPLETE
COMPLETED
Cost exception
Total overrun
−$356K
IMMEDIATE ACTION
Renegotiate contractor rates and freeze variation orders.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
4 / 11

## Slide 5
PRJ-002 · PATROL VESSEL DESIGN
PRJ-002 is budgeted for August
05
PLANNED / ON TRACK
0%
PROGRESS
BASELINE BUDGET
$800K
AUG 2026
DEC 2026
PLANNED START
PLANNED FINISH
DESIGN FOCUS
Carbon mold design and CFD analysis.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
5 / 11

## Slide 6
PRJ-003 · SUBSEA FRAME
PRJ-003 is 30% complete with CPI at 0.94
06
ACTIVE / ON TRACK
Chart: 
| Complete | Remaining
Progress | 30 | 70
30%
COMPLETE
BASELINE
$1.20M
SPENT
$382.5K
CPI
0.94
ENGINEERING
Complete
FABRICATION
Steel work starting
Budget tracking remains close to plan.
CURRENT FOCUS
Move cleanly from engineering completion into steel fabrication.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
6 / 11

## Slide 7
PRJ-004 · WORKBOAT HULL
PRJ-004: 70% complete with budget pressure
07
ACTIVE / ON TRACK
70%
DRAWINGS APPROVED
Welding and assembly are ongoing.
Chart: 
| Spent | Baseline
USD millions | 1.48 | 2
USD MILLIONS
COST PERFORMANCE INDEX
0.95
Slight budget pressure; monitor fabrication productivity through completion.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
7 / 11

## Slide 8
PRJ-005 · LOGISTICS PONTOON
PRJ-005 nears completion at CPI 0.97
08
ACTIVE / ON TRACK
BASELINE
$1.00M
SPENT
$927K
CPI
0.97
Chart: 
| Complete | Remaining
Progress | 90 | 10
90%
COMPLETE
FINANCIAL POSITION
In good standing
PROJECT MANAGER
Frank Ellingsen
NEAR-TERM PRIORITY
Protect the final 10% from avoidable cost leakage.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
8 / 11

## Slide 9
PRJ-006 · CARGO HATCH
PRJ-006 closes under budget at CPI 1.02
09
COMPLETED / ON TRACK
100%
DELIVERED
Molding and testing fully verified.
BASELINE
$600K
SPENT
$586.5K
CPI
1.02
UNDER BUDGET
$13.5K
Successful close-out confirms disciplined delivery and verification.
CLOSE-OUT RESULT
Completed on scope, fully verified, and under budget.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
9 / 11

## Slide 10
PORTFOLIO RAID
Three constraints need active mitigation
10
RISK
Carbon sheet delivery delay from supplier
ISSUE
Welder overtime limits exceeded in fabrication
DEPENDENCY
Sea trials depend on DNV class approval
MITIGATION
Allocate junior welders to assist.
Immediate relief for fabrication capacity constraints.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
10 / 11

## Slide 11
RECOMMENDATIONS
Four actions stabilize cost and schedule
11
01
Renegotiate outfitting contractor rates (WBS 1 & 3)
02
Shift composite fabricators to outfitting to optimize
03
Enforce double-shift schedules to recover sea trials
04
Integrate DuckDB tracking into future estimations
NEXT REVIEW
Track owner, due date, and measurable impact for each action.
Q2 2026 · PROJECT PORTFOLIO EXECUTIVE REVIEW
11 / 11