## Slide 1
Project Portfolio Executive Review
Q2 2026 Status Report | Frank Ellingsen
• Comprehensive status of 6 active & completed projects
• EVM metrics overview & financial audits
• Strategic recommendations & corrective actions

## Slide 2
1. Portfolio Overview & Health
• Total Baseline (BAC): 7,100,000 USD
• Total Spent (AC): 5,220,810 USD
• Earned Value (EV): 4,752,500 USD
• Portfolio CPI: 0.91 (Muted cost overrun)

## Slide 3
2. PRJ-001 Vessel Construction
• Status: Completed (99.5% progress)
• Baseline: 1.5M USD | Actual Cost: 1.85M USD
• CPI: 0.81 | Total Overrun: -356K USD
• Action: Renegotiate contractor rates & freeze VOs

## Slide 4
3. PRJ-002 Patrol Vessel Design
• Status: Planned (0% progress)
• Baseline Budget: 800,000 USD
• Planned Start: Aug 2026 | Finish: Dec 2026
• Focus: Carbon mold design and CFD analysis

## Slide 5
4. PRJ-003 Subsea Cable Frame
• Status: Active (30% progress)
• Baseline: 1.2M USD | Spent: 382.5K USD
• CPI: 0.94 (Tracking close to budget)
• Focus: Engineering complete, steel fabrication starting

## Slide 6
5. PRJ-004 Workboat Hull
• Status: Active (70% progress)
• Baseline: 2.0M USD | Spent: 1.48M USD
• CPI: 0.95 (Slight budget pressure)
• Focus: Drawings approved, welding & assembly ongoing

## Slide 7
6. PRJ-005 Logistics Pontoon
• Status: Active (90% progress)
• Baseline: 1.0M USD | Spent: 927K USD
• CPI: 0.97 (In good financial standing)
• Project Manager: Frank Ellingsen

## Slide 8
7. PRJ-006 Composite Cargo Hatch
• Status: Completed (100% progress)
• Baseline: 600,000 USD | Spent: 586,500 USD
• CPI: 1.02 (Under budget success)
• Deliverables: Molding & testing fully verified

## Slide 9
8. Key Portfolio Risks & RAID Log
• Risk: Carbon sheet delivery delay from supplier
• Issue: Welder overtime limits exceeded in fabrication
• Dependency: Sea trials depend on DNV class approval
• Mitigation: Allocate junior welders to assist

## Slide 10
9. Recommendations & Next Steps
• Renegotiate outfitting contractor rates (WBS 1 & 3)
• Shift composite fabricators to outfitting to optimize
• Enforce double-shift schedules to recover sea trials
• Integrate DuckDB tracking into future estimations