## Dashboard
Q2 2026 Project Portfolio Executive Review
Six projects. One portfolio view. Clear decisions on cost, schedule, and risk — modeled after Project_Portfolio_Review.pptx and driven by live workbook tables.
PORTFOLIO CPI |  |  | COST VARIANCE |  |  | PROJECT MIX |  |  | PORTFOLIO EAC
0.9103 |  |  | -$468K |  |  | 3 active |  |  | $7.7M
Target: > 1.00 |  |  | EV minus AC |  |  | 2 completed · 1 planned |  |  | Typical variance forecast
Story in brief: The portfolio earns 0.91 per $1 spent, with earned value trailing actual cost by $468,310. PRJ-001 is the primary cost exception at CPI 0.81, while PRJ-006 closed under budget. Active delivery remains broadly stable, but fabrication capacity and supplier constraints need management attention.
PORTFOLIO HEALTH | [5 empty] | PROJECT CPI WATCHLIST
EXECUTIVE PROJECT TABLE
Project | Alert | Progress | BAC | Actual Cost | CPI | Variance | Action
PRJ-001 | CRITICAL | 99.5% | 1500000 | 1848810 | 0.80728 | -356310 | Renegotiate contractor rates and freeze variation orders
PRJ-002 | PLANNED | 0% | 800000 | 0 |  | 0 | Prepare August design start and resource ramp
PRJ-003 | CRITICAL | 30% | 1200000 | 382500 | 0.94118 | -22500 | Move cleanly from engineering to steel fabrication
PRJ-004 | CRITICAL | 70% | 2000000 | 1476000 | 0.94851 | -76000 | Monitor welding productivity through completion
PRJ-005 | WATCH | 90% | 1000000 | 927000 | 0.97087 | -27000 | Protect final 10% from cost leakage
PRJ-006 | ON TRACK | 100% | 600000 | 586500 | 1.023 | 13500 | Close out lessons learned and verification pack
RAID & RECOMMENDATIONS
[7 empty] | Type | Constraint | Owner | Status
[7 empty] | Risk | Carbon sheet delivery delay from supplier | Morten Hansen | Active
[7 empty] | Issue | Welder overtime limits exceeded in fabrication | Morten Hansen | Active
[7 empty] | Dependency | Sea trials depend on DNV class approval | Frank Ellingsen | Active
RECOMMENDED ACTIONS
1. Renegotiate outfitting contractor rates (WBS 1 & 3)
RAG Legend | Red | Amber | Green
Rules | CPI < 0.95 / negative CV | CPI 0.95–<1.00, planned/watch, or zero CV | CPI ≥ 1.00 / positive CV

## Portfolio Metrics
Portfolio Metrics Engine | [20 empty] | Project | BAC | EV | AC | Project | CPI | Project | Labor AC | Material AC | Project | Start Offset | Duration | Type | Description | Owner | Status | No. | Recommendation
Live EVM calculations supporting the executive dashboard. Formulas follow EV = BAC × progress, CV = EV − AC, CPI = EV / AC, SPI = EV / PV, and EAC = BAC / CPI. | [20 empty] | PRJ-001 | 1500000 | 1492500 | 1848810 | PRJ-001 | 0.80728 | PRJ-001 | 1326810 | 522000 | PRJ-006 | 0 | 181 | Risk | Carbon sheet delivery delay from supplier | Morten Hansen | Active | 1 | Renegotiate outfitting contractor rates (WBS 1 & 3)
[21 empty] | PRJ-002 | 800000 | 0 | 0 | PRJ-002 |  | PRJ-002 | 0 | 0 | PRJ-005 | 123 | 180 | Issue | Welder overtime limits exceeded in fabrication | Morten Hansen | Active | 2 | Shift composite fabricators to outfitting to optimize
Report Date | 2026-06-30 | [19 empty] | PRJ-003 | 1200000 | 360000 | 382500 | PRJ-003 | 0.94118 | PRJ-003 | 332500 | 50000 | PRJ-004 | 151 | 183 | Dependency | Sea trials depend on DNV class approval | Frank Ellingsen | Active | 3 | Enforce double-shift schedules to recover sea trials
[21 empty] | PRJ-004 | 2000000 | 1400000 | 1476000 | PRJ-004 | 0.94851 | PRJ-004 | 1226000 | 250000 | PRJ-003 | 212 | 183 |  |  |  |  | 4 | Integrate DuckDB tracking into future estimations
WBS_ID | ProjectID | WBS Code | Element Name | Planned Cost | Planned Hours | Latest Progress | EV | Labor AC | Material AC | AC | CV | CPI | [8 empty] | PRJ-005 | 1000000 | 900000 | 927000 | PRJ-005 | 0.97087 | PRJ-005 | 747000 | 180000 | PRJ-002 | 304 | 152
WBS-001 | PRJ-001 | 1 | Project Management & Engineering | 300000 | 400 | 0.975 | 292500 | 419230 | 0 | 419230 | -126730 | 0.69771 | [8 empty] | PRJ-006 | 600000 | 600000 | 586500 | PRJ-006 | 1.023 | PRJ-006 | 516500 | 70000 | PRJ-001 | 92 | 180
WBS-002 | PRJ-001 | 2 | Hull Fabrication & Assembly | 600000 | 1200 | 1 | 600000 | 374950 | 245500 | 620450 | -20450 | 0.96704 | [18 empty] | 45931
WBS-003 | PRJ-001 | 3 | Outfitting & Integration | 400000 | 800 | 1 | 400000 | 297445 | 243000 | 540445 | -140445 | 0.74013
WBS-004 | PRJ-001 | 4 | Sea Trials & Handover | 200000 | 300 | 1 | 200000 | 235185 | 33500 | 268685 | -68685 | 0.74437
WBS-005 | PRJ-002 | 1 | Design & CFD Analysis | 300000 | 300 | 0 | 0 | 0 | 0 | 0 | 0
WBS-006 | PRJ-002 | 2 | Material Procurement | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS-007 | PRJ-003 | 1 | Structural Frame Engineering | 400000 | 400 | 0.9 | 360000 | 332500 | 0 | 332500 | 27500 | 1.0827
WBS-008 | PRJ-003 | 2 | Steel Fabrication | 800000 | 1000 | 0 | 0 | 0 | 50000 | 50000 | -50000 | 0
WBS-009 | PRJ-004 | 1 | Engineering Drawings & Class Approval | 500000 | 500 | 1 | 500000 | 456000 | 0 | 456000 | 44000 | 1.0965
WBS-010 | PRJ-004 | 2 | Hull Welding & Assembly | 1500000 | 2000 | 0.6 | 900000 | 770000 | 250000 | 1020000 | -120000 | 0.88235
WBS-011 | PRJ-005 | 1 | Project Control & PM | 200000 | 250 | 1 | 200000 | 187000 | 0 | 187000 | 13000 | 1.0695
WBS-012 | PRJ-005 | 2 | Pontoon Assembly & Painting | 800000 | 1000 | 0.875 | 700000 | 560000 | 180000 | 740000 | -40000 | 0.94595
WBS-013 | PRJ-006 | 1 | Hatch Engineering & FEA | 200000 | 200 | 1 | 200000 | 180500 | 0 | 180500 | 19500 | 1.108
WBS-014 | PRJ-006 | 2 | Molding & Testing | 400000 | 500 | 1 | 400000 | 336000 | 70000 | 406000 | -6000 | 0.98522
ProjectID | Project Name | Manager | Status | BAC | Start | End | Progress | EV | PV | Labor AC | Material AC | AC | CV | SV | CPI | SPI | EAC | Forecast Variance | Alert | Recommended Action
PRJ-001 | Composite Maritime Vessel Construction | Morten Hansen | Completed | 1500000 | 46023 | 46203 | 0.995 | 1492500 | 1500000 | 1326810 | 522000 | 1848810 | -356310 | -7500 | 0.80728 | 0.995 | 1858100.5025 | -358100.5025 | CRITICAL | Renegotiate contractor rates and freeze variation orders
PRJ-002 | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | Planned | 800000 | 46235 | 46387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 800000 | 0 | PLANNED | Prepare August design start and resource ramp
PRJ-003 | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | Active | 1200000 | 46143 | 46326 | 0.3 | 360000 | 393442.623 | 332500 | 50000 | 382500 | -22500 | -33442.623 | 0.94118 | 0.915 | 1275000 | -75000 | CRITICAL | Move cleanly from engineering to steel fabrication
PRJ-004 | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | Active | 2000000 | 46082 | 46265 | 0.7 | 1400000 | 1322404.3716 | 1226000 | 250000 | 1476000 | -76000 | 77595.6284 | 0.94851 | 1.0587 | 2108571.4286 | -108571.4286 | CRITICAL | Monitor welding productivity through completion
PRJ-005 | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | Active | 1000000 | 46054 | 46234 | 0.9 | 900000 | 827777.7778 | 747000 | 180000 | 927000 | -27000 | 72222.2222 | 0.97087 | 1.0872 | 1030000 | -30000 | WATCH | Protect final 10% from cost leakage
PRJ-006 | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | Completed | 600000 | 45931 | 46112 | 1 | 600000 | 600000 | 516500 | 70000 | 586500 | 13500 | 0 | 1.023 | 1 | 586500 | 13500 | ON TRACK | Close out lessons learned and verification pack
Metric | Value
Portfolio BAC | 7100000
Earned Value | 4752500
Actual Cost | 5220810
Cost Variance | -468310
Portfolio CPI | 0.9103
Portfolio EAC | 7658171.9311
Active Projects | 3
Completed Projects | 2
Planned Projects | 1
Critical Projects | 3

## Data Model
Project Portfolio Data Model
Relational map inferred from the 8 workbook tables. Native Power Pivot model creation is not exposed here, so this sheet documents the model and keeps integrity checks live with workbook formulas.
Story in brief: Projects and resources are the two master dimensions. WBS elements are the central bridge connecting planned work, labor actuals, material actuals, and physical progress. All tested foreign-key relationships currently resolve with no unmatched keys; raid_log should be normalized before it is joined into reporting.
Table | Primary key | Grain | Rows | Purpose | Notes | Column1 | Column2
projects | ProjectID | 1 row per project | 6 | Portfolio project master: dates, owner, BAC, status | Parent for WBS; project manager can map to resources by name
resources | ResourceID | 1 row per person/resource | 5 | Labor resource master with role and hourly rate | Parent for timesheets and assignments
wbs_elements | WBS_ID | 1 row per WBS element | 14 | Work breakdown structure under each project | Central bridge between projects, labor, materials, and progress
resource_assignments | AssignmentID | 1 row per planned resource allocation to WBS | 17 | Planned hours by resource and WBS | Fact table for planned labor allocation
material_costs | PurchaseID | 1 row per material purchase | 14 | Actual material purchases and cost by WBS | Fact table for material actuals
timesheets | TimesheetID | 1 row per resource/WBS work entry | 299 | Actual labor hours by date, resource, and WBS | Fact table for labor actuals
physical_progress | ProgressID | 1 row per progress update | 57 | Reported percent complete by WBS and date | Fact table for earned progress
Model coverage: 6 projects, 14 WBS elements, 299 timesheet rows, 14 material purchases, 57 progress records.
From table | From key | To table | To key | Cardinality | Rows tested | Unmatched FK | Status
projects | ProjectManager | resources | ResourceName | Many-to-one by name | 6 | 0 | OK
wbs_elements | ProjectID | projects | ProjectID | Many-to-one | 14 | 0 | OK
resource_assignments | WBS_ID | wbs_elements | WBS_ID | Many-to-one | 17 | 0 | OK
resource_assignments | ResourceID | resources | ResourceID | Many-to-one | 17 | 0 | OK
material_costs | WBS_ID | wbs_elements | WBS_ID | Many-to-one | 14 | 0 | OK
timesheets | WBS_ID | wbs_elements | WBS_ID | Many-to-one | 299 | 0 | OK
timesheets | ResourceID | resources | ResourceID | Many-to-one | 299 | 0 | OK
physical_progress | WBS_ID | wbs_elements | WBS_ID | Many-to-one | 57 | 0 | OK
physical_progress | ReportedBy | resources | ResourceName | Many-to-one by name | 57 | 0 | OK
Table | Field | Role | Description
projects | ProjectID | Primary key | Project identifier
projects | ProjectName | Attribute | Project display name
projects | ProjectManager | Foreign key by name | Maps to resources[ResourceName]
projects | BudgetAtCompletion_BAC | Measure base | Approved baseline budget
projects | StartDate | Date | Planned/actual start
projects | EndDate | Date | Planned/actual finish
projects | Status | Attribute | Project lifecycle status
resources | ResourceID | Primary key | Resource identifier
resources | ResourceName | Alternate key | Person/resource name
resources | Role | Attribute | Resource role
resources | HourlyRate | Measure base | Cost rate per hour
wbs_elements | WBS_ID | Primary key | WBS identifier
wbs_elements | ProjectID | Foreign key | Maps to projects[ProjectID]
wbs_elements | WBS_Code | Attribute | WBS numeric/code
wbs_elements | ElementName | Attribute | WBS element name
wbs_elements | PlannedCost | Measure base | Planned cost for element
wbs_elements | PlannedHours | Measure base | Planned hours for element
resource_assignments | AssignmentID | Primary key | Assignment identifier
resource_assignments | WBS_ID | Foreign key | Maps to wbs_elements[WBS_ID]
resource_assignments | ResourceID | Foreign key | Maps to resources[ResourceID]
resource_assignments | AllocatedHours | Measure base | Planned allocation hours
material_costs | PurchaseID | Primary key | Purchase/invoice identifier
material_costs | WBS_ID | Foreign key | Maps to wbs_elements[WBS_ID]
material_costs | PurchaseDate | Date | Purchase date
material_costs | Description | Attribute | Material description
material_costs | Quantity | Measure base | Purchased quantity
material_costs | UnitPrice | Measure base | Price per unit
material_costs | TotalActualCost | Measure base | Material actual cost
timesheets | TimesheetID | Primary key | Timesheet line identifier
timesheets | ResourceID | Foreign key | Maps to resources[ResourceID]
timesheets | WBS_ID | Foreign key | Maps to wbs_elements[WBS_ID]
timesheets | WorkDate | Date | Work date
timesheets | HoursWorked | Measure base | Actual hours worked
timesheets | ApprovalStatus | Attribute | Approval state
physical_progress | ProgressID | Primary key | Progress record identifier
physical_progress | WBS_ID | Foreign key | Maps to wbs_elements[WBS_ID]
physical_progress | RecordDate | Date | Progress record date
physical_progress | PercentComplete | Measure base | Reported completion percentage
physical_progress | ReportedBy | Foreign key by name | Maps to resources[ResourceName]
raid_log | RiskID* | Primary key after normalization | Currently stored in Column1 after embedded header row
raid_log | Type* | Attribute | Risk/assumption/issue/dependency
raid_log | Description* | Attribute | RAID description
raid_log | Impact* | Attribute | Impact level
raid_log | Probability* | Attribute | Probability level
raid_log | MitigationStrategy* | Attribute | Mitigation plan
raid_log | Owner* | Foreign key by name | Can map to resources[ResourceName] after normalization
raid_log | Status* | Attribute | RAID status

## projects
ProjectID | ProjectName | ProjectManager | BudgetAtCompletion_BAC | StartDate | EndDate | Status
PRJ-001 | Composite Maritime Vessel Construction | Morten Hansen | 1500000 | 2026-01-01 | 2026-06-30 | Completed
PRJ-002 | PRJ-002: Patrol Vessel Carbon Mold Design | Morten Hansen | 800000 | 2026-08-01 | 2026-12-31 | Planned
PRJ-003 | PRJ-003: Subsea Cable Installation Frame | Erik Johansen | 1200000 | 2026-05-01 | 2026-10-31 | Active
PRJ-004 | PRJ-004: Autonomous Workboat Hull Weldments | Astrid Nilsen | 2000000 | 2026-03-01 | 2026-08-31 | Active
PRJ-005 | PRJ-005: Defense Logistics Pontoon Build | Frank Ellingsen | 1000000 | 2026-02-01 | 2026-07-31 | Active
PRJ-006 | PRJ-006: Lightweight Composite Cargo Hatch | Morten Hansen | 600000 | 2025-10-01 | 2026-03-31 | Completed

## resources
ResourceID | ResourceName | Role | HourlyRate
RES-001 | Frank Ellingsen | Project Controller | 850
RES-002 | Morten Hansen | Project Manager | 1000
RES-003 | Erik Johansen | Senior Design Engineer | 950
RES-004 | Astrid Nilsen | Structural Welder | 700
RES-005 | Lars Olsen | Marine Electrician | 750

## wbs_elements
WBS_ID | ProjectID | WBS_Code | ElementName | PlannedCost | PlannedHours
WBS-001 | PRJ-001 | 1 | Project Management & Engineering | 300000 | 400
WBS-002 | PRJ-001 | 2 | Hull Fabrication & Assembly | 600000 | 1200
WBS-003 | PRJ-001 | 3 | Outfitting & Integration | 400000 | 800
WBS-004 | PRJ-001 | 4 | Sea Trials & Handover | 200000 | 300
WBS-005 | PRJ-002 | 1 | Design & CFD Analysis | 300000 | 300
WBS-006 | PRJ-002 | 2 | Material Procurement | 500000 | 0
WBS-007 | PRJ-003 | 1 | Structural Frame Engineering | 400000 | 400
WBS-008 | PRJ-003 | 2 | Steel Fabrication | 800000 | 1000
WBS-009 | PRJ-004 | 1 | Engineering Drawings & Class Approval | 500000 | 500
WBS-010 | PRJ-004 | 2 | Hull Welding & Assembly | 1500000 | 2000
WBS-011 | PRJ-005 | 1 | Project Control & PM | 200000 | 250
WBS-012 | PRJ-005 | 2 | Pontoon Assembly & Painting | 800000 | 1000
WBS-013 | PRJ-006 | 1 | Hatch Engineering & FEA | 200000 | 200
WBS-014 | PRJ-006 | 2 | Molding & Testing | 400000 | 500

## resource_assignments
AssignmentID | WBS_ID | ResourceID | AllocatedHours
ASG-001 | WBS-001 | RES-001 | 100
ASG-002 | WBS-001 | RES-002 | 200
ASG-003 | WBS-001 | RES-003 | 100
ASG-004 | WBS-002 | RES-004 | 1000
ASG-005 | WBS-002 | RES-003 | 200
ASG-006 | WBS-003 | RES-005 | 600
ASG-007 | WBS-003 | RES-004 | 200
ASG-008 | WBS-004 | RES-002 | 100
ASG-009 | WBS-004 | RES-005 | 150
ASG-010 | WBS-004 | RES-001 | 50
ASG-011 | WBS-008 | RES-004 | 1000
ASG-012 | WBS-009 | RES-003 | 500
ASG-013 | WBS-010 | RES-004 | 2000
ASG-014 | WBS-011 | RES-001 | 250
ASG-015 | WBS-012 | RES-004 | 1000
ASG-016 | WBS-013 | RES-003 | 200
ASG-017 | WBS-014 | RES-004 | 500

## material_costs
PurchaseID | WBS_ID | PurchaseDate | Description | Quantity | UnitPrice | TotalActualCost
INV-001 | WBS-002 | 2026-02-05 | Structural Composite Carbon Sheets | 10 | 15000 | 150000
INV-002 | WBS-002 | 2026-02-12 | Epoxy Resin Infusion Kit | 20 | 2500 | 50000
INV-003 | WBS-002 | 2026-02-28 | Steel Support Beam Frames | 4 | 8000 | 32000
INV-004 | WBS-002 | 2026-03-10 | Additional Epoxies (Overrun material) | 5 | 2700 | 13500
INV-005 | WBS-003 | 2026-04-05 | Marine Cabin Electrical Wiring | 2 | 12000 | 24000
INV-006 | WBS-003 | 2026-04-20 | Simrad Integrated Marine Dashboard | 1 | 45000 | 45000
INV-007 | WBS-003 | 2026-05-02 | Twin Electric Inboard Engines | 2 | 65000 | 130000
INV-008 | WBS-003 | 2026-05-18 | Battery Storage Bank Lithium 10kWh | 2 | 22000 | 44000
INV-009 | WBS-004 | 2026-06-05 | DNV Safety & Compliance Certification | 1 | 25000 | 25000
INV-010 | WBS-004 | 2026-06-15 | Test Trial Bio-Fuel & Supplies | 1 | 8500 | 8500
MAT-3001 | WBS-008 | 2026-05-10 | Steel Frame Pre-payment Deposit | 1 | 50000 | 50000
MAT-4001 | WBS-010 | 2026-03-25 | Consumables & Steel Plates | 1 | 250000 | 250000
MAT-5001 | WBS-012 | 2026-03-01 | Paint & Marine Alloy Plates | 1 | 180000 | 180000
MAT-6001 | WBS-014 | 2025-11-01 | Composite Cutting Fiber | 1 | 70000 | 70000

## timesheets
TimesheetID | ResourceID | WBS_ID | WorkDate | HoursWorked | ApprovalStatus
TS-0001 | RES-001 | WBS-001 | 2026-01-02 | 4.1 | Approved
TS-0002 | RES-001 | WBS-001 | 2026-01-09 | 3.5 | Approved
TS-0003 | RES-001 | WBS-001 | 2026-01-16 | 3.8 | Approved
TS-0004 | RES-001 | WBS-001 | 2026-01-23 | 3.7 | Approved
TS-0005 | RES-001 | WBS-001 | 2026-01-30 | 4.2 | Approved
TS-0006 | RES-001 | WBS-001 | 2026-02-06 | 4.2 | Approved
TS-0007 | RES-001 | WBS-001 | 2026-02-13 | 4.4 | Approved
TS-0008 | RES-001 | WBS-001 | 2026-02-20 | 3.6 | Approved
TS-0009 | RES-001 | WBS-001 | 2026-02-27 | 3.9 | Approved
TS-0010 | RES-001 | WBS-001 | 2026-03-06 | 3.5 | Approved
TS-0011 | RES-001 | WBS-001 | 2026-03-13 | 3.7 | Approved
TS-0012 | RES-001 | WBS-001 | 2026-03-20 | 4 | Approved
TS-0013 | RES-001 | WBS-001 | 2026-03-27 | 3.5 | Approved
TS-0014 | RES-001 | WBS-001 | 2026-04-03 | 3.7 | Approved
TS-0015 | RES-001 | WBS-001 | 2026-04-10 | 4.1 | Approved
TS-0016 | RES-001 | WBS-001 | 2026-04-17 | 4 | Approved
TS-0017 | RES-001 | WBS-001 | 2026-04-24 | 3.7 | Approved
TS-0018 | RES-001 | WBS-001 | 2026-05-01 | 4.1 | Approved
TS-0019 | RES-001 | WBS-001 | 2026-05-08 | 4.3 | Approved
TS-0020 | RES-001 | WBS-001 | 2026-05-15 | 3.5 | Approved
TS-0021 | RES-001 | WBS-001 | 2026-05-22 | 4.3 | Approved
TS-0022 | RES-001 | WBS-001 | 2026-05-29 | 4.2 | Approved
TS-0023 | RES-001 | WBS-001 | 2026-06-05 | 3.8 | Approved
TS-0024 | RES-001 | WBS-001 | 2026-06-12 | 3.7 | Approved
TS-0025 | RES-001 | WBS-001 | 2026-06-19 | 4.5 | Approved
TS-0026 | RES-001 | WBS-001 | 2026-06-26 | 3.8 | Approved
TS-0027 | RES-002 | WBS-001 | 2026-01-05 | 7.6 | Approved
TS-0028 | RES-002 | WBS-001 | 2026-01-12 | 7.6 | Approved
TS-0029 | RES-002 | WBS-001 | 2026-01-19 | 8.8 | Approved
TS-0030 | RES-002 | WBS-001 | 2026-01-26 | 8.4 | Approved
TS-0031 | RES-002 | WBS-001 | 2026-02-02 | 8.7 | Approved
TS-0032 | RES-002 | WBS-001 | 2026-02-09 | 8.6 | Approved
TS-0033 | RES-002 | WBS-001 | 2026-02-16 | 8.3 | Approved
TS-0034 | RES-002 | WBS-001 | 2026-02-23 | 9 | Approved
TS-0035 | RES-002 | WBS-001 | 2026-03-02 | 8.1 | Approved
TS-0036 | RES-002 | WBS-001 | 2026-03-09 | 8.3 | Approved
TS-0037 | RES-002 | WBS-001 | 2026-03-16 | 8.7 | Approved
TS-0038 | RES-002 | WBS-001 | 2026-03-23 | 8.4 | Approved
TS-0039 | RES-002 | WBS-001 | 2026-03-30 | 8.8 | Approved
TS-0040 | RES-002 | WBS-001 | 2026-04-06 | 8.4 | Approved
TS-0041 | RES-002 | WBS-001 | 2026-04-13 | 8.6 | Approved
TS-0042 | RES-002 | WBS-001 | 2026-04-20 | 7.6 | Approved
TS-0043 | RES-002 | WBS-001 | 2026-04-27 | 7.8 | Approved
TS-0044 | RES-002 | WBS-001 | 2026-05-04 | 7.9 | Approved
TS-0045 | RES-002 | WBS-001 | 2026-05-11 | 7.6 | Approved
TS-0046 | RES-002 | WBS-001 | 2026-05-18 | 7.8 | Approved
TS-0047 | RES-002 | WBS-001 | 2026-05-25 | 7.7 | Approved
TS-0048 | RES-002 | WBS-001 | 2026-06-01 | 7.9 | Approved
TS-0049 | RES-002 | WBS-001 | 2026-06-08 | 8.5 | Approved
TS-0050 | RES-002 | WBS-001 | 2026-06-15 | 8 | Approved
TS-0051 | RES-002 | WBS-001 | 2026-06-22 | 8.1 | Approved
TS-0052 | RES-002 | WBS-001 | 2026-06-29 | 7.8 | Approved
TS-0053 | RES-003 | WBS-001 | 2026-01-01 | 2.8 | Approved
TS-0054 | RES-003 | WBS-001 | 2026-01-02 | 3.4 | Approved
TS-0055 | RES-003 | WBS-001 | 2026-01-05 | 3.1 | Approved
TS-0056 | RES-003 | WBS-001 | 2026-01-06 | 3.1 | Approved
TS-0057 | RES-003 | WBS-001 | 2026-01-07 | 2.7 | Approved
TS-0058 | RES-003 | WBS-001 | 2026-01-08 | 3.2 | Approved
TS-0059 | RES-003 | WBS-001 | 2026-01-09 | 2.7 | Approved
TS-0060 | RES-003 | WBS-001 | 2026-01-12 | 2.9 | Approved
TS-0061 | RES-003 | WBS-001 | 2026-01-13 | 3.5 | Approved
TS-0062 | RES-003 | WBS-001 | 2026-01-14 | 3.1 | Approved
TS-0063 | RES-003 | WBS-001 | 2026-01-15 | 3.1 | Approved
TS-0064 | RES-003 | WBS-001 | 2026-01-16 | 3.2 | Approved
TS-0065 | RES-003 | WBS-001 | 2026-01-19 | 3.3 | Approved
TS-0066 | RES-003 | WBS-001 | 2026-01-20 | 3.3 | Approved
TS-0067 | RES-003 | WBS-001 | 2026-01-21 | 2.7 | Approved
TS-0068 | RES-003 | WBS-001 | 2026-01-22 | 2.5 | Approved
TS-0069 | RES-003 | WBS-001 | 2026-01-23 | 2.8 | Approved
TS-0070 | RES-003 | WBS-001 | 2026-01-26 | 2.8 | Approved
TS-0071 | RES-003 | WBS-001 | 2026-01-27 | 2.7 | Approved
TS-0072 | RES-003 | WBS-001 | 2026-01-28 | 3.4 | Approved
TS-0073 | RES-003 | WBS-001 | 2026-01-29 | 3.4 | Approved
TS-0074 | RES-003 | WBS-001 | 2026-01-30 | 2.8 | Approved
TS-0075 | RES-003 | WBS-001 | 2026-02-02 | 3.2 | Approved
TS-0076 | RES-003 | WBS-001 | 2026-02-03 | 2.9 | Approved
TS-0077 | RES-003 | WBS-001 | 2026-02-04 | 3.4 | Approved
TS-0078 | RES-003 | WBS-001 | 2026-02-05 | 3 | Approved
TS-0079 | RES-003 | WBS-001 | 2026-02-06 | 2.8 | Approved
TS-0080 | RES-003 | WBS-001 | 2026-02-09 | 2.7 | Approved
TS-0081 | RES-003 | WBS-001 | 2026-02-10 | 3.1 | Approved
TS-0082 | RES-003 | WBS-001 | 2026-02-11 | 2.8 | Approved
TS-0083 | RES-003 | WBS-001 | 2026-02-12 | 3.1 | Approved
TS-0084 | RES-003 | WBS-001 | 2026-02-13 | 3.4 | Approved
TS-0085 | RES-003 | WBS-001 | 2026-02-16 | 2.9 | Approved
TS-0086 | RES-003 | WBS-001 | 2026-02-17 | 2.7 | Approved
TS-0087 | RES-003 | WBS-001 | 2026-02-18 | 3.5 | Approved
TS-0088 | RES-003 | WBS-001 | 2026-02-19 | 3 | Approved
TS-0089 | RES-003 | WBS-001 | 2026-02-20 | 2.6 | Approved
TS-0090 | RES-003 | WBS-001 | 2026-02-23 | 2.5 | Approved
TS-0091 | RES-003 | WBS-001 | 2026-02-24 | 2.6 | Approved
TS-0092 | RES-003 | WBS-001 | 2026-02-25 | 3.1 | Approved
TS-0093 | RES-003 | WBS-001 | 2026-02-26 | 3.3 | Approved
TS-0094 | RES-003 | WBS-001 | 2026-02-27 | 2.9 | Approved
TS-0095 | RES-004 | WBS-002 | 2026-02-02 | 8.1 | Approved
TS-0096 | RES-004 | WBS-002 | 2026-02-03 | 8.4 | Approved
TS-0097 | RES-004 | WBS-002 | 2026-02-04 | 9 | Approved
TS-0098 | RES-004 | WBS-002 | 2026-02-05 | 8.5 | Approved
TS-0099 | RES-004 | WBS-002 | 2026-02-06 | 9 | Approved
TS-0100 | RES-004 | WBS-002 | 2026-02-09 | 8.9 | Approved
TS-0101 | RES-004 | WBS-002 | 2026-02-10 | 8 | Approved
TS-0102 | RES-004 | WBS-002 | 2026-02-11 | 8.7 | Approved
TS-0103 | RES-004 | WBS-002 | 2026-02-12 | 8.7 | Approved
TS-0104 | RES-004 | WBS-002 | 2026-02-13 | 8.5 | Approved
TS-0105 | RES-004 | WBS-002 | 2026-02-16 | 8.3 | Approved
TS-0106 | RES-004 | WBS-002 | 2026-02-17 | 8.6 | Approved
TS-0107 | RES-004 | WBS-002 | 2026-02-18 | 8.1 | Approved
TS-0108 | RES-004 | WBS-002 | 2026-02-19 | 8.4 | Approved
TS-0109 | RES-004 | WBS-002 | 2026-02-20 | 8.5 | Approved
TS-0110 | RES-004 | WBS-002 | 2026-02-23 | 9 | Approved
TS-0111 | RES-004 | WBS-002 | 2026-02-24 | 8.9 | Approved
TS-0112 | RES-004 | WBS-002 | 2026-02-25 | 8.3 | Approved
TS-0113 | RES-004 | WBS-002 | 2026-02-26 | 8.5 | Approved
TS-0114 | RES-004 | WBS-002 | 2026-02-27 | 8.2 | Approved
TS-0115 | RES-004 | WBS-002 | 2026-03-02 | 8.9 | Approved
TS-0116 | RES-004 | WBS-002 | 2026-03-03 | 8.9 | Approved
TS-0117 | RES-004 | WBS-002 | 2026-03-04 | 8.3 | Approved
TS-0118 | RES-004 | WBS-002 | 2026-03-05 | 8.6 | Approved
TS-0119 | RES-004 | WBS-002 | 2026-03-06 | 8.6 | Approved
TS-0120 | RES-004 | WBS-002 | 2026-03-09 | 8.2 | Approved
TS-0121 | RES-004 | WBS-002 | 2026-03-10 | 8.8 | Approved
TS-0122 | RES-004 | WBS-002 | 2026-03-11 | 8.5 | Approved
TS-0123 | RES-004 | WBS-002 | 2026-03-12 | 8.8 | Approved
TS-0124 | RES-004 | WBS-002 | 2026-03-13 | 8.5 | Approved
TS-0125 | RES-004 | WBS-002 | 2026-03-16 | 8 | Approved
TS-0126 | RES-004 | WBS-002 | 2026-03-17 | 8.3 | Approved
TS-0127 | RES-004 | WBS-002 | 2026-03-18 | 8 | Approved
TS-0128 | RES-004 | WBS-002 | 2026-03-19 | 8.9 | Approved
TS-0129 | RES-004 | WBS-002 | 2026-03-20 | 8.9 | Approved
TS-0130 | RES-004 | WBS-002 | 2026-03-23 | 8.8 | Approved
TS-0131 | RES-004 | WBS-002 | 2026-03-24 | 8.3 | Approved
TS-0132 | RES-004 | WBS-002 | 2026-03-25 | 8.1 | Approved
TS-0133 | RES-004 | WBS-002 | 2026-03-26 | 8.9 | Approved
TS-0134 | RES-004 | WBS-002 | 2026-03-27 | 8.9 | Approved
TS-0135 | RES-004 | WBS-002 | 2026-03-30 | 8.1 | Approved
TS-0136 | RES-004 | WBS-002 | 2026-03-31 | 8.5 | Approved
TS-0137 | RES-004 | WBS-002 | 2026-04-01 | 8.1 | Approved
TS-0138 | RES-004 | WBS-002 | 2026-04-02 | 8.8 | Approved
TS-0139 | RES-004 | WBS-002 | 2026-04-03 | 8.8 | Approved
TS-0140 | RES-004 | WBS-002 | 2026-04-06 | 8.1 | Approved
TS-0141 | RES-004 | WBS-002 | 2026-04-07 | 8.5 | Approved
TS-0142 | RES-004 | WBS-002 | 2026-04-08 | 8.5 | Approved
TS-0143 | RES-004 | WBS-002 | 2026-04-09 | 8.3 | Approved
TS-0144 | RES-004 | WBS-002 | 2026-04-10 | 8.9 | Approved
TS-0145 | RES-004 | WBS-002 | 2026-04-13 | 8.4 | Approved
TS-0146 | RES-004 | WBS-002 | 2026-04-14 | 8.2 | Approved
TS-0147 | RES-004 | WBS-002 | 2026-04-15 | 8.5 | Approved
TS-0148 | RES-003 | WBS-002 | 2026-02-02 | 2.2 | Approved
TS-0149 | RES-003 | WBS-002 | 2026-02-04 | 1.7 | Approved
TS-0150 | RES-003 | WBS-002 | 2026-02-06 | 1.8 | Approved
TS-0151 | RES-003 | WBS-002 | 2026-02-09 | 2.5 | Approved
TS-0152 | RES-003 | WBS-002 | 2026-02-11 | 2.1 | Approved
TS-0153 | RES-003 | WBS-002 | 2026-02-13 | 1.9 | Approved
TS-0154 | RES-003 | WBS-002 | 2026-02-16 | 2 | Approved
TS-0155 | RES-003 | WBS-002 | 2026-02-18 | 1.6 | Approved
TS-0156 | RES-003 | WBS-002 | 2026-02-20 | 1.7 | Approved
TS-0157 | RES-003 | WBS-002 | 2026-02-23 | 1.8 | Approved
TS-0158 | RES-003 | WBS-002 | 2026-02-25 | 2.1 | Approved
TS-0159 | RES-003 | WBS-002 | 2026-02-27 | 1.7 | Approved
TS-0160 | RES-003 | WBS-002 | 2026-03-02 | 1.7 | Approved
TS-0161 | RES-003 | WBS-002 | 2026-03-04 | 1.6 | Approved
TS-0162 | RES-003 | WBS-002 | 2026-03-06 | 2.1 | Approved
TS-0163 | RES-003 | WBS-002 | 2026-03-09 | 1.7 | Approved
TS-0164 | RES-003 | WBS-002 | 2026-03-11 | 2.4 | Approved
TS-0165 | RES-003 | WBS-002 | 2026-03-13 | 2.4 | Approved
TS-0166 | RES-003 | WBS-002 | 2026-03-16 | 1.6 | Approved
TS-0167 | RES-003 | WBS-002 | 2026-03-18 | 1.7 | Approved
TS-0168 | RES-003 | WBS-002 | 2026-03-20 | 2.2 | Approved
TS-0169 | RES-003 | WBS-002 | 2026-03-23 | 1.7 | Approved
TS-0170 | RES-003 | WBS-002 | 2026-03-25 | 1.6 | Approved
TS-0171 | RES-003 | WBS-002 | 2026-03-27 | 2.4 | Approved
TS-0172 | RES-003 | WBS-002 | 2026-03-30 | 2.1 | Approved
TS-0173 | RES-003 | WBS-002 | 2026-04-01 | 2 | Approved
TS-0174 | RES-003 | WBS-002 | 2026-04-03 | 2.3 | Approved
TS-0175 | RES-003 | WBS-002 | 2026-04-06 | 2.3 | Approved
TS-0176 | RES-003 | WBS-002 | 2026-04-08 | 1.7 | Approved
TS-0177 | RES-003 | WBS-002 | 2026-04-10 | 1.6 | Approved
TS-0178 | RES-003 | WBS-002 | 2026-04-13 | 1.9 | Approved
TS-0179 | RES-003 | WBS-002 | 2026-04-15 | 1.9 | Approved
TS-0180 | RES-005 | WBS-003 | 2026-04-01 | 7.7 | Approved
TS-0181 | RES-005 | WBS-003 | 2026-04-02 | 7.9 | Approved
TS-0182 | RES-005 | WBS-003 | 2026-04-03 | 7.9 | Approved
TS-0183 | RES-005 | WBS-003 | 2026-04-06 | 8.2 | Approved
TS-0184 | RES-005 | WBS-003 | 2026-04-07 | 7.3 | Approved
TS-0185 | RES-005 | WBS-003 | 2026-04-08 | 7.6 | Approved
TS-0186 | RES-005 | WBS-003 | 2026-04-09 | 7.5 | Approved
TS-0187 | RES-005 | WBS-003 | 2026-04-10 | 8.1 | Approved
TS-0188 | RES-005 | WBS-003 | 2026-04-13 | 7.4 | Approved
TS-0189 | RES-005 | WBS-003 | 2026-04-14 | 7.4 | Approved
TS-0190 | RES-005 | WBS-003 | 2026-04-15 | 7.6 | Approved
TS-0191 | RES-005 | WBS-003 | 2026-04-16 | 7.6 | Approved
TS-0192 | RES-005 | WBS-003 | 2026-04-17 | 7.5 | Approved
TS-0193 | RES-005 | WBS-003 | 2026-04-20 | 7.4 | Approved
TS-0194 | RES-005 | WBS-003 | 2026-04-21 | 8.1 | Approved
TS-0195 | RES-005 | WBS-003 | 2026-04-22 | 7.6 | Approved
TS-0196 | RES-005 | WBS-003 | 2026-04-23 | 8.1 | Approved
TS-0197 | RES-005 | WBS-003 | 2026-04-24 | 7.8 | Approved
TS-0198 | RES-005 | WBS-003 | 2026-04-27 | 7.3 | Approved
TS-0199 | RES-005 | WBS-003 | 2026-04-28 | 8.2 | Approved
TS-0200 | RES-005 | WBS-003 | 2026-04-29 | 8 | Approved
TS-0201 | RES-005 | WBS-003 | 2026-04-30 | 8.2 | Approved
TS-0202 | RES-005 | WBS-003 | 2026-05-01 | 8.1 | Approved
TS-0203 | RES-005 | WBS-003 | 2026-05-04 | 8 | Approved
TS-0204 | RES-005 | WBS-003 | 2026-05-05 | 7.4 | Approved
TS-0205 | RES-005 | WBS-003 | 2026-05-06 | 7.7 | Approved
TS-0206 | RES-005 | WBS-003 | 2026-05-07 | 7.4 | Approved
TS-0207 | RES-005 | WBS-003 | 2026-05-08 | 7.6 | Approved
TS-0208 | RES-005 | WBS-003 | 2026-05-11 | 7.3 | Approved
TS-0209 | RES-005 | WBS-003 | 2026-05-12 | 7.6 | Approved
TS-0210 | RES-005 | WBS-003 | 2026-05-13 | 8.2 | Approved
TS-0211 | RES-005 | WBS-003 | 2026-05-14 | 7.5 | Approved
TS-0212 | RES-005 | WBS-003 | 2026-05-15 | 8 | Approved
TS-0213 | RES-005 | WBS-003 | 2026-05-18 | 7.7 | Approved
TS-0214 | RES-005 | WBS-003 | 2026-05-19 | 7.6 | Approved
TS-0215 | RES-005 | WBS-003 | 2026-05-20 | 8.2 | Approved
TS-0216 | RES-005 | WBS-003 | 2026-05-21 | 8.2 | Approved
TS-0217 | RES-005 | WBS-003 | 2026-05-22 | 7.8 | Approved
TS-0218 | RES-005 | WBS-003 | 2026-05-25 | 7.9 | Approved
TS-0219 | RES-005 | WBS-003 | 2026-05-26 | 7.4 | Approved
TS-0220 | RES-005 | WBS-003 | 2026-05-27 | 7.5 | Approved
TS-0221 | RES-005 | WBS-003 | 2026-05-28 | 8.2 | Approved
TS-0222 | RES-005 | WBS-003 | 2026-05-29 | 7.8 | Approved
TS-0223 | RES-004 | WBS-003 | 2026-04-02 | 4 | Approved
TS-0224 | RES-004 | WBS-003 | 2026-04-07 | 4.2 | Approved
TS-0225 | RES-004 | WBS-003 | 2026-04-09 | 3.6 | Approved
TS-0226 | RES-004 | WBS-003 | 2026-04-14 | 4.1 | Approved
TS-0227 | RES-004 | WBS-003 | 2026-04-16 | 4 | Approved
TS-0228 | RES-004 | WBS-003 | 2026-04-21 | 4.4 | Approved
TS-0229 | RES-004 | WBS-003 | 2026-04-23 | 3.7 | Approved
TS-0230 | RES-004 | WBS-003 | 2026-04-28 | 4.5 | Approved
TS-0231 | RES-004 | WBS-003 | 2026-04-30 | 3.6 | Approved
TS-0232 | RES-004 | WBS-003 | 2026-05-05 | 3.7 | Approved
TS-0233 | RES-004 | WBS-003 | 2026-05-07 | 4.1 | Approved
TS-0234 | RES-004 | WBS-003 | 2026-05-12 | 4.2 | Approved
TS-0235 | RES-004 | WBS-003 | 2026-05-14 | 3.7 | Approved
TS-0236 | RES-004 | WBS-003 | 2026-05-19 | 3.6 | Approved
TS-0237 | RES-004 | WBS-003 | 2026-05-21 | 4.4 | Approved
TS-0238 | RES-004 | WBS-003 | 2026-05-26 | 3.7 | Approved
TS-0239 | RES-004 | WBS-003 | 2026-05-28 | 4.1 | Approved
TS-0240 | RES-002 | WBS-004 | 2026-06-01 | 4.1 | Approved
TS-0241 | RES-002 | WBS-004 | 2026-06-02 | 3.9 | Approved
TS-0242 | RES-002 | WBS-004 | 2026-06-03 | 4.1 | Approved
TS-0243 | RES-002 | WBS-004 | 2026-06-04 | 4 | Approved
TS-0244 | RES-002 | WBS-004 | 2026-06-05 | 4.4 | Approved
TS-0245 | RES-002 | WBS-004 | 2026-06-08 | 3.7 | Approved
TS-0246 | RES-002 | WBS-004 | 2026-06-09 | 4.2 | Approved
TS-0247 | RES-002 | WBS-004 | 2026-06-10 | 3.7 | Approved
TS-0248 | RES-002 | WBS-004 | 2026-06-11 | 3.9 | Approved
TS-0249 | RES-002 | WBS-004 | 2026-06-12 | 4.2 | Approved
TS-0250 | RES-002 | WBS-004 | 2026-06-15 | 3.8 | Approved
TS-0251 | RES-002 | WBS-004 | 2026-06-16 | 3.8 | Approved
TS-0252 | RES-002 | WBS-004 | 2026-06-17 | 4.3 | Approved
TS-0253 | RES-002 | WBS-004 | 2026-06-18 | 3.6 | Approved
TS-0254 | RES-002 | WBS-004 | 2026-06-19 | 4 | Approved
TS-0255 | RES-002 | WBS-004 | 2026-06-22 | 4.5 | Approved
TS-0256 | RES-002 | WBS-004 | 2026-06-23 | 4.5 | Approved
TS-0257 | RES-002 | WBS-004 | 2026-06-24 | 3.6 | Approved
TS-0258 | RES-002 | WBS-004 | 2026-06-25 | 3.7 | Approved
TS-0259 | RES-002 | WBS-004 | 2026-06-26 | 3.8 | Approved
TS-0260 | RES-002 | WBS-004 | 2026-06-29 | 4.4 | Approved
TS-0261 | RES-002 | WBS-004 | 2026-06-30 | 4.4 | Approved
TS-0262 | RES-005 | WBS-004 | 2026-06-01 | 7.9 | Approved
TS-0263 | RES-005 | WBS-004 | 2026-06-02 | 7.4 | Approved
TS-0264 | RES-005 | WBS-004 | 2026-06-03 | 7.2 | Approved
TS-0265 | RES-005 | WBS-004 | 2026-06-04 | 7.8 | Approved
TS-0266 | RES-005 | WBS-004 | 2026-06-05 | 7.7 | Approved
TS-0267 | RES-005 | WBS-004 | 2026-06-08 | 7.6 | Approved
TS-0268 | RES-005 | WBS-004 | 2026-06-09 | 8 | Approved
TS-0269 | RES-005 | WBS-004 | 2026-06-10 | 7.7 | Approved
TS-0270 | RES-005 | WBS-004 | 2026-06-11 | 7 | Approved
TS-0271 | RES-005 | WBS-004 | 2026-06-12 | 7.8 | Approved
TS-0272 | RES-005 | WBS-004 | 2026-06-15 | 7.3 | Approved
TS-0273 | RES-005 | WBS-004 | 2026-06-16 | 7.7 | Approved
TS-0274 | RES-005 | WBS-004 | 2026-06-17 | 7.9 | Approved
TS-0275 | RES-005 | WBS-004 | 2026-06-18 | 7.1 | Approved
TS-0276 | RES-005 | WBS-004 | 2026-06-19 | 7.1 | Approved
TS-0277 | RES-005 | WBS-004 | 2026-06-22 | 7.1 | Approved
TS-0278 | RES-005 | WBS-004 | 2026-06-23 | 7.6 | Approved
TS-0279 | RES-005 | WBS-004 | 2026-06-24 | 7.3 | Approved
TS-0280 | RES-005 | WBS-004 | 2026-06-25 | 7.6 | Approved
TS-0281 | RES-005 | WBS-004 | 2026-06-26 | 7.7 | Approved
TS-0282 | RES-005 | WBS-004 | 2026-06-29 | 7.2 | Approved
TS-0283 | RES-005 | WBS-004 | 2026-06-30 | 7.6 | Approved
TS-0284 | RES-001 | WBS-004 | 2026-06-02 | 2.8 | Approved
TS-0285 | RES-001 | WBS-004 | 2026-06-04 | 3 | Approved
TS-0286 | RES-001 | WBS-004 | 2026-06-09 | 3.4 | Approved
TS-0287 | RES-001 | WBS-004 | 2026-06-11 | 3.3 | Approved
TS-0288 | RES-001 | WBS-004 | 2026-06-16 | 2.6 | Approved
TS-0289 | RES-001 | WBS-004 | 2026-06-18 | 2.9 | Approved
TS-0290 | RES-001 | WBS-004 | 2026-06-23 | 2.8 | Approved
TS-0291 | RES-001 | WBS-004 | 2026-06-25 | 2.5 | Approved
TS-0292 | RES-001 | WBS-004 | 2026-06-30 | 3.3 | Approved
TS-3001 | RES-003 | WBS-007 | 2026-05-15 | 350 | Approved
TS-4001 | RES-003 | WBS-009 | 2026-03-20 | 480 | Approved
TS-4002 | RES-004 | WBS-010 | 2026-04-10 | 1100 | Approved
TS-5001 | RES-001 | WBS-011 | 2026-02-28 | 220 | Approved
TS-5002 | RES-004 | WBS-012 | 2026-03-15 | 800 | Approved
TS-6001 | RES-003 | WBS-013 | 2025-10-25 | 190 | Approved
TS-6002 | RES-004 | WBS-014 | 2025-11-20 | 480 | Approved

## physical_progress
ProgressID | WBS_ID | RecordDate | PercentComplete | ReportedBy
PRG-0001 | WBS-001 | 2026-01-07 | 0.039 | Frank Ellingsen
PRG-0002 | WBS-001 | 2026-01-14 | 0.078 | Frank Ellingsen
PRG-0003 | WBS-001 | 2026-01-21 | 0.117 | Frank Ellingsen
PRG-0004 | WBS-001 | 2026-01-28 | 0.156 | Frank Ellingsen
PRG-0005 | WBS-001 | 2026-02-04 | 0.195 | Frank Ellingsen
PRG-0006 | WBS-001 | 2026-02-11 | 0.234 | Frank Ellingsen
PRG-0007 | WBS-001 | 2026-02-18 | 0.273 | Frank Ellingsen
PRG-0008 | WBS-001 | 2026-02-25 | 0.312 | Frank Ellingsen
PRG-0009 | WBS-001 | 2026-03-04 | 0.351 | Frank Ellingsen
PRG-0010 | WBS-001 | 2026-03-11 | 0.39 | Frank Ellingsen
PRG-0011 | WBS-001 | 2026-03-18 | 0.429 | Frank Ellingsen
PRG-0012 | WBS-001 | 2026-03-25 | 0.468 | Frank Ellingsen
PRG-0013 | WBS-001 | 2026-04-01 | 0.507 | Frank Ellingsen
PRG-0014 | WBS-001 | 2026-04-08 | 0.546 | Frank Ellingsen
PRG-0015 | WBS-001 | 2026-04-15 | 0.585 | Frank Ellingsen
PRG-0016 | WBS-001 | 2026-04-22 | 0.624 | Frank Ellingsen
PRG-0017 | WBS-001 | 2026-04-29 | 0.663 | Frank Ellingsen
PRG-0018 | WBS-001 | 2026-05-06 | 0.702 | Frank Ellingsen
PRG-0019 | WBS-001 | 2026-05-13 | 0.741 | Frank Ellingsen
PRG-0020 | WBS-001 | 2026-05-20 | 0.78 | Frank Ellingsen
PRG-0021 | WBS-001 | 2026-05-27 | 0.819 | Frank Ellingsen
PRG-0022 | WBS-001 | 2026-06-03 | 0.858 | Frank Ellingsen
PRG-0023 | WBS-001 | 2026-06-10 | 0.897 | Frank Ellingsen
PRG-0024 | WBS-001 | 2026-06-17 | 0.936 | Frank Ellingsen
PRG-0025 | WBS-001 | 2026-06-24 | 0.975 | Frank Ellingsen
PRG-0026 | WBS-002 | 2026-02-07 | 0.095 | Frank Ellingsen
PRG-0027 | WBS-002 | 2026-02-14 | 0.19 | Frank Ellingsen
PRG-0028 | WBS-002 | 2026-02-21 | 0.285 | Frank Ellingsen
PRG-0029 | WBS-002 | 2026-02-28 | 0.38 | Frank Ellingsen
PRG-0030 | WBS-002 | 2026-03-07 | 0.408 | Frank Ellingsen
PRG-0031 | WBS-002 | 2026-03-14 | 0.437 | Frank Ellingsen
PRG-0032 | WBS-002 | 2026-03-21 | 0.465 | Frank Ellingsen
PRG-0033 | WBS-002 | 2026-03-28 | 0.645 | Frank Ellingsen
PRG-0034 | WBS-002 | 2026-04-04 | 0.825 | Frank Ellingsen
PRG-0035 | WBS-002 | 2026-04-11 | 1 | Frank Ellingsen
PRG-0036 | WBS-003 | 2026-04-07 | 0.13 | Frank Ellingsen
PRG-0037 | WBS-003 | 2026-04-14 | 0.26 | Frank Ellingsen
PRG-0038 | WBS-003 | 2026-04-21 | 0.39 | Frank Ellingsen
PRG-0039 | WBS-003 | 2026-04-28 | 0.52 | Frank Ellingsen
PRG-0040 | WBS-003 | 2026-05-05 | 0.65 | Frank Ellingsen
PRG-0041 | WBS-003 | 2026-05-12 | 0.78 | Frank Ellingsen
PRG-0042 | WBS-003 | 2026-05-19 | 0.91 | Frank Ellingsen
PRG-0043 | WBS-003 | 2026-05-26 | 1 | Frank Ellingsen
PRG-0044 | WBS-004 | 2026-06-07 | 0.25 | Frank Ellingsen
PRG-0045 | WBS-004 | 2026-06-14 | 0.5 | Frank Ellingsen
PRG-0046 | WBS-004 | 2026-06-21 | 0.75 | Frank Ellingsen
PRG-0047 | WBS-004 | 2026-06-28 | 1 | Frank Ellingsen
PRG-2001 | WBS-005 | 2026-07-31 | 0 | Frank Ellingsen
PRG-2002 | WBS-006 | 2026-07-31 | 0 | Frank Ellingsen
PRG-3001 | WBS-007 | 2026-05-30 | 0.9 | Frank Ellingsen
PRG-3002 | WBS-008 | 2026-05-30 | 0 | Frank Ellingsen
PRG-4001 | WBS-009 | 2026-04-15 | 1 | Frank Ellingsen
PRG-4002 | WBS-010 | 2026-04-15 | 0.6 | Frank Ellingsen
PRG-5001 | WBS-011 | 2026-04-30 | 1 | Frank Ellingsen
PRG-5002 | WBS-012 | 2026-04-30 | 0.875 | Frank Ellingsen
PRG-6001 | WBS-013 | 2026-03-31 | 1 | Frank Ellingsen
PRG-6002 | WBS-014 | 2026-03-31 | 1 | Frank Ellingsen

## raid_log
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
RiskID | Type | Description | Impact | Probability | MitigationStrategy | Owner | Status
R-001 | Risk | Delay in composite carbon sheet deliveries from overseas supplier | High | Medium | Pre-order early or source alternative local supplier | Morten Hansen | Active
A-001 | Assumption | Subcontractor electrician rates remain fixed under contract | Medium | Low | Keep signed SLA agreements as references | Frank Ellingsen | Closed
I-001 | Issue | Astrid Nilsen welder overtime limit breached due to recovery fabrication schedule | Medium | High | Allocate junior welder to assist with low-priority tasks | Morten Hansen | Active
D-001 | Dependency | Sea trials (WBS 4.0) depend on DNV safety and compliance certification approval | High | High | Submit compliance paperwork 2 weeks in advance of handover date | Frank Ellingsen | Active