## Cover
Office Fit-Out Project Control Workbook
PM-EVM compliant workbook map: setup controls, task plan, Gantt, EVM S-curve, dashboard, source dimensions, and fact tables.
Sheet | Purpose | Tab Color Legend
Setup | Project-level controls: project metadata, status date, reporting period, and RAG thresholds. | Color | Category | Sheets
Task Plan | Integrated WBS/task control table linking baseline dates, BAC, progress, AC, EV, variances, forecasts, and RAG status. |  | Navigation / Reference | Cover, Glossary
EVM | Weekly EVM reporting table with cumulative PV, AC, EV, SV, CV, SPI, CPI, EAC, ETC, and VAC. |  | Method / Governance | Method Roadmap, PID, PM-EVM Compliance, Review
EVM Charts | Baseline Gantt schedule and EVM S-curve generated from the same WBS, budget, progress, and actual-cost data. |  | Controls / Planning | Setup, Task Plan, Task Capture, Resource Grid
EVM Dashboard | Management view with KPI tiles, WBS performance breakdown, trends, and RAG coloring. |  | Management Outputs | EVM Dashboard, EVM, EVM Charts
PM-EVM Compliance | Checklist mapping the workbook to the attached PM-EVM guideline. |  | Dimension Data | Dim_Project, Dim_WBS, Dim_Resource, Dim_Calendar
Dim_* / Fact_* | Star-schema source data used by the live formulas and charts. |  | Fact Data | Fact_Baseline_PV, Fact_Actual_Costs, Fact_Physical_Progress
Glossary | Definitions for the EVM, WBS, Gantt, schedule, cost, RAG, and data-model terms used in the workbook.
Method Roadmap | 12-step project management method mapped to workbook sheets and current project controls. | Input / Control / Output Classification
PID | Project Initiation Document template with business case, scope, controls, risk and financial sections. | Class | Meaning | Sheets
Task Capture | Task-list brainstorming sheet based on the attached list-the-tasks method, linked to current WBS. | Input | Source data or user-entered templates that feed calculations. | Dim_Project, Dim_WBS, Dim_Resource, Dim_Calendar, Fact_Baseline_PV, Fact_Actual_Costs, Fact_Physical_Progress, PID, Task Capture, Review
Resource Grid | Weekly hours/cost resource allocation grid adapted from the attached Gantt template. | Control | Assumptions, governance, validation, methods, and planning logic that manage how inputs are interpreted. | Setup, Method Roadmap, PM-EVM Compliance, Task Plan, Resource Grid
Review | GOOD / BAD / BETTER review template and action log. | Output | Management-facing reports, charts, dashboards, and reference views produced from inputs and controls. | Cover, Glossary, EVM Dashboard, EVM, EVM Charts
Garden Gantt Model | Attached garden-office Gantt template implemented with current project weekly hours and cost data.
PERT Diagram | Visio-style PERT network diagram reflecting the current WBS, schedule, progress and RAG status. | Sheet | Class | Reason
Red Actions | Recommended recovery actions for all current red RAG WBS items and control risks. | Cover | Output | Workbook navigation and summary.
Pivot Summary | High-level PivotTables and descriptive statistics for project cost, schedule, EVM, and RAG performance. | Glossary | Output
|  | Review | Input
|  | Setup | Control
|  | PID | Input
|  | Method Roadmap | Control
|  | PM-EVM Compliance | Control
|  | Task Plan | Control
|  | Task Capture | Input
|  | EVM Dashboard | Output
|  | Resource Grid | Control
|  | Dim_Project | Input
|  | Dim_WBS | Input
|  | Dim_Resource | Input
|  | Dim_Calendar | Input
|  | Fact_Baseline_PV | Input
|  | Fact_Actual_Costs | Input
|  | Fact_Physical_Progress | Input
|  | EVM | Output
|  | EVM Charts | Output

## Slicer Controls
Workbook Slicer Controls
Use this panel to filter the source Excel Tables directly. Slicers are grouped by reporting outputs, source inputs, and governance/control tables.
MANAGEMENT OUTPUTS
SOURCE INPUTS
GOVERNANCE / CONTROL
Slicer name | Source area | Field | Caption
slc_Dashboard_Status | Dashboard | Status | Dashboard: Status
slc_Dashboard_Type | Dashboard | Type | Dashboard: Type
slc_TaskPlan_Status | Task Plan | Status | Task Plan: Status
slc_TaskPlan_Type | Task Plan | Type | Task Plan: Type
slc_TaskPlan_WBSID | Task Plan | WBS ID | Task Plan: WBS ID
slc_EVM_Status | EVM | Status | EVM: Status
slc_EVM_Week | EVM | Week | EVM: Week
slc_PERT_RAG | PERT | RAG | PERT: RAG
slc_Resource_Measure | Resource Grid | Measure | Resource Grid: Measure
slc_Resource_RAG | Resource Grid | RAG | Resource Grid: RAG
slc_Calendar_Month | Calendar | Month | Calendar: Month
slc_Calendar_Week | Calendar | Week | Calendar: Week
slc_DimResource_Role | Resources | Role | Resources: Role
slc_DimWBS_Type | WBS Master | Type | WBS Master: Type
slc_DimWBS_WBSID | WBS Master | WBS ID | WBS Master: WBS ID
slc_ActualCosts_ResourceID | Actual Costs | Resource | Actual Costs: Resource
slc_ActualCosts_WBSID | Actual Costs | WBS ID | Actual Costs: WBS ID
slc_BaselinePV_WBSID | Baseline PV | WBS ID | Baseline PV: WBS ID
slc_Progress_WBSID | Progress | WBS ID | Progress: WBS ID
slc_TaskCapture_Type | Task Capture | Type | Task Capture: Type
slc_Method_Status | Method Roadmap | Status | Method Roadmap: Status
slc_PIDRisk_Owner | PID Risks | Owner | PID Risks: Owner
slc_PIDRisk_RAG | PID Risks | RAG | PID Risks: RAG
slc_Review_Owner | Review Actions | Owner | Review Actions: Owner
slc_Review_RAG | Review Actions | RAG | Review Actions: RAG
slc_Compliance_Status | PM-EVM | Status | PM-EVM: Status
slc_Glossary_Category | Glossary | Category | Glossary: Category
slc_Method_Owner | Method Roadmap | Owner | Method Roadmap: Owner
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Glossary
Project Control Glossary
Definitions for the EVM, WBS, Gantt, schedule, cost, and RAG terms used across this workbook.
Category | Term | Abbrev. | Definition | Workbook reference
Project setup | Project Start |  | Approved start date for the project control baseline. | Setup!B7 / Dim_Project!C2
Project setup | Project End |  | Approved planned end date for the project. | Setup!B8 / Dim_Project!D2
Project setup | Status Date |  | Cut-off date for reported progress, actual costs, and EVM metrics. | Setup!B9 / EVM Dashboard!B4
Scope / WBS | Work Breakdown Structure | WBS | Hierarchical breakdown of project scope into controllable work packages or activities. | Dim_WBS / Task Plan
Scope / WBS | WBS ID |  | Unique identifier used to connect WBS activities to baseline PV, actual costs, and progress facts. | Dim_WBS!A:A
Scope / WBS | Activity / Task |  | A controllable unit of project work with budget, schedule, progress, and cost tracking. | Task Plan!C:C
Schedule | Baseline Start |  | Planned start date for a WBS activity from the approved baseline. | Task Plan!E:E
Schedule | Baseline Finish |  | Planned finish date for a WBS activity from the approved baseline. | Task Plan!F:F
Schedule | Duration Days |  | Calendar-day span between baseline start and finish dates. | Task Plan!G:G
Schedule | Gantt Chart |  | Timeline chart showing planned activity timing and duration by WBS activity. | EVM Charts!Gantt Schedule
Cost / EVM | Budget at Completion | BAC | Approved total budget for the project or WBS activity. | Setup!B11 / Task Plan!H:H
Cost / EVM | Planned Value | PV | Budgeted value of work planned to be complete by a given date. | Task Plan!I:I / EVM!C:C
Cost / EVM | Actual Cost | AC | Actual cost incurred by a given date. | Task Plan!J:J / EVM!D:D
Cost / EVM | Physical Progress | Progress % | Latest reported percent complete for each WBS activity as of the status date. | Task Plan!K:K
Cost / EVM | Earned Value | EV | Budgeted value of the work actually completed; calculated as BAC × progress. | Task Plan!L:L / EVM!E:E
Variance | Schedule Variance | SV | EV minus PV; negative means less work completed than planned. | Task Plan!M:M / EVM!F:F
Variance | Cost Variance | CV | EV minus AC; negative means cost overrun for completed work. | Task Plan!N:N / EVM!G:G
Performance index | Schedule Performance Index | SPI | EV divided by PV; below 1.0 indicates unfavorable schedule efficiency. | Task Plan!O:O / EVM!H:H
Performance index | Cost Performance Index | CPI | EV divided by AC; below 1.0 indicates unfavorable cost efficiency. | Task Plan!P:P / EVM!I:I
Forecast | Estimate at Completion | EAC | Forecast final project or WBS cost, typically BAC divided by CPI. | Task Plan!Q:Q / EVM!K:K
Forecast | Estimate to Complete | ETC | Forecast remaining cost to complete the work; EAC minus AC. | Task Plan!R:R / EVM!L:L
Forecast | Variance at Completion | VAC | Expected budget variance at completion; BAC minus EAC. | Task Plan!S:S / EVM!M:M
Chart | EVM S-Curve |  | Line chart comparing cumulative PV, EV, and AC over time. | EVM Charts!EVM S-Curve
RAG | Green |  | Good condition: on/above plan, favorable variance, or acceptable performance threshold. | Setup!A18:D18
RAG | Amber |  | Watch condition: close to threshold or mid-progress; monitor closely. | Setup!A19:D19
RAG | Red |  | Action condition: negative variance, low progress, CPI/SPI below threshold, or overrun. | Setup!A20:D20
Reporting | Dashboard |  | Management summary view showing KPIs, WBS performance, trend data, and RAG status. | EVM Dashboard!A1:P47
Reporting | Tie-out |  | Validation that dashboard KPIs match the detailed EVM reporting table at the status date. | EVM!H19:M25
Data model | Dimension Table | Dim | Reference table describing projects, WBS, resources, or calendar dates. | Dim_Project / Dim_WBS / Dim_Resource / Dim_Calendar
Data model | Fact Table | Fact | Transaction or event table containing planned values, actual costs, or progress observations. | Fact_Baseline_PV / Fact_Actual_Costs / Fact_Physical_Progress
Workbook classification | Input |  | Source data or user-entered content that feeds project calculations and reports. | Cover!D13:H39
Workbook classification | Control |  | Assumptions, thresholds, validation, governance, and planning logic used to interpret inputs. | Cover!D13:H39
Workbook classification | Output |  | Reports, charts, dashboards, and references produced from the input data and control logic. | Cover!D13:H39

## Review
Project Review & Lessons
Review template from attachment: GOOD / BAD / BETTER plus action log for plan adjustments and lessons learned.
Project Description | Office Fit-Out
Project Period | 2026-05-04 to 2026-07-26
Status Date | 2026-06-30
Review Owner | Frank Ellingsen
Review Date | 2026-08-04
GOOD — what went well that others should repeat?
BAD — what mistakes were made or unexpected issues occurred?
BETTER / ACTION LOG | Owner | Due date | Decision required? | RAG | Linked workbook evidence
Investigate schedule slippage driving SPI below 1.0 | Project Controls |  | Yes | Red | EVM Dashboard!J10 / Task Plan!O17
Review cost efficiency and current EAC forecast | Project Controls |  | Yes | Red | EVM Dashboard!G10 / Task Plan!Q17
Confirm mitigation for red WBS activities in Gantt | Project Manager |  | Yes | Red | EVM Charts!Gantt Schedule
Check future material/subcontractor dependencies | Planner |  | No | Amber | Task Plan / Resource Grid
Capture lessons from completed WBS items | Project Team |  | No | Amber | Task Capture / Review
Review source | 13.1.2 Review Template.pdf

## PID
Project Initiation Document (PID)
PID template from the attached method, prefilled with current workbook metadata where available. Fill yellow cells during project definition.
Project header
Project Name | Office Fit-Out
Project Number | P101
Project Risk Level | H/M/L
Prepared by | Frank Ellingsen
Date | 2026-08-04
Persons consulted
Key Driver | Cost / Quality / Time
1. Business Case
Why this project; why now; options considered; what if we do not do it; benefits; payback period.
2.1 In Scope / Included
Work and deliverables included in the project.
2.2 Out of Scope / Excluded
Work explicitly excluded from the project.
2.3 Dependencies
How the project impacts or is impacted by other projects or programmes.
2.4 Constraints
Deadlines, budget limits, resource limitations or other delivery constraints.
2.5 Assumptions
Assumptions currently being used for planning.
3. Key Actions Proposed
Must include a high-level or detailed Gantt chart.
4. Project Controls and Reporting
How progress will be reported, frequency, method and responsibility.
Frequency / timing | How control is reported | Responsibility | Next report date | Status
Weekly | EVM Dashboard + EVM Charts | Project Controls |  | Active
Stage end | PID / Review pack | Project Manager |  | Planned
Monthly | Board summary | Project Manager |  | Planned
5. Risk Control
Project risks and containment measures.
Project Risk | Containment Measures | Owner | Due Date | RAG
Schedule slippage | Monitor SPI and Gantt status line; escalate red WBS tasks. | Project Controls |  | Red
Cost overrun | Monitor CPI/CV/EAC and review WBS cost drivers. | Project Controls |  | Red
Resource availability | Use weekly Resource Grid to identify conflicts. | Resource Manager |  | Amber
Scope creep | Confirm in/out of scope and change-control route in PID. | Project Manager |  | Amber
Quality issue | Define acceptance criteria and quality checks by task. | Project Manager |  | Amber
Supplier delay | Track procurement/material activities and delivery milestones. | Project Manager |  | Amber
6. Financial Implications
Quarterly/annual financial profile adapted from the PID template; Year 1 is linked to the current baseline planned value.
Financial Implications | Q1 | Q2 | Q3 | Q4 | Total
Amount Year 1 | 220233.34 | 48416.66 | 0 | 0 | 268650
Amount Year 2 | 0 | 0 | 0 | 0 | 0
Amount Year 3 | 0 | 0 | 0 | 0 | 0
Amount Year 4 | 0 | 0 | 0 | 0 | 0
Amount Year 5 | 0 | 0 | 0 | 0 | 0

## Method Roadmap
12-Step Project Management Method Roadmap
Course method embedded into the workbook: define, list, sequence, estimate, check, Gantt, resource, risk, monitor progress/cost, adjust, and review.
Step | Method step | Purpose | Workbook implementation | Primary sheet / range | Owner | Status | Source
1 | Define the project | Create the project definition and controls. | PID template added with live project metadata. | PID!A1:H50 | Project Manager | Active | 1.2 12 Step Process / 2.1.2 PID template
2 | List the tasks | Capture all tasks without initially worrying about order, cost, or time. | Task Capture sheet added; WBS imported from current Dim_WBS and grouped by type. | Task Capture!A4:J18 | Project Team | Active | 3.1.5 List the Tasks / 4.1 List of Tasks
3 | Establish task order | Convert brainstormed tasks into planned sequencing. | Task Plan and Gantt use WBS order and baseline dates. | Task Plan!A4:T17 | Planner | Active | 1.2 12 Step Process
4 | Estimate time | Estimate duration by task. | Baseline start, finish, and duration calculated per WBS. | Task Plan!E5:G17 | Planner | Active | 1.2 12 Step Process
5 | Margin check & reality check | Check whether dates, budget, and resource assumptions are feasible. | Status tie-out, EVM checks, and RAG indicators added. | EVM!H19:M25 | Project Controls | Active | 1.2 12 Step Process
6 | Gantt Chart | Show planned timing and status. | Gantt chart with RAG bars and status-date marker exists. | EVM Charts!Gantt Schedule | Project Controls | Active | 8.1.2 Gantt templates
7 | Resource allocation | Map tasks to people/resources and weekly loading. | Resource Grid added with weekly hours and costs by WBS. | Resource Grid!A4:Z35 | Resource Manager | Active | 8.1.2 Gantt template from garden office
8 | Predicting & reducing risk | Identify project risks and containment measures. | PID risk-control register added. | PID!A63:E70 | Project Manager | Template ready | 2.1.2 PID template
9 | Monitoring progress | Track completion against plan. | Progress is linked from Fact_Physical_Progress to Task Plan and dashboard. | Task Plan!K5:K17 | Project Controls | Active | 1.2 12 Step Process
10 | Monitoring cost | Track actual cost and forecast. | EVM reporting monitors AC, CV, CPI, EAC, ETC, VAC. | EVM!A4:N16 | Project Controls | Active | 1.2 12 Step Process
11 | Adjusting the plan | Use EVM and RAG exceptions to trigger decisions. | Decision/action log added to Review. | Review!A20:F28 | Project Board | Template ready | 1.2 12 Step Process
12 | Review & lessons | Capture good, bad, better after delivery. | Review sheet added with GOOD / BAD / BETTER structure. | Review!A4:F17 | Project Team | Template ready | 13.1.2 Review Template

## PM-EVM Compliance
PM-EVM Compliance Checklist
Workbook compliance map against the attached PM-EVM guideline: WBS, Gantt, EVM, dashboard, live formulas, and exception-focused reporting.
Guideline requirement | Workbook implementation | Location | Status | Evidence
Setup controls: project metadata, status date, reporting period, rates/thresholds | Added setup control sheet with live project metadata and thresholds | Setup!A4:D20 | Compliant | PM-EVM.md lines 117-126
Task Plan as integrated WBS/task control view | Added live task table combining WBS, dates, BAC, PV, AC, progress, EV, variances, forecasts and RAG | Task Plan!A4:T17 | Compliant | PM-EVM.md lines 120-125
Gantt display tied to WBS baseline dates | Existing EVM Charts Gantt uses WBS activities, baseline start/finish and duration | EVM Charts!Gantt Schedule | Compliant | PM-EVM.md lines 122-125
EVM by reporting period with PV, EV, AC, SV, CV, SPI, CPI, BAC, EAC, ETC, VAC | Added EVM reporting table with weekly live formulas | EVM!A4:N16 | Compliant | PM-EVM.md lines 123-124
S-curve shows cumulative PV, EV, and AC over time | Existing EVM S-curve chart is sourced from weekly cumulative helper table | EVM Charts!EVM S-Curve | Compliant | PM-EVM.md lines 50-54
Dashboard summarizes management KPIs and top WBS exceptions | Existing dashboard has KPI tiles, WBS table, RAG, variance/status fields | EVM Dashboard!A1:P47 | Compliant | PM-EVM.md lines 781-785
Exception-focused reporting with RAG / traffic-light indicators | RAG rules applied across performance indices, progress, variances, and status cells | EVM Dashboard, Task Plan, EVM | Compliant | PM-EVM.md lines 781-785
Consistent WBS codes, budgets, dates, and actuals across views | Task Plan, EVM, Gantt and dashboard all reference Dim_WBS and fact tables | Dim_WBS / Fact_* | Compliant | PM-EVM.md lines 270-274
Validate formulas and totals | Added formula validation and status-date tie-out to dashboard KPIs | EVM!H19:M25 | Compliant | PM-EVM.md lines 783-785

## Setup
Setup Controls
Single place to review project metadata, status date, reporting period, and RAG thresholds used by the control workbook.
Control | Value
Project ID | P101
Project Name | Office Fit-Out
Project Start | 2026-05-04
Project End | 2026-07-26
Status Date | 2026-06-30
Reporting Period | Weekly
Budget at Completion (BAC) | 268650
CPI/SPI Red Threshold | 0.95
CPI/SPI Green Threshold | 1
Progress Amber Threshold | 0.5
Progress Green Threshold | 0.8
RAG | Metric | Rule | Interpretation
Green | CPI/SPI | >= 1.00 | On or above plan
Amber | CPI/SPI | 0.95 to < 1.00 | Near threshold / watch
Red | CPI/SPI | < 0.95 | Action required

## Task Plan
Task Plan
Integrated WBS control table: one live task-level view for scope, schedule, budget, progress, actuals, forecasts, and RAG status.
WBS ID | WBS Code | Task / Activity | Type | Baseline Start | Baseline Finish | Duration Days | BAC (NOK) | PV @ Status | AC @ Status | Progress % | EV @ Status | SV | CV | SPI | CPI | EAC | ETC | VAC | Status
WBS-01 | 1 | Project Management | Labor | 2026-05-04 | 2026-07-26 | 84 | 18000 | 13500 | 9600 | 50% | 9000 | -4500 | -600 | 0.66667 | 0.9375 | 19200 | 9600 | -1200 | Red
WBS-02 | 2 | Site Survey & Mobilization | Labor | 2026-05-04 | 2026-05-10 | 7 | 8500 | 8500 | 8700 | 100% | 8500 | 0 | -200 | 1 | 0.97701 | 8700 | 0 | -200 | Red
WBS-03 | 3 | Design & Engineering | Labor | 2026-05-04 | 2026-05-24 | 21 | 19200 | 19200 | 18195.04 | 100% | 19200 | 0 | 1004.96 | 1 | 1.0552 | 18195.04 | 0 | 1004.96 | Green
WBS-04 | 4 | Procurement - Materials | Material | 2026-05-11 | 2026-06-07 | 28 | 42000 | 42000 | 41300 | 100% | 42000 | 0 | 700 | 1 | 1.0169 | 41300 | 0 | 700 | Green
WBS-05 | 5 | Demolition & Prep | Labor | 2026-05-11 | 2026-05-31 | 21 | 13200 | 13200 | 13408.16 | 100% | 13200 | 0 | -208.16 | 1 | 0.98448 | 13408.16 | 0 | -208.16 | Red
WBS-06 | 6 | Electrical Rough-In | Labor | 2026-05-25 | 2026-06-14 | 21 | 26000 | 26000 | 26206.24 | 70% | 18200 | -7800 | -8006.24 | 0.7 | 0.69449 | 37437.4857 | 11231.2457 | -11437.4857 | Red
WBS-07 | 7 | HVAC Installation | Subcontractor | 2026-06-01 | 2026-06-28 | 28 | 36000 | 36000 | 17476.8 | 40% | 14400 | -21600 | -3076.8 | 0.4 | 0.82395 | 43692 | 26215.2 | -7692 | Red
WBS-08 | 8 | Partitions & Drywall | Subcontractor | 2026-06-08 | 2026-07-05 | 28 | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -21032.004 | -131.204 | 0.24886 | 0.98152 | 28527.2265 | 21428.0265 | -527.2265 | Red
WBS-09 | 9 | Flooring | Material | 2026-06-22 | 2026-07-12 | 21 | 35750 | 23833.34 | 0 | 0% | 0 | -23833.34 | 0 | 0 | 1 | 35750 | 35750 | 0 | Red
WBS-10 | 10 | Fixtures & Furniture | Material | 2026-06-29 | 2026-07-19 | 21 | 30000 | 10000 | 0 | 0% | 0 | -10000 | 0 | 0 | 1 | 30000 | 30000 | 0 | Red
WBS-11 | 11 | Testing / Commissioning | Labor | 2026-07-13 | 2026-07-26 | 14 | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 8400 | 8400 | 0 | Green
WBS-12 | 12 | Handover & Closeout | Labor | 2026-07-20 | 2026-07-26 | 7 | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 3600 | 3600 | 0 | Green
Total / Project Portfolio | [5 empty] | 84 | 268650 | 220233.34 | 141985.44 | 48.94% | 131467.996 | -88765.344 | -10517.444 | 0.59695 | 0.92593 | 290142.0088 | 148156.5688 | -21492.0088 | Red
Formulas:
Baseline Start = MINIFS(Fact_Baseline_PV!$A:$A,Fact_Baseline_PV!$B:$B,[WBS ID])
Baseline Finish = MAXIFS(Fact_Baseline_PV!$A:$A,Fact_Baseline_PV!$B:$B,[WBS ID])+6

## Task Capture
Task Capture / List the Tasks
Method: first list all tasks without worrying about order, cost, or time; then group into phases and convert into the controlled Task Plan.
Phase / Area | Task | WBS ID | Type | Included? | Event / Milestone? | Owner | Notes | Source / next action | Mapped to Task Plan
Labor | Project Management | WBS-01 | Labor | Yes |  |  |  | Imported from current WBS | 5
Labor | Site Survey & Mobilization | WBS-02 | Labor | Yes |  |  |  | Imported from current WBS | 6
Labor | Design & Engineering | WBS-03 | Labor | Yes |  |  |  | Imported from current WBS | 7
Material | Procurement - Materials | WBS-04 | Material | Yes |  |  |  | Imported from current WBS | 8
Labor | Demolition & Prep | WBS-05 | Labor | Yes |  |  |  | Imported from current WBS | 9
Labor | Electrical Rough-In | WBS-06 | Labor | Yes |  |  |  | Imported from current WBS | 10
Subcontractor | HVAC Installation | WBS-07 | Subcontractor | Yes |  |  |  | Imported from current WBS | 11
Subcontractor | Partitions & Drywall | WBS-08 | Subcontractor | Yes |  |  |  | Imported from current WBS | 12
Material | Flooring | WBS-09 | Material | Yes |  |  |  | Imported from current WBS | 13
Material | Fixtures & Furniture | WBS-10 | Material | Yes |  |  |  | Imported from current WBS | 14
Labor | Testing / Commissioning | WBS-11 | Labor | Yes |  |  |  | Imported from current WBS | 15
Labor | Handover & Closeout | WBS-12 | Labor | Yes |  |  |  | Imported from current WBS | 16
Brainstorm / new | [7 empty] | Add new tasks here before sequencing
Brainstorm / new | [7 empty] | Add new tasks here before sequencing
Example task-list method from attachment | Garden office example grouped tasks: clear the space, foundations, buy the shed, install shed, legal. Use this area to add unstructured tasks before converting them to WBS.

## EVM Dashboard
OFFICE FIT-OUT - PROJECT CONTROLLING DASHBOARD
EVM Performance Status ¦ Tufte-Compliant Design ¦ Data-Ink Maximized
Status Date: | 2026-06-30 |  | Status Week: | 8 |  | Sector: | Corporate Real Estate | [5 empty] | RAG Legend | Rule | Meaning
[13 empty] | Green | Good | On/above plan or low exposure
BUDGET AT COMPLETION (BAC) |  |  | PLANNED VALUE (PV) |  |  | ACTUAL COST (AC) |  |  | EARNED VALUE (EV) |  |  |  | Amber | Watch | Near threshold / medium exposure
268650 |  |  | 220233.34 |  |  | 141985.44 |  |  | 131467.996 |  |  |  | Red | Action | Behind plan, overrun, or high exposure
COST VARIANCE (CV) |  |  | SCHEDULE VARIANCE (SV) |  |  | CPI (COST INDEX) |  |  | SPI (SCHEDULE INDEX)
-10517.444 |  |  | -88765.344 |  |  | 0.92593 |  |  | 0.59695
ESTIMATE AT COMPLETION (EAC) |  |  | ESTIMATE TO COMPLETE (ETC) |  |  | VARIANCE AT COMPLETION (VAC) |  |  | PROJECT PROGRESS %
290142.0088 |  |  | 148156.5688 |  |  | -21492.0088 |  |  | 48.94%
WBS Element Performance Breakdown
WBS ID | Activity Name | Type | Budget (BAC) | Planned Value (PV) | Actual Cost (AC) | Progress % | Earned Value (EV) | CV | SV | CPI | SPI | EAC | ETC | VAC | Status
WBS-01 | Project Management | Labor | 18000 | 13500 | 9600 | 50% | 9000 | -600 | -4500 | 0.9375 | 0.66667 | 19200 | 9600 | -1200 | 🔴 Overrun
WBS-02 | Site Survey & Mobilization | Labor | 8500 | 8500 | 8700 | 100% | 8500 | -200 | 0 | 0.97701 | 1 | 8700 | 0 | -200 | 🔴 Overrun
WBS-03 | Design & Engineering | Labor | 19200 | 19200 | 18195.04 | 100% | 19200 | 1004.96 | 0 | 1.0552 | 1 | 18195.04 | 0 | 1004.96 | On Track
WBS-04 | Procurement - Materials | Material | 42000 | 42000 | 41300 | 100% | 42000 | 700 | 0 | 1.0169 | 1 | 41300 | 0 | 700 | On Track
WBS-05 | Demolition & Prep | Labor | 13200 | 13200 | 13408.16 | 100% | 13200 | -208.16 | 0 | 0.98448 | 1 | 13408.16 | 0 | -208.16 | 🔴 Overrun
WBS-06 | Electrical Rough-In | Labor | 26000 | 26000 | 26206.24 | 70% | 18200 | -8006.24 | -7800 | 0.69449 | 0.7 | 37437.4857 | 11231.2457 | -11437.4857 | 🔴 Overrun
WBS-07 | HVAC Installation | Subcontractor | 36000 | 36000 | 17476.8 | 40% | 14400 | -3076.8 | -21600 | 0.82395 | 0.4 | 43692 | 26215.2 | -7692 | 🔴 Overrun
WBS-08 | Partitions & Drywall | Subcontractor | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -131.204 | -21032.004 | 0.98152 | 0.24886 | 28527.2265 | 21428.0265 | -527.2265 | 🔴 Overrun
WBS-09 | Flooring | Material | 35750 | 23833.34 | 0 | 0% | 0 | 0 | -23833.34 | 1 | 0 | 35750 | 35750 | 0 | 🔴 Overrun
WBS-10 | Fixtures & Furniture | Material | 30000 | 10000 | 0 | 0% | 0 | 0 | -10000 | 1 | 0 | 30000 | 30000 | 0 | 🔴 Overrun
WBS-11 | Testing / Commissioning | Labor | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 8400 | 8400 | 0 | On Track
WBS-12 | Handover & Closeout | Labor | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 3600 | 3600 | 0 | On Track
Total / Project Portfolio |  |  | 268650 | 220233.34 | 141985.44 | 48.94% | 131467.996 | -10517.444 | -88765.344 | 0.92593 | 0.59695 | 290142.0088 | 148156.5688 | -21492.0088 | 🔴 Overrun
Weekly Cumulative Performance Trends
Week | Week Date | Weekly PV | Cum PV | Weekly AC | Cum AC | Cum EV | CV | SV | CPI | SPI
1 | 2026-05-04 | 16400 | 16400 | 16295.04 | 16295.04 | 15087.994 | -1207.046 | -1312.006 | 0.92593 | 0.92
2 | 2026-05-11 | 22800 | 39200 | 22654.08 | 38949.12 | 51151.9976 | 12202.8776 | 11951.9976 | 1.3133 | 1.3049
3 | 2026-05-18 | 22800 | 62000 | 22654.08 | 61603.2 | 108191.9976 | 46588.7976 | 46191.9976 | 1.7563 | 1.745
4 | 2026-05-25 | 25066.67 | 87066.67 | 24906.24 | 86509.44 | 188293.3256 | 101783.8856 | 101226.6556 | 2.1766 | 2.1626
5 | 2026-06-01 | 29666.67 | 116733.34 | 29476.8 | 115986.24 | 295687.9996 | 179701.7596 | 178954.6596 | 2.5493 | 2.533
6 | 2026-06-08 | 26166.66 | 142900 | 25999.2 | 141985.44 | 427155.9956 | 285170.5556 | 284255.9956 | 3.0084 | 2.9892
7 | 2026-06-15 | 17500 | 160400 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 266755.9956 | 3.0084 | 2.6631
8 | 2026-06-22 | 29416.67 | 189816.67 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 237339.3256 | 3.0084 | 2.2504
9 | 2026-06-29 | 30416.67 | 220233.34 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 206922.6556 | 3.0084 | 1.9396
10 | 2026-07-06 | 23416.66 | 243650 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 183505.9956 | 3.0084 | 1.7532
11 | 2026-07-13 | 15700 | 259350 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 167805.9956 | 3.0084 | 1.647
12 | 2026-07-20 | 9300 | 268650 | 0 | 141985.44 | 427155.9956 | 285170.5556 | 158505.9956 | 3.0084 | 1.59

## Red Actions
Red RAG Action Recommendations
Focused recovery actions for WBS items and control risks currently flagged Red. Evidence is pulled live from tbl_Task_Plan.
STORY IN BRIEF
The red status is mainly schedule-driven: Flooring, Fixtures & Furniture, Partitions & Drywall, HVAC, and Electrical Rough-In are the recovery priorities because their SPI and schedule variances are pulling the project off plan. Cost exposure is concentrated in Electrical Rough-In and HVAC, while completed red tasks need closeout variance review rather than delivery acceleration. The recommended response is a short recovery sprint: remove blockers, confirm subcontractor/material readiness, reset near-term dates, and escalate decision items already logged in the Review sheet.
Red WBS items |  | Worst red SPI |  | Largest red SV |  | Red forecast overrun
8 |  | 0 |  | -23833.34 |  | 21264.8722
Priority | WBS ID | Activity | Red driver | Live evidence | Recommended action | Owner | Due date
1 | WBS-09 | Flooring | Schedule / not started | 0% complete; SPI 0.00; CPI 1.00; SV -23,833 NOK | Start recovery immediately: confirm all prerequisites from HVAC/drywall, lock crew/material availability, and publish a catch-up start/finish date within the next planning cycle. | Planner | 2026-07-02
2 | WBS-08 | Partitions & Drywall | Low progress / schedule | 25% complete; SPI 0.25; CPI 0.98; SV -21,032 NOK | Run a blocker review with electrical rough-in and subcontractor leads; add resources or resequence drylining areas to recover the critical path. | Project Manager | 2026-07-02
3 | WBS-07 | HVAC Installation | Subcontractor schedule + cost | 40% complete; SPI 0.40; CPI 0.82; SV -21,600 NOK | Require a subcontractor recovery plan: committed crew levels, daily output targets, and commercial review of cost burn versus earned progress. | Project Manager | 2026-07-02
4 | WBS-06 | Electrical Rough-In | Cost + schedule | 70% complete; SPI 0.70; CPI 0.69; SV -7,800 NOK | Hold a root-cause review on low CPI/SPI; separate scope change from productivity loss, update EAC, and escalate any funding/date decision. | Project Controls | 2026-07-02
5 | WBS-10 | Fixtures & Furniture | Future work at risk | 0% complete; SPI 0.00; CPI 1.00; SV -10,000 NOK | Confirm fixture/furniture procurement, delivery slots, and installation dependency on flooring; prepare fallback suppliers if dates slip. | Procurement / Planner | 2026-07-05
6 | WBS-01 | Project Management | Management effort behind plan | 50% complete; SPI 0.67; CPI 0.94; SV -4,500 NOK | Increase recovery cadence: daily issue log, weekly decision pack, and named owners for every red WBS mitigation. | Project Manager | 2026-07-02
7 | WBS-02 | Site Survey & Mobilization | Completed cost variance | 100% complete; SPI 1.00; CPI 0.98; SV 0 NOK | Close out the small overrun: validate final actuals, code any one-off cost correctly, and prevent it from distorting future forecasts. | Project Controls | 2026-07-07
8 | WBS-05 | Demolition & Prep | Completed cost variance | 100% complete; SPI 1.00; CPI 0.98; SV 0 NOK | Close out demolition/prep variance and capture lessons learned for estimate accuracy and crew productivity assumptions. | Project Controls | 2026-07-07
ESCALATE / TRACK
Use Review!A21:F23 as the decision log for schedule slippage, EAC/cost review, and red WBS mitigation. Use PID!A64:E65 as the risk register entries for schedule slippage and cost overrun. Refresh this sheet after changing the source Task Plan or thresholds.

## Pivot Summary
High-Level Pivot Summary & Descriptive Statistics
PivotTables summarize the key project-control tables; descriptive statistics are live formulas linked to the Task Plan source range.
STORY IN BRIEF
The project is under schedule pressure, with red WBS items concentrated in unfinished material/subcontractor and rough-in work. The PivotTables summarize exposure by Type, Status, WBS, and week; the descriptive statistics quantify central tendency and outliers across task-level cost and schedule metrics.
Red WBS | Total BAC | Actual Cost | Earned Value | Avg SPI | Avg CPI | Forecast overrun
0 | 0 | 0 | 0 | 0 | 0 | 0
DESCRIPTIVE STATISTICS
Metric | Count | Mean | Median | Std Dev | Min | Max
BAC (NOK) | 0 | 0 | 0 | 0 | 0 | 0
PV @ Status | 0 | 0 | 0 | 0 | 0 | 0
AC @ Status | 0 | 0 | 0 | 0 | 0 | 0
EV @ Status | 0 | 0 | 0 | 0 | 0 | 0
Progress % | 0 | 0% | 0% | 0% | 0% | 0%
SPI | 0 | 0 | 0 | 0 | 0 | 0
CPI | 0 | 0 | 0 | 0 | 0 | 0
SV | 0 | 0 | 0 | 0 | 0 | 0
CV | 0 | 0 | 0 | 0 | 0 | 0
VAC | 0 | 0 | 0 | 0 | 0 | 0
PIVOT: COST / VALUE BY TYPE
Row Labels | Sum of BAC (NOK) | Sum of PV @ Status | Sum of AC @ Status | Sum of EV @ Status | Sum of SV | Sum of CV | Sum of VAC
Labor | 96900 | 80400 | 76109.44 | 68100 | -12300 | -8009.44 | -12040.6857
Material | 107750 | 75833.34 | 41300 | 42000 | -33833.34 | 700 | 700
Subcontractor | 64000 | 64000 | 24576 | 21367.996 | -42632.004 | -3208.004 | -8219.2265
Grand Total | 268650 | 220233.34 | 141985.44 | 131467.996 | -88765.344 | -10517.444 | -19559.9122
PIVOT: COST / VALUE BY STATUS
Row Labels | Sum of BAC (NOK) | Sum of PV @ Status | Sum of AC @ Status | Sum of EV @ Status | Sum of SV | Sum of CV | Sum of VAC
Green | 73200 | 61200 | 59495.04 | 61200 | 0 | 1704.96 | 1704.96
Red | 195450 | 159033.34 | 82490.4 | 70267.996 | -88765.344 | -12222.404 | -21264.8722
Grand Total | 268650 | 220233.34 | 141985.44 | 131467.996 | -88765.344 | -10517.444 | -19559.9122
PIVOT: ACTUAL COSTS BY WBS
Row Labels | Sum of Actual_Cost | Sum of Hours_Worked
WBS-01 | 9600 | 6.3
WBS-02 | 8700 | 3.95
WBS-03 | 18195.04 | 7.6
WBS-04 | 41300 | 0
WBS-05 | 13408.16 | 6.05
WBS-06 | 26206.24 | 10.1
WBS-07 | 17476.8 | 0
WBS-08 | 7099.2 | 0
Grand Total | 141985.44 | 34
PIVOT: WEEKLY EVM SUMMARY
Row Labels | Sum of Cum PV | Sum of Cum AC | Sum of Cum EV | Sum of SV | Sum of CV | Sum of VAC
1 | 16400 | 16295.04 | 15087.994 | -1312.006 | -1207.046 | -21492.1154
2 | 39200 | 38949.12 | 36064.0036 | -3135.9964 | -2885.1164 | -21491.971
3 | 62000 | 61603.2 | 57040 | -4960 | -4563.2 | -21492
4 | 87066.67 | 86509.44 | 80101.328 | -6965.342 | -6408.112 | -21492.0193
5 | 116733.34 | 115986.24 | 107394.674 | -9338.666 | -8591.566 | -21491.9802
6 | 142900 | 141985.44 | 131467.996 | -11432.004 | -10517.444 | -21492.0088
7 | 160400 | 141985.44 | 131467.996 | -28932.004 | -10517.444 | -21492.0088
8 | 189816.67 | 141985.44 | 131467.996 | -58348.674 | -10517.444 | -21492.0088
9 | 220233.34 | 141985.44 | 131467.996 | -88765.344 | -10517.444 | -21492.0088
10 | 243650 | 141985.44 | 131467.996 | -112182.004 | -10517.444 | -21492.0088
11 | 259350 | 141985.44 | 131467.996 | -127882.004 | -10517.444 | -21492.0088
12 | 268650 | 141985.44 | 131467.996 | -137182.004 | -10517.444 | -21492.0088
Grand Total | 1806400.02 | 1313241.12 | 1215963.9716 | -590436.0484 | -97277.1484 | -257904.1477

## Resource Grid
Resource Allocation Grid
Weekly hours and cost grid adapted from the attached Gantt template: rows are WBS tasks; columns are reporting weeks; totals are live formulas from actual-cost facts.
WBS ID | Activity | Resource / Role | Measure | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Total | BAC | Actual @ Status | Remaining BAC | CPI | RAG | Template source | Notes
WBS-01 | Project Management | Labor | Hours | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 18000 | 9600 | 8400 | 0.9375 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-01 | Project Management | Labor | Cost | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 18000 | 9600 | 8400 | 0.9375 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-02 | Site Survey & Mobilization | Labor | Hours | 3.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.95 | 8500 | 8700 | -200 | 0.97701 | Amber | 8.1.2 Gantt template from garden office | Hours row
WBS-02 | Site Survey & Mobilization | Labor | Cost | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8700 | 8500 | 8700 | -200 | 0.97701 | Amber | 8.1.2 Gantt template from garden office | Cost row
WBS-03 | Design & Engineering | Labor | Hours | 2.5 | 2.5 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6 | 19200 | 18195.04 | 1004.96 | 1.0552 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-03 | Design & Engineering | Labor | Cost | 5995.04 | 6000 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18195.04 | 19200 | 18195.04 | 1004.96 | 1.0552 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-04 | Procurement - Materials | Material | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 41300 | 700 | 1.0169 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-04 | Procurement - Materials | Material | Cost | 0 | 10500 | 10200 | 10200 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41300 | 42000 | 41300 | 700 | 1.0169 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-05 | Demolition & Prep | Labor | Hours | 0 | 2.05 | 2.1 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.05 | 13200 | 13408.16 | -208.16 | 0.98448 | Amber | 8.1.2 Gantt template from garden office | Hours row
WBS-05 | Demolition & Prep | Labor | Cost | 0 | 4554.08 | 4654.08 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13408.16 | 13200 | 13408.16 | -208.16 | 0.98448 | Amber | 8.1.2 Gantt template from garden office | Cost row
WBS-06 | Electrical Rough-In | Labor | Hours | 0 | 0 | 0 | 3.45 | 3.4 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 10.1 | 26000 | 26206.24 | -206.24 | 0.69449 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-06 | Electrical Rough-In | Labor | Cost | 0 | 0 | 0 | 8906.24 | 8800 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 26206.24 | 26000 | 26206.24 | -206.24 | 0.69449 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-07 | HVAC Installation | Subcontractor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 17476.8 | 18523.2 | 0.82395 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-07 | HVAC Installation | Subcontractor | Cost | 0 | 0 | 0 | 0 | 8676.8 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 17476.8 | 36000 | 17476.8 | 18523.2 | 0.82395 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-08 | Partitions & Drywall | Subcontractor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 7099.2 | 20900.8 | 0.98152 | Amber | 8.1.2 Gantt template from garden office | Hours row
WBS-08 | Partitions & Drywall | Subcontractor | Cost | 0 | 0 | 0 | 0 | 0 | 7099.2 | 0 | 0 | 0 | 0 | 0 | 0 | 7099.2 | 28000 | 7099.2 | 20900.8 | 0.98152 | Amber | 8.1.2 Gantt template from garden office | Cost row
WBS-09 | Flooring | Material | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35750 | 0 | 35750 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-09 | Flooring | Material | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35750 | 0 | 35750 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-10 | Fixtures & Furniture | Material | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-10 | Fixtures & Furniture | Material | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-11 | Testing / Commissioning | Labor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 8400 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-11 | Testing / Commissioning | Labor | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 8400 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-12 | Handover & Closeout | Labor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-12 | Handover & Closeout | Labor | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
Gantt of Gantts / monthly workload summary | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Total | Source | Interpretation
Planned PV | 87066.67 | 133166.67 | 48416.66 | 0 | 0 | 0 | 0 | 0 | 268650 | 8.1.2 Gantt of Gantts template | Monthly portfolio-style total from current project PV
Actual Cost | 86509.44 | 55476 | 0 | 0 | 0 | 0 | 0 | 0 | 141985.44 | 8.1.2 Gantt of Gantts template | Monthly portfolio-style total from actual costs
Active WBS count | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 8.1.2 Gantt of Gantts template | Simple monthly activity indicator

## Dim_Project
Project_ID | Project_Name | Start_Date | End_Date | BAC | Sector
P101 | Office Fit-Out | 2026-05-04 | 2026-07-26 | 268650 | Corporate Real Estate

## Dim_WBS
WBS_ID | WBS_Code | Activity_Name | Type | Total_Budget
WBS-01 | 1 | Project Management | Labor | 18000
WBS-02 | 2 | Site Survey & Mobilization | Labor | 8500
WBS-03 | 3 | Design & Engineering | Labor | 19200
WBS-04 | 4 | Procurement - Materials | Material | 42000
WBS-05 | 5 | Demolition & Prep | Labor | 13200
WBS-06 | 6 | Electrical Rough-In | Labor | 26000
WBS-07 | 7 | HVAC Installation | Subcontractor | 36000
WBS-08 | 8 | Partitions & Drywall | Subcontractor | 28000
WBS-09 | 9 | Flooring | Material | 35750
WBS-10 | 10 | Fixtures & Furniture | Material | 30000
WBS-11 | 11 | Testing / Commissioning | Labor | 8400
WBS-12 | 12 | Handover & Closeout | Labor | 3600

## Dim_Resource
Resource_ID | Resource_Name | Role | Hourly_Rate
R01 | Project Manager | Management | 1500
R02 | Lead Engineer | Engineering | 2400
R03 | Electrician | Trades | 2600
R04 | Demolition Crew | Labor | 2200
R05 | Testing Engineer | QA | 2100
R06 | Closeout Specialist | QA | 1800
R07 | Materials Vendor | Vendor | 0
R08 | HVAC Contractor | Contractor | 0
R09 | Drywall Contractor | Contractor | 0
R10 | Flooring Supplier | Vendor | 0
R11 | Furniture Supplier | Vendor | 0

## Dim_Calendar
Date | Year | Month | Month_Name | Quarter | Week_Number | Is_Weekday
2026-05-04 | 2026 | 5 | May | 2 | 1 | 1
2026-05-05 | 2026 | 5 | May | 2 | 1 | 1
2026-05-06 | 2026 | 5 | May | 2 | 1 | 1
2026-05-07 | 2026 | 5 | May | 2 | 1 | 1
2026-05-08 | 2026 | 5 | May | 2 | 1 | 1
2026-05-09 | 2026 | 5 | May | 2 | 1 | 0
2026-05-10 | 2026 | 5 | May | 2 | 1 | 0
2026-05-11 | 2026 | 5 | May | 2 | 2 | 1
2026-05-12 | 2026 | 5 | May | 2 | 2 | 1
2026-05-13 | 2026 | 5 | May | 2 | 2 | 1
2026-05-14 | 2026 | 5 | May | 2 | 2 | 1
2026-05-15 | 2026 | 5 | May | 2 | 2 | 1
2026-05-16 | 2026 | 5 | May | 2 | 2 | 0
2026-05-17 | 2026 | 5 | May | 2 | 2 | 0
2026-05-18 | 2026 | 5 | May | 2 | 3 | 1
2026-05-19 | 2026 | 5 | May | 2 | 3 | 1
2026-05-20 | 2026 | 5 | May | 2 | 3 | 1
2026-05-21 | 2026 | 5 | May | 2 | 3 | 1
2026-05-22 | 2026 | 5 | May | 2 | 3 | 1
2026-05-23 | 2026 | 5 | May | 2 | 3 | 0
2026-05-24 | 2026 | 5 | May | 2 | 3 | 0
2026-05-25 | 2026 | 5 | May | 2 | 4 | 1
2026-05-26 | 2026 | 5 | May | 2 | 4 | 1
2026-05-27 | 2026 | 5 | May | 2 | 4 | 1
2026-05-28 | 2026 | 5 | May | 2 | 4 | 1
2026-05-29 | 2026 | 5 | May | 2 | 4 | 1
2026-05-30 | 2026 | 5 | May | 2 | 4 | 0
2026-05-31 | 2026 | 5 | May | 2 | 4 | 0
2026-06-01 | 2026 | 6 | June | 2 | 5 | 1
2026-06-02 | 2026 | 6 | June | 2 | 5 | 1
2026-06-03 | 2026 | 6 | June | 2 | 5 | 1
2026-06-04 | 2026 | 6 | June | 2 | 5 | 1
2026-06-05 | 2026 | 6 | June | 2 | 5 | 1
2026-06-06 | 2026 | 6 | June | 2 | 5 | 0
2026-06-07 | 2026 | 6 | June | 2 | 5 | 0
2026-06-08 | 2026 | 6 | June | 2 | 6 | 1
2026-06-09 | 2026 | 6 | June | 2 | 6 | 1
2026-06-10 | 2026 | 6 | June | 2 | 6 | 1
2026-06-11 | 2026 | 6 | June | 2 | 6 | 1
2026-06-12 | 2026 | 6 | June | 2 | 6 | 1
2026-06-13 | 2026 | 6 | June | 2 | 6 | 0
2026-06-14 | 2026 | 6 | June | 2 | 6 | 0
2026-06-15 | 2026 | 6 | June | 2 | 7 | 1
2026-06-16 | 2026 | 6 | June | 2 | 7 | 1
2026-06-17 | 2026 | 6 | June | 2 | 7 | 1
2026-06-18 | 2026 | 6 | June | 2 | 7 | 1
2026-06-19 | 2026 | 6 | June | 2 | 7 | 1
2026-06-20 | 2026 | 6 | June | 2 | 7 | 0
2026-06-21 | 2026 | 6 | June | 2 | 7 | 0
2026-06-22 | 2026 | 6 | June | 2 | 8 | 1
2026-06-23 | 2026 | 6 | June | 2 | 8 | 1
2026-06-24 | 2026 | 6 | June | 2 | 8 | 1
2026-06-25 | 2026 | 6 | June | 2 | 8 | 1
2026-06-26 | 2026 | 6 | June | 2 | 8 | 1
2026-06-27 | 2026 | 6 | June | 2 | 8 | 0
2026-06-28 | 2026 | 6 | June | 2 | 8 | 0
2026-06-29 | 2026 | 6 | June | 2 | 9 | 1
2026-06-30 | 2026 | 6 | June | 2 | 9 | 1
2026-07-01 | 2026 | 7 | July | 3 | 9 | 1
2026-07-02 | 2026 | 7 | July | 3 | 9 | 1
2026-07-03 | 2026 | 7 | July | 3 | 9 | 1
2026-07-04 | 2026 | 7 | July | 3 | 9 | 0
2026-07-05 | 2026 | 7 | July | 3 | 9 | 0
2026-07-06 | 2026 | 7 | July | 3 | 10 | 1
2026-07-07 | 2026 | 7 | July | 3 | 10 | 1
2026-07-08 | 2026 | 7 | July | 3 | 10 | 1
2026-07-09 | 2026 | 7 | July | 3 | 10 | 1
2026-07-10 | 2026 | 7 | July | 3 | 10 | 1
2026-07-11 | 2026 | 7 | July | 3 | 10 | 0
2026-07-12 | 2026 | 7 | July | 3 | 10 | 0
2026-07-13 | 2026 | 7 | July | 3 | 11 | 1
2026-07-14 | 2026 | 7 | July | 3 | 11 | 1
2026-07-15 | 2026 | 7 | July | 3 | 11 | 1
2026-07-16 | 2026 | 7 | July | 3 | 11 | 1
2026-07-17 | 2026 | 7 | July | 3 | 11 | 1
2026-07-18 | 2026 | 7 | July | 3 | 11 | 0
2026-07-19 | 2026 | 7 | July | 3 | 11 | 0
2026-07-20 | 2026 | 7 | July | 3 | 12 | 1
2026-07-21 | 2026 | 7 | July | 3 | 12 | 1
2026-07-22 | 2026 | 7 | July | 3 | 12 | 1
2026-07-23 | 2026 | 7 | July | 3 | 12 | 1
2026-07-24 | 2026 | 7 | July | 3 | 12 | 1
2026-07-25 | 2026 | 7 | July | 3 | 12 | 0
2026-07-26 | 2026 | 7 | July | 3 | 12 | 0

## Fact_Baseline_PV
Date | WBS_ID | Planned_Value
2026-05-04 | WBS-01 | 1500
2026-05-11 | WBS-01 | 1500
2026-05-18 | WBS-01 | 1500
2026-05-25 | WBS-01 | 1500
2026-06-01 | WBS-01 | 1500
2026-06-08 | WBS-01 | 1500
2026-06-15 | WBS-01 | 1500
2026-06-22 | WBS-01 | 1500
2026-06-29 | WBS-01 | 1500
2026-07-06 | WBS-01 | 1500
2026-07-13 | WBS-01 | 1500
2026-07-20 | WBS-01 | 1500
2026-05-04 | WBS-02 | 8500
2026-05-04 | WBS-03 | 6400
2026-05-11 | WBS-03 | 6400
2026-05-18 | WBS-03 | 6400
2026-05-11 | WBS-04 | 10500
2026-05-18 | WBS-04 | 10500
2026-05-25 | WBS-04 | 10500
2026-06-01 | WBS-04 | 10500
2026-05-11 | WBS-05 | 4400
2026-05-18 | WBS-05 | 4400
2026-05-25 | WBS-05 | 4400
2026-05-25 | WBS-06 | 8666.67
2026-06-01 | WBS-06 | 8666.67
2026-06-08 | WBS-06 | 8666.66
2026-06-01 | WBS-07 | 9000
2026-06-08 | WBS-07 | 9000
2026-06-15 | WBS-07 | 9000
2026-06-22 | WBS-07 | 9000
2026-06-08 | WBS-08 | 7000
2026-06-15 | WBS-08 | 7000
2026-06-22 | WBS-08 | 7000
2026-06-29 | WBS-08 | 7000
2026-06-22 | WBS-09 | 11916.67
2026-06-29 | WBS-09 | 11916.67
2026-07-06 | WBS-09 | 11916.66
2026-06-29 | WBS-10 | 10000
2026-07-06 | WBS-10 | 10000
2026-07-13 | WBS-10 | 10000
2026-07-13 | WBS-11 | 4200
2026-07-20 | WBS-11 | 4200
2026-07-20 | WBS-12 | 3600

## Fact_Actual_Costs
Date | WBS_ID | Resource_ID | Actual_Cost | Hours_Worked
2026-05-04 | WBS-01 | R01 | 320 | 0.21
2026-05-05 | WBS-01 | R01 | 320 | 0.21
2026-05-06 | WBS-01 | R01 | 320 | 0.21
2026-05-07 | WBS-01 | R01 | 320 | 0.21
2026-05-08 | WBS-01 | R01 | 320 | 0.21
2026-05-04 | WBS-02 | R04 | 1740 | 0.79
2026-05-05 | WBS-02 | R04 | 1740 | 0.79
2026-05-06 | WBS-02 | R04 | 1740 | 0.79
2026-05-07 | WBS-02 | R04 | 1740 | 0.79
2026-05-08 | WBS-02 | R04 | 1740 | 0.79
2026-05-04 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-05 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-06 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-07 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-08 | WBS-03 | R02 | 1199 | 0.5
2026-05-11 | WBS-01 | R01 | 320 | 0.21
2026-05-12 | WBS-01 | R01 | 320 | 0.21
2026-05-13 | WBS-01 | R01 | 320 | 0.21
2026-05-14 | WBS-01 | R01 | 320 | 0.21
2026-05-15 | WBS-01 | R01 | 320 | 0.21
2026-05-11 | WBS-03 | R02 | 1200 | 0.5
2026-05-12 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-03 | R02 | 1200 | 0.5
2026-05-14 | WBS-03 | R02 | 1200 | 0.5
2026-05-15 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-04 | R07 | 10500 | 0
2026-05-11 | WBS-05 | R04 | 910.82 | 0.41
2026-05-12 | WBS-05 | R04 | 910.82 | 0.41
2026-05-13 | WBS-05 | R04 | 910.82 | 0.41
2026-05-14 | WBS-05 | R04 | 910.82 | 0.41
2026-05-15 | WBS-05 | R04 | 910.8 | 0.41
2026-05-18 | WBS-01 | R01 | 320 | 0.21
2026-05-19 | WBS-01 | R01 | 320 | 0.21
2026-05-20 | WBS-01 | R01 | 320 | 0.21
2026-05-21 | WBS-01 | R01 | 320 | 0.21
2026-05-22 | WBS-01 | R01 | 320 | 0.21
2026-05-18 | WBS-03 | R02 | 1240 | 0.52
2026-05-19 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-03 | R02 | 1240 | 0.52
2026-05-21 | WBS-03 | R02 | 1240 | 0.52
2026-05-22 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-04 | R07 | 10200 | 0
2026-05-18 | WBS-05 | R04 | 930.82 | 0.42
2026-05-19 | WBS-05 | R04 | 930.82 | 0.42
2026-05-20 | WBS-05 | R04 | 930.82 | 0.42
2026-05-21 | WBS-05 | R04 | 930.82 | 0.42
2026-05-22 | WBS-05 | R04 | 930.8 | 0.42
2026-05-25 | WBS-01 | R01 | 320 | 0.21
2026-05-26 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-01 | R01 | 320 | 0.21
2026-05-28 | WBS-01 | R01 | 320 | 0.21
2026-05-29 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-04 | R07 | 10200 | 0
2026-05-25 | WBS-05 | R04 | 840 | 0.38
2026-05-26 | WBS-05 | R04 | 840 | 0.38
2026-05-27 | WBS-05 | R04 | 840 | 0.38
2026-05-28 | WBS-05 | R04 | 840 | 0.38
2026-05-29 | WBS-05 | R04 | 840 | 0.38
2026-05-25 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-26 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-27 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-28 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-29 | WBS-06 | R03 | 1781.24 | 0.69
2026-06-01 | WBS-01 | R01 | 320 | 0.21
2026-06-02 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-01 | R01 | 320 | 0.21
2026-06-04 | WBS-01 | R01 | 320 | 0.21
2026-06-05 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-04 | R07 | 10400 | 0
2026-06-01 | WBS-06 | R03 | 1760 | 0.68
2026-06-02 | WBS-06 | R03 | 1760 | 0.68
2026-06-03 | WBS-06 | R03 | 1760 | 0.68
2026-06-04 | WBS-06 | R03 | 1760 | 0.68
2026-06-05 | WBS-06 | R03 | 1760 | 0.68
2026-06-01 | WBS-07 | R08 | 1735.36 | 0
2026-06-02 | WBS-07 | R08 | 1735.36 | 0
2026-06-03 | WBS-07 | R08 | 1735.36 | 0
2026-06-04 | WBS-07 | R08 | 1735.36 | 0
2026-06-05 | WBS-07 | R08 | 1735.36 | 0
2026-06-08 | WBS-01 | R01 | 320 | 0.21
2026-06-09 | WBS-01 | R01 | 320 | 0.21
2026-06-10 | WBS-01 | R01 | 320 | 0.21
2026-06-11 | WBS-01 | R01 | 320 | 0.21
2026-06-12 | WBS-01 | R01 | 320 | 0.21
2026-06-08 | WBS-06 | R03 | 1700 | 0.65
2026-06-09 | WBS-06 | R03 | 1700 | 0.65
2026-06-10 | WBS-06 | R03 | 1700 | 0.65
2026-06-11 | WBS-06 | R03 | 1700 | 0.65
2026-06-12 | WBS-06 | R03 | 1700 | 0.65
2026-06-08 | WBS-07 | R08 | 1760 | 0
2026-06-09 | WBS-07 | R08 | 1760 | 0
2026-06-10 | WBS-07 | R08 | 1760 | 0
2026-06-11 | WBS-07 | R08 | 1760 | 0
2026-06-12 | WBS-07 | R08 | 1760 | 0
2026-06-08 | WBS-08 | R09 | 1419.84 | 0
2026-06-09 | WBS-08 | R09 | 1419.84 | 0
2026-06-10 | WBS-08 | R09 | 1419.84 | 0
2026-06-11 | WBS-08 | R09 | 1419.84 | 0
2026-06-12 | WBS-08 | R09 | 1419.84 | 0

## Fact_Physical_Progress
Date | WBS_ID | Physical_Progress_Pct
2026-05-08 | WBS-01 | 8.333%
2026-05-08 | WBS-02 | 100%
2026-05-08 | WBS-03 | 26.5%
2026-05-15 | WBS-01 | 16.67%
2026-05-15 | WBS-02 | 100%
2026-05-15 | WBS-03 | 60%
2026-05-15 | WBS-04 | 20%
2026-05-15 | WBS-05 | 35.18%
2026-05-22 | WBS-01 | 25%
2026-05-22 | WBS-02 | 100%
2026-05-22 | WBS-03 | 100%
2026-05-22 | WBS-04 | 45%
2026-05-22 | WBS-05 | 45%
2026-05-29 | WBS-01 | 33.33%
2026-05-29 | WBS-02 | 100%
2026-05-29 | WBS-03 | 100%
2026-05-29 | WBS-04 | 70%
2026-05-29 | WBS-05 | 85%
2026-05-29 | WBS-06 | 22.24%
2026-06-05 | WBS-01 | 41.67%
2026-06-05 | WBS-02 | 100%
2026-06-05 | WBS-03 | 100%
2026-06-05 | WBS-04 | 100%
2026-06-05 | WBS-05 | 100%
2026-06-05 | WBS-06 | 50%
2026-06-05 | WBS-07 | 11.1%
2026-06-12 | WBS-01 | 50%
2026-06-12 | WBS-02 | 100%
2026-06-12 | WBS-03 | 100%
2026-06-12 | WBS-04 | 100%
2026-06-12 | WBS-05 | 100%
2026-06-12 | WBS-06 | 70%
2026-06-12 | WBS-07 | 40%
2026-06-12 | WBS-08 | 24.89%

## EVM
EVM Reporting
Weekly earned value reporting table using the guideline formulas: PV, AC, EV, SV, CV, SPI, CPI, BAC, EAC, ETC, and VAC.
Week | Week Date | Cum PV | Cum AC | Cum EV | SV | CV | SPI | CPI | BAC | EAC | ETC | VAC | Status
1 | 2026-05-08 | 16400 | 16295.04 | 15087.994 | -1312.006 | -1207.046 | 0.92 | 0.92593 | 268650 | 290142.1154 | 273847.0754 | -21492.1154 | Red
2 | 2026-05-15 | 39200 | 38949.12 | 36064.0036 | -3135.9964 | -2885.1164 | 0.92 | 0.92593 | 268650 | 290141.971 | 251192.851 | -21491.971 | Red
3 | 2026-05-22 | 62000 | 61603.2 | 57040 | -4960 | -4563.2 | 0.92 | 0.92593 | 268650 | 290142 | 228538.8 | -21492 | Red
4 | 2026-05-29 | 87066.67 | 86509.44 | 80101.328 | -6965.342 | -6408.112 | 0.92 | 0.92593 | 268650 | 290142.0193 | 203632.5793 | -21492.0193 | Red
5 | 2026-06-05 | 116733.34 | 115986.24 | 107394.674 | -9338.666 | -8591.566 | 0.92 | 0.92593 | 268650 | 290141.9802 | 174155.7402 | -21491.9802 | Red
6 | 2026-06-12 | 142900 | 141985.44 | 131467.996 | -11432.004 | -10517.444 | 0.92 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
7 | 2026-06-19 | 160400 | 141985.44 | 131467.996 | -28932.004 | -10517.444 | 0.81963 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
8 | 2026-06-26 | 189816.67 | 141985.44 | 131467.996 | -58348.674 | -10517.444 | 0.69261 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
9 | 2026-07-03 | 220233.34 | 141985.44 | 131467.996 | -88765.344 | -10517.444 | 0.59695 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
10 | 2026-07-10 | 243650 | 141985.44 | 131467.996 | -112182.004 | -10517.444 | 0.53958 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
11 | 2026-07-17 | 259350 | 141985.44 | 131467.996 | -127882.004 | -10517.444 | 0.50691 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
12 | 2026-07-24 | 268650 | 141985.44 | 131467.996 | -137182.004 | -10517.444 | 0.48937 | 0.92593 | 268650 | 290142.0088 | 148156.5688 | -21492.0088 | Red
Formula | Workbook implementation | Guideline meaning | Current status-date value | Check | Source | Column1 | Status tie-out | Dashboard value | Task Plan value | Variance | Check2 | Source3
SV = EV - PV | #N/A | Schedule variance at status date | #N/A | Live | PM-EVM.md lines 145-150 |  | PV | 220233.34 | 220233.34 | 0 | OK | Task Plan!I17
CV = EV - AC | #N/A | Cost variance at status date | #N/A | Live | PM-EVM.md lines 145-150 |  | AC | 141985.44 | 141985.44 | 0 | OK | Task Plan!J17
SPI = EV / PV | #N/A | Schedule efficiency | #N/A | Live | PM-EVM.md lines 145-150 |  | EV | 131467.996 | 131467.996 | 0 | OK | Task Plan!L17
CPI = EV / AC | #N/A | Cost efficiency | #N/A | Live | PM-EVM.md lines 145-150 |  | SPI | 0.59695 | 0.59695 | 0 | OK | Task Plan!O17
EAC = BAC / CPI | #N/A | Forecast final cost | #N/A | Live | PM-EVM.md lines 203-214 |  | CPI | 0.92593 | 0.92593 | 0 | OK | Task Plan!P17
VAC = BAC - EAC | #N/A | Expected budget variance at completion | #N/A | Live | PM-EVM.md lines 203-214 |  | VAC | -21492.0088 | -21492.0088 | 0 | OK | Task Plan!S17

## EVM Charts
Project Schedule & EVM Curves | [7 empty] | Project Start | 2026-05-04
Gantt schedule is derived from baseline PV dates by WBS; the S-curve uses cumulative PV, actual cost, and earned value as of each weekly status date. | [7 empty] | Project Finish | 2026-07-26
[8 empty] | Status Date | 2026-06-30
WBS ID | Activity | Start | Finish | Start Offset | Duration Days | Progress % | RAG
WBS-01 | Project Management | 2026-05-04 | 2026-07-26 | 0 | 84 | 50% | Amber | RAG Legend | Rule | Used in charts
WBS-02 | Site Survey & Mobilization | 2026-05-04 | 2026-05-10 | 0 | 7 | 100% | Green | Green | Good / baseline target | Gantt good bars; PV line
WBS-03 | Design & Engineering | 2026-05-04 | 2026-05-24 | 0 | 21 | 100% | Green | Amber | Watch / earned progress | Gantt watch bars; EV line
WBS-04 | Procurement - Materials | 2026-05-11 | 2026-06-07 | 7 | 28 | 100% | Green | Red | Action / cost exposure | Gantt action bars; AC line
WBS-05 | Demolition & Prep | 2026-05-11 | 2026-05-31 | 7 | 21 | 100% | Green | White | Hidden helper | Gantt start-offset series
WBS-06 | Electrical Rough-In | 2026-05-25 | 2026-06-14 | 21 | 21 | 70% | Amber | Red dotted | Status date | Vertical marker at 2026-06-30
WBS-07 | HVAC Installation | 2026-06-01 | 2026-06-28 | 28 | 28 | 40% | Red
WBS-08 | Partitions & Drywall | 2026-06-08 | 2026-07-05 | 35 | 28 | 24.89% | Red
WBS-09 | Flooring | 2026-06-22 | 2026-07-12 | 49 | 21 | 0% | Red
WBS-10 | Fixtures & Furniture | 2026-06-29 | 2026-07-19 | 56 | 21 | 0% | Red
WBS-11 | Testing / Commissioning | 2026-07-13 | 2026-07-26 | 70 | 14 | 0% | Red
WBS-12 | Handover & Closeout | 2026-07-20 | 2026-07-26 | 77 | 7 | 0% | Red
Week | Week Date | Cum PV | Cum AC | Cum EV | CPI | SPI
1 | 2026-05-08 | 16400 | 16295.04 | 15087.994 | 0.92593 | 0.92
2 | 2026-05-15 | 39200 | 38949.12 | 36064.0036 | 0.92593 | 0.92
3 | 2026-05-22 | 62000 | 61603.2 | 57040 | 0.92593 | 0.92
4 | 2026-05-29 | 87066.67 | 86509.44 | 80101.328 | 0.92593 | 0.92
5 | 2026-06-05 | 116733.34 | 115986.24 | 107394.674 | 0.92593 | 0.92
6 | 2026-06-12 | 142900 | 141985.44 | 131467.996 | 0.92593 | 0.92
7 | 2026-06-19 | 160400 | 141985.44 | 131467.996 | 0.92593 | 0.81963
8 | 2026-06-26 | 189816.67 | 141985.44 | 131467.996 | 0.92593 | 0.69261
9 | 2026-07-03 | 220233.34 | 141985.44 | 131467.996 | 0.92593 | 0.59695
10 | 2026-07-10 | 243650 | 141985.44 | 131467.996 | 0.92593 | 0.53958
11 | 2026-07-17 | 259350 | 141985.44 | 131467.996 | 0.92593 | 0.50691
12 | 2026-07-24 | 268650 | 141985.44 | 131467.996 | 0.92593 | 0.48937
Formulas:
Start = MINIFS(Fact_Baseline_PV!$A:$A,Fact_Baseline_PV!$B:$B,[WBS ID])
Finish = MAXIFS(Fact_Baseline_PV!$A:$A,Fact_Baseline_PV!$B:$B,[WBS ID])+6

## Simple Gantt Model
Gantt Model — Office Fit-Out
Adapted from the attached Garden Office Gantt template. This sheet is populated from the current workbook WBS, baseline PV, actual cost, actual hours, progress, CPI/RAG status, and status date.
Project controls and model mapping
Project | Office Fit-Out | Project Start | 2026-05-04 | Project End | 2026-07-26 | Status Date | 2026-06-30 | BAC | 268,650.00 NOK | Source | Current workbook
Template element | Implemented as | Source table | Meaning | Classification
My hours | Weekly hours grid | Fact_Actual_Costs[Hours_Worked] | Actual hours by WBS and week; o = planned week with no actual hours yet. | Control
Total costs | Weekly cost grid | Fact_Actual_Costs[Actual_Cost] | Actual cost by WBS and week; o = planned week with no actual cost yet. | Control
My hours — current project actual hours by WBS / week
Task | Role / Type | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | Total
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Management | Labor | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | o | o | o | o | o | o | 6.3
Site Survey & Mobilization | Labor | 1: 3.95 | 3.95
Design & Engineering | Labor | 1: 2.5; 2: 2.5; 3: 2.6 | 7.6
Procurement - Materials | Material | [12 empty] | 0 | bar: 2 to 5; 9
Demolition & Prep | Labor | 2: 2.05; 3: 2.1; 4: 1.9 | 6.05
Electrical Rough-In | Labor | 4: 3.45; 5: 3.4; 6: 3.25 | 10.1
HVAC Installation | Subcontractor | [12 empty] | 0 | bar: 5 to 9
Partitions & Drywall | Subcontractor | [12 empty] | 0 | bar: 6 to 9
Flooring | Material | [12 empty] | 0 | bar: 8 to 10
Fixtures & Furniture | Material | [12 empty] | 0 | bar: 9 to 11
Testing / Commissioning | Labor | [12 empty] | 0 | bar: 9; 11 to 12
Handover & Closeout | Labor | [12 empty] | 0 | bar: 9; 12
my total hours |  | 7.5 | 5.6 | 5.75 | 6.4 | 4.45 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Total costs — current project actual costs by WBS / week
Task | Who / Type | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | Total
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Management | Labor | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | o | o | o | o | o | o | 9600
Site Survey & Mobilization | Labor | 1: 8700 | 8700
Design & Engineering | Labor | 1: 5995.04; 2: 6000; 3: 6200 | 18195.04
Procurement - Materials | Material | 2: 10500; 3: 10200; 4: 10200; 5: 10400 | 41300
Demolition & Prep | Labor | 2: 4554.08; 3: 4654.08; 4: 4200 | 13408.16
Electrical Rough-In | Labor | 4: 8906.24; 5: 8800; 6: 8500 | 26206.24
HVAC Installation | Subcontractor | 5: 8676.8; 6: 8800; 7: o; 8: o | 17476.8
Partitions & Drywall | Subcontractor | 6: 7099.2; 7: o; 8: o; 9: o | 7099.2
Flooring | Material | [12 empty] | 0 | bar: 8 to 10
Fixtures & Furniture | Material | [12 empty] | 0 | bar: 9 to 11
Testing / Commissioning | Labor | [12 empty] | 0 | bar: 9; 11 to 12
Handover & Closeout | Labor | [12 empty] | 0 | bar: 9; 12
my total costs |  | 16295.04 | 22654.08 | 22654.08 | 24906.24 | 29476.8 | 25999.2 | 0 | 0 | 0 | 0 | 0 | 0 | 141985.44
Task | BAC | PV @ Status | AC @ Status | Progress % | EV @ Status | SV | CV | SPI | CPI | RAG
Project Management | 18000 | 13500 | 9600 | 50% | 9000 | -4500 | -600 | 0.66667 | 0.9375 | Red
Site Survey & Mobilization | 8500 | 8500 | 8700 | 100% | 8500 | 0 | -200 | 1 | 0.97701 | Red
Design & Engineering | 19200 | 19200 | 18195.04 | 100% | 19200 | 0 | 1004.96 | 1 | 1.0552 | Green
Procurement - Materials | 42000 | 42000 | 41300 | 100% | 42000 | 0 | 700 | 1 | 1.0169 | Green
Demolition & Prep | 13200 | 13200 | 13408.16 | 100% | 13200 | 0 | -208.16 | 1 | 0.98448 | Red
Electrical Rough-In | 26000 | 26000 | 26206.24 | 70% | 18200 | -7800 | -8006.24 | 0.7 | 0.69449 | Red
HVAC Installation | 36000 | 36000 | 17476.8 | 40% | 14400 | -21600 | -3076.8 | 0.4 | 0.82395 | Red
Partitions & Drywall | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -21032.004 | -131.204 | 0.24886 | 0.98152 | Red
Flooring | 35750 | 23833.34 | 0 | 0% | 0 | -23833.34 | 0 | 0 | 1 | Red
Fixtures & Furniture | 30000 | 10000 | 0 | 0% | 0 | -10000 | 0 | 0 | 1 | Red
Testing / Commissioning | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | Green
Handover & Closeout | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | Green
Status timeline: 2026-06-30 | bar: 1 to 9
Legend | Meaning | 1: Applied to
Red dotted vertical line | Status date 2026-06-30 | 1: My hours and Total costs grids
Green row | CPI/SPI >= 1.00 and favorable variance | 1: Summary + task totals
Amber row | Near threshold | 1: Summary + task totals
Red row | Behind plan / cost overrun / low index | 1: Summary + task totals

## PERT Diagram
Swimlane PERT Diagram — Office Fit-Out
PERT network grouped into swimlanes by Task Plan type: Labor, Material, and Subcontractor. Status date: 2026-06-30. Node colors use the workbook RAG status.
WBS ID | Activity | Baseline Start | Baseline Finish | Duration | Progress | SPI | CPI | RAG | Inferred predecessor(s) | Visio-style PERT Legend | Column1 | Column2
WBS-01 | Project Management | 2026-05-04 | 2026-07-26 | 84 | 50% | 0.67 | 0.94 | Red | START | Green | On track | CPI/SPI/variance favorable
WBS-02 | Site Survey & Mobilization | 2026-05-04 | 2026-05-10 | 7 | 100% | 1 | 0.98 | Red | START | Amber | Watch | Near threshold
WBS-03 | Design & Engineering | 2026-05-04 | 2026-05-24 | 21 | 100% | 1 | 1.06 | Green | START | Red | Action | Behind plan / overrun
WBS-04 | Procurement - Materials | 2026-05-11 | 2026-06-07 | 28 | 100% | 1 | 1.02 | Green | WBS-02 / WBS-03 | Gray | Start / Finish | Network endpoints
WBS-05 | Demolition & Prep | 2026-05-11 | 2026-05-31 | 21 | 100% | 1 | 0.98 | Red | WBS-02 / WBS-03
WBS-06 | Electrical Rough-In | 2026-05-25 | 2026-06-14 | 21 | 70% | 0.7 | 0.69 | Red | WBS-04 / WBS-05
WBS-07 | HVAC Installation | 2026-06-01 | 2026-06-28 | 28 | 40% | 0.4 | 0.82 | Red | WBS-06
WBS-08 | Partitions & Drywall | 2026-06-08 | 2026-07-05 | 28 | 24.9% | 0.25 | 0.98 | Red | WBS-06
WBS-09 | Flooring | 2026-06-22 | 2026-07-12 | 21 | 0% | 0 | 1 | Red | WBS-07 / WBS-08
WBS-10 | Fixtures & Furniture | 2026-06-29 | 2026-07-19 | 21 | 0% | 0 | 1 | Red | WBS-07 / WBS-08
WBS-11 | Testing / Commissioning | 2026-07-13 | 2026-07-26 | 14 | 0% | 1 | 1 | Green | WBS-09 / WBS-10
WBS-12 | Handover & Closeout | 2026-07-20 | 2026-07-26 | 7 | 0% | 1 | 1 | Green | WBS-11
Swimlane view below: dependencies flow left-to-right; each horizontal lane groups work by Task Plan type.
Labor
Material
Subcontractor
Task-type swimlane PERT network
START
FINISH
WBS-01 Project Management 50% | SPI 0.67 | CPI 0.94
WBS-02 Site Survey 100% | SPI 1.00 | CPI 0.98
WBS-03 Design & Engineering 100% | SPI 1.00 | CPI 1.06
WBS-04 Procurement 100% | SPI 1.00 | CPI 1.02
WBS-05 Demolition & Prep 100% | SPI 1.00 | CPI 0.98
WBS-06 Electrical Rough-In 70% | SPI 0.70 | CPI 0.69
WBS-07 HVAC Installation 40% | SPI 0.40 | CPI 0.82
WBS-08 Partitions & Drywall 25% | SPI 0.25 | CPI 0.98
WBS-09 Flooring 0% | SPI 0.00 | CPI 1.00
WBS-10 Fixtures & Furniture 0% | SPI 0.00 | CPI 1.00
WBS-11 Testing 0% | SPI 1.00 | CPI 1.00
WBS-12 Handover & Closeout 0% | SPI 1.00 | CPI 1.00
Legend
Red
Amber
Green
Dependency assumption: predecessor links follow the baseline sequence already inferred in the original PERT diagram.