## Cover
Office Fit-Out Project Control Workbook
PM-EVM compliant workbook map: setup controls, task plan, Gantt, EVM S-curve, dashboard, source dimensions, and fact tables.
Sheet | Purpose | Tab Color Legend
Setup | Project-level controls: project metadata, status date, reporting period, and RAG thresholds. | Color | Category | Sheets
Task Plan | Integrated WBS/task control table linking baseline dates, BAC, progress, AC, EV, variances, forecasts, and RAG status. |  | Navigation / Reference | Cover, Glossary
EVM | Weekly EVM reporting table with cumulative PV, AC, EV, SV, CV, SPI, CPI, EAC, ETC, and VAC. |  | Method / Governance | Method Roadmap, PID, PM-EVM Compliance, Review
EVM Charts | Baseline Gantt schedule and EVM S-curve generated from the same WBS, budget, progress, and actual-cost data. |  | Controls / Planning | Setup, Task Plan, Task Capture, Resource Grid
EVM Dashboard | Management view with KPI tiles, WBS performance breakdown, trends, and RAG coloring. |  | Management Outputs | EVM Dashboard, EVM, EVM Charts
PM-EVM Compliance | Checklist mapping the workbook to the attached PM-EVM guideline. |  | Dimension Data | Dim_Project, Dim_WBS, Dim_Resource, Dim_Calendar
Dim_* / Fact_* | Star-schema source data used by the live formulas and charts. |  | Fact Data | Fact_Baseline_PV, Fact_Actual_Costs, Fact_Physical_Progress
Glossary | Definitions for the EVM, WBS, Gantt, schedule, cost, RAG, and data-model terms used in the workbook.
Method Roadmap | 12-step project management method mapped to workbook sheets and current project controls. | Input / Control / Output Classification
PID | Project Initiation Document template with business case, scope, controls, risk and financial sections. | Class | Meaning | Sheets
Task Capture | Task-list brainstorming sheet based on the attached list-the-tasks method, linked to current WBS. | Input | Source data or user-entered templates that feed calculations. | Dim_Project, Dim_WBS, Dim_Resource, Dim_Calendar, Fact_Baseline_PV, Fact_Actual_Costs, Fact_Physical_Progress, PID, Task Capture, Review
Resource Grid | Weekly hours/cost resource allocation grid adapted from the attached Gantt template. | Control | Assumptions, governance, validation, methods, and planning logic that manage how inputs are interpreted. | Setup, Method Roadmap, PM-EVM Compliance, Task Plan, Resource Grid
Review | GOOD / BAD / BETTER review template and action log. | Output | Management-facing reports, charts, dashboards, and reference views produced from inputs and controls. | Cover, Glossary, EVM Dashboard, EVM, EVM Charts
Garden Gantt Model | Attached garden-office Gantt template implemented with current project weekly hours and cost data.
PERT Diagram | Visio-style PERT network diagram reflecting the current WBS, schedule, progress and RAG status. | Sheet | Class | Reason
Red Actions | Recommended recovery actions for all current red RAG WBS items and control risks. | Cover | Output | Workbook navigation and summary.
Pivot Summary | High-level PivotTables and descriptive statistics for project cost, schedule, EVM, and RAG performance. | Glossary | Output
|  | Review | Input
|  | Setup | Control
|  | PID | Input
|  | Method Roadmap | Control
|  | PM-EVM Compliance | Control
|  | Task Plan | Control
|  | Task Capture | Input
|  | EVM Dashboard | Output
|  | Resource Grid | Control
|  | Dim_Project | Input
|  | Dim_WBS | Input
|  | Dim_Resource | Input
|  | Dim_Calendar | Input
|  | Fact_Baseline_PV | Input
|  | Fact_Actual_Costs | Input
|  | Fact_Physical_Progress | Input
|  | EVM | Output
|  | EVM Charts | Output

## Slicer Controls
Workbook Slicer Controls
Use this panel to filter the source Excel Tables directly. Slicers are grouped by reporting outputs, source inputs, and governance/control tables.
MANAGEMENT OUTPUTS
SOURCE INPUTS
GOVERNANCE / CONTROL
Slicer name | Source area | Field | Caption
slc_Dashboard_Status | Dashboard | Status | Dashboard: Status
slc_Dashboard_Type | Dashboard | Type | Dashboard: Type
slc_TaskPlan_Status | Task Plan | Status | Task Plan: Status
slc_TaskPlan_Type | Task Plan | Type | Task Plan: Type
slc_TaskPlan_WBSID | Task Plan | WBS ID | Task Plan: WBS ID
slc_EVM_Status | EVM | Status | EVM: Status
slc_EVM_Week | EVM | Week | EVM: Week
slc_PERT_RAG | PERT | RAG | PERT: RAG
slc_Resource_Measure | Resource Grid | Measure | Resource Grid: Measure
slc_Resource_RAG | Resource Grid | RAG | Resource Grid: RAG
slc_Calendar_Month | Calendar | Month | Calendar: Month
slc_Calendar_Week | Calendar | Week | Calendar: Week
slc_DimResource_Role | Resources | Role | Resources: Role
slc_DimWBS_Type | WBS Master | Type | WBS Master: Type
slc_DimWBS_WBSID | WBS Master | WBS ID | WBS Master: WBS ID
slc_ActualCosts_ResourceID | Actual Costs | Resource | Actual Costs: Resource
slc_ActualCosts_WBSID | Actual Costs | WBS ID | Actual Costs: WBS ID
slc_BaselinePV_WBSID | Baseline PV | WBS ID | Baseline PV: WBS ID
slc_Progress_WBSID | Progress | WBS ID | Progress: WBS ID
slc_TaskCapture_Type | Task Capture | Type | Task Capture: Type
slc_Method_Status | Method Roadmap | Status | Method Roadmap: Status
slc_PIDRisk_Owner | PID Risks | Owner | PID Risks: Owner
slc_PIDRisk_RAG | PID Risks | RAG | PID Risks: RAG
slc_Review_Owner | Review Actions | Owner | Review Actions: Owner
slc_Review_RAG | Review Actions | RAG | Review Actions: RAG
slc_Compliance_Status | PM-EVM | Status | PM-EVM: Status
slc_Glossary_Category | Glossary | Category | Glossary: Category
slc_Method_Owner | Method Roadmap | Owner | Method Roadmap: Owner

## Glossary
Project Control Glossary
Definitions for the EVM, WBS, Gantt, schedule, cost, and RAG terms used across this workbook.
Category | Term | Abbrev. | Definition | Workbook reference
Project setup | Project Start |  | Approved start date for the project control baseline. | Setup!B7 / Dim_Project!C2
Project setup | Project End |  | Approved planned end date for the project. | Setup!B8 / Dim_Project!D2
Project setup | Status Date |  | Cut-off date for reported progress, actual costs, and EVM metrics. | Setup!B9 / EVM Dashboard!B4
Scope / WBS | Work Breakdown Structure | WBS | Hierarchical breakdown of project scope into controllable work packages or activities. | Dim_WBS / Task Plan
Scope / WBS | WBS ID |  | Unique identifier used to connect WBS activities to baseline PV, actual costs, and progress facts. | Dim_WBS!A:A
Scope / WBS | Activity / Task |  | A controllable unit of project work with budget, schedule, progress, and cost tracking. | Task Plan!C:C
Schedule | Baseline Start |  | Planned start date for a WBS activity from the approved baseline. | Task Plan!E:E
Schedule | Baseline Finish |  | Planned finish date for a WBS activity from the approved baseline. | Task Plan!F:F
Schedule | Duration Days |  | Calendar-day span between baseline start and finish dates. | Task Plan!G:G
Schedule | Gantt Chart |  | Timeline chart showing planned activity timing and duration by WBS activity. | EVM Charts!Gantt Schedule
Cost / EVM | Budget at Completion | BAC | Approved total budget for the project or WBS activity. | Setup!B11 / Task Plan!H:H
Cost / EVM | Planned Value | PV | Budgeted value of work planned to be complete by a given date. | Task Plan!I:I / EVM!C:C
Cost / EVM | Actual Cost | AC | Actual cost incurred by a given date. | Task Plan!J:J / EVM!D:D
Cost / EVM | Physical Progress | Progress % | Latest reported percent complete for each WBS activity as of the status date. | Task Plan!K:K
Cost / EVM | Earned Value | EV | Budgeted value of the work actually completed; calculated as BAC × progress. | Task Plan!L:L / EVM!E:E
Variance | Schedule Variance | SV | EV minus PV; negative means less work completed than planned. | Task Plan!M:M / EVM!F:F
Variance | Cost Variance | CV | EV minus AC; negative means cost overrun for completed work. | Task Plan!N:N / EVM!G:G
Performance index | Schedule Performance Index | SPI | EV divided by PV; below 1.0 indicates unfavorable schedule efficiency. | Task Plan!O:O / EVM!H:H
Performance index | Cost Performance Index | CPI | EV divided by AC; below 1.0 indicates unfavorable cost efficiency. | Task Plan!P:P / EVM!I:I
Forecast | Estimate at Completion | EAC | Forecast final project or WBS cost, typically BAC divided by CPI. | Task Plan!Q:Q / EVM!K:K
Forecast | Estimate to Complete | ETC | Forecast remaining cost to complete the work; EAC minus AC. | Task Plan!R:R / EVM!L:L
Forecast | Variance at Completion | VAC | Expected budget variance at completion; BAC minus EAC. | Task Plan!S:S / EVM!M:M
Chart | EVM S-Curve |  | Line chart comparing cumulative PV, EV, and AC over time. | EVM Charts!EVM S-Curve
RAG | Green |  | Good condition: on/above plan, favorable variance, or acceptable performance threshold. | Setup!A18:D18
RAG | Amber |  | Watch condition: close to threshold or mid-progress; monitor closely. | Setup!A19:D19
RAG | Red |  | Action condition: negative variance, low progress, CPI/SPI below threshold, or overrun. | Setup!A20:D20
Reporting | Dashboard |  | Management summary view showing KPIs, WBS performance, trend data, and RAG status. | EVM Dashboard!A1:P47
Reporting | Tie-out |  | Validation that dashboard KPIs match the detailed EVM reporting table at the status date. | EVM!H19:M25
Data model | Dimension Table | Dim | Reference table describing projects, WBS, resources, or calendar dates. | Dim_Project / Dim_WBS / Dim_Resource / Dim_Calendar
Data model | Fact Table | Fact | Transaction or event table containing planned values, actual costs, or progress observations. | Fact_Baseline_PV / Fact_Actual_Costs / Fact_Physical_Progress
Workbook classification | Input |  | Source data or user-entered content that feeds project calculations and reports. | Cover!D13:H39
Workbook classification | Control |  | Assumptions, thresholds, validation, governance, and planning logic used to interpret inputs. | Cover!D13:H39
Workbook classification | Output |  | Reports, charts, dashboards, and references produced from the input data and control logic. | Cover!D13:H39

## Review
Project Review & Lessons
Review template from attachment: GOOD / BAD / BETTER plus action log for plan adjustments and lessons learned.
Project Description | Generic Master Project
Project Period | 2026-01-01 to 2026-12-31
Status Date | 2026-06-30
Review Owner | Frank Ellingsen
Review Date | 2026-08-04
GOOD — what went well that others should repeat?
BAD — what mistakes were made or unexpected issues occurred?
BETTER / ACTION LOG | Owner | Due date | Decision required? | RAG | Linked workbook evidence
1 | 2026-01-01 | Action description | Owner | Medium | Open
Review cost efficiency and current EAC forecast | Project Controls |  | Yes | Red | EVM Dashboard!G10 / Task Plan!Q17
Confirm mitigation for red WBS activities in Gantt | Project Manager |  | Yes | Red | EVM Charts!Gantt Schedule
Check future material/subcontractor dependencies | Planner |  | No | Amber | Task Plan / Resource Grid
Capture lessons from completed WBS items | Project Team |  | No | Amber | Task Capture / Review
Review source | 13.1.2 Review Template.pdf

## PID
Project Initiation Document (PID)
PID template from the attached method, prefilled with current workbook metadata where available. Fill yellow cells during project definition.
Project header
Project Name | Generic Master Project
Project Number | PRJ001
Project Risk Level | H/M/L
Prepared by | Frank Ellingsen
Date | 2026-08-04
Persons consulted
Key Driver | Cost / Quality / Time
1. Business Case
Why this project; why now; options considered; what if we do not do it; benefits; payback period.
2.1 In Scope / Included
Work and deliverables included in the project.
2.2 Out of Scope / Excluded
Work explicitly excluded from the project.
2.3 Dependencies
How the project impacts or is impacted by other projects or programmes.
2.4 Constraints
Deadlines, budget limits, resource limitations or other delivery constraints.
2.5 Assumptions
Assumptions currently being used for planning.
3. Key Actions Proposed
Must include a high-level or detailed Gantt chart.
4. Project Controls and Reporting
How progress will be reported, frequency, method and responsibility.
Frequency / timing | How control is reported | Responsibility | Next report date | Status
Project Controls Lead | Role Description | Name | Contact | Approved
Stage end | PID / Review pack | Project Manager |  | Planned
Monthly | Board summary | Project Manager |  | Planned
5. Risk Control
Project risks and containment measures.
Project Risk | Containment Measures | Owner | Due Date | RAG
Risk ID | Risk Description | Probability | Impact | Mitigation Strategy
Cost overrun | Monitor CPI/CV/EAC and review WBS cost drivers. | Project Controls |  | Red
Resource availability | Use weekly Resource Grid to identify conflicts. | Resource Manager |  | Amber
Scope creep | Confirm in/out of scope and change-control route in PID. | Project Manager |  | Amber
Quality issue | Define acceptance criteria and quality checks by task. | Project Manager |  | Amber
Supplier delay | Track procurement/material activities and delivery milestones. | Project Manager |  | Amber
6. Financial Implications
Quarterly/annual financial profile adapted from the PID template; Year 1 is linked to the current baseline planned value.
Financial Implications | Q1 | Q2 | Q3 | Q4 | Total
Cost Category | 0 | 0 | 0 | Comments | Status
Amount Year 2 | 0 | 0 | 0 | 0 | 0
Amount Year 3 | 0 | 0 | 0 | 0 | 0
Amount Year 4 | 0 | 0 | 0 | 0 | 0
Amount Year 5 | 0 | 0 | 0 | 0 | 0

## Method Roadmap
12-Step Project Management Method Roadmap
Course method embedded into the workbook: define, list, sequence, estimate, check, Gantt, resource, risk, monitor progress/cost, adjust, and review.
Step | Method step | Purpose | Workbook implementation | Primary sheet / range | Owner | Status | Source
1 | Define the project | Create the project definition and controls. | PID template added with live project metadata. | PID!A1:H50 | Project Manager | Active | 1.2 12 Step Process / 2.1.2 PID template
2 | List the tasks | Capture all tasks without initially worrying about order, cost, or time. | Task Capture sheet added; WBS imported from current Dim_WBS and grouped by type. | Task Capture!A4:J18 | Project Team | Active | 3.1.5 List the Tasks / 4.1 List of Tasks
3 | Establish task order | Convert brainstormed tasks into planned sequencing. | Task Plan and Gantt use WBS order and baseline dates. | Task Plan!A4:T17 | Planner | Active | 1.2 12 Step Process
4 | Estimate time | Estimate duration by task. | Baseline start, finish, and duration calculated per WBS. | Task Plan!E5:G17 | Planner | Active | 1.2 12 Step Process
5 | Margin check & reality check | Check whether dates, budget, and resource assumptions are feasible. | Status tie-out, EVM checks, and RAG indicators added. | EVM!H19:M25 | Project Controls | Active | 1.2 12 Step Process
6 | Gantt Chart | Show planned timing and status. | Gantt chart with RAG bars and status-date marker exists. | EVM Charts!Gantt Schedule | Project Controls | Active | 8.1.2 Gantt templates
7 | Resource allocation | Map tasks to people/resources and weekly loading. | Resource Grid added with weekly hours and costs by WBS. | Resource Grid!A4:Z35 | Resource Manager | Active | 8.1.2 Gantt template from garden office
8 | Predicting & reducing risk | Identify project risks and containment measures. | PID risk-control register added. | PID!A63:E70 | Project Manager | Template ready | 2.1.2 PID template
9 | Monitoring progress | Track completion against plan. | Progress is linked from Fact_Physical_Progress to Task Plan and dashboard. | Task Plan!K5:K17 | Project Controls | Active | 1.2 12 Step Process
10 | Monitoring cost | Track actual cost and forecast. | EVM reporting monitors AC, CV, CPI, EAC, ETC, VAC. | EVM!A4:N16 | Project Controls | Active | 1.2 12 Step Process
11 | Adjusting the plan | Use EVM and RAG exceptions to trigger decisions. | Decision/action log added to Review. | Review!A20:F28 | Project Board | Template ready | 1.2 12 Step Process
12 | Review & lessons | Capture good, bad, better after delivery. | Review sheet added with GOOD / BAD / BETTER structure. | Review!A4:F17 | Project Team | Template ready | 13.1.2 Review Template

## PM-EVM Compliance
PM-EVM Compliance Checklist
Workbook compliance map against the attached PM-EVM guideline: WBS, Gantt, EVM, dashboard, live formulas, and exception-focused reporting.
Guideline requirement | Workbook implementation | Location | Status | Evidence
Setup controls: project metadata, status date, reporting period, rates/thresholds | Added setup control sheet with live project metadata and thresholds | Setup!A4:D20 | Compliant | PM-EVM.md lines 117-126
Task Plan as integrated WBS/task control view | Added live task table combining WBS, dates, BAC, PV, AC, progress, EV, variances, forecasts and RAG | Task Plan!A4:T17 | Compliant | PM-EVM.md lines 120-125
Gantt display tied to WBS baseline dates | Existing EVM Charts Gantt uses WBS activities, baseline start/finish and duration | EVM Charts!Gantt Schedule | Compliant | PM-EVM.md lines 122-125
EVM by reporting period with PV, EV, AC, SV, CV, SPI, CPI, BAC, EAC, ETC, VAC | Added EVM reporting table with weekly live formulas | EVM!A4:N16 | Compliant | PM-EVM.md lines 123-124
S-curve shows cumulative PV, EV, and AC over time | Existing EVM S-curve chart is sourced from weekly cumulative helper table | EVM Charts!EVM S-Curve | Compliant | PM-EVM.md lines 50-54
Dashboard summarizes management KPIs and top WBS exceptions | Existing dashboard has KPI tiles, WBS table, RAG, variance/status fields | EVM Dashboard!A1:P47 | Compliant | PM-EVM.md lines 781-785
Exception-focused reporting with RAG / traffic-light indicators | RAG rules applied across performance indices, progress, variances, and status cells | EVM Dashboard, Task Plan, EVM | Compliant | PM-EVM.md lines 781-785
Consistent WBS codes, budgets, dates, and actuals across views | Task Plan, EVM, Gantt and dashboard all reference Dim_WBS and fact tables | Dim_WBS / Fact_* | Compliant | PM-EVM.md lines 270-274
Validate formulas and totals | Added formula validation and status-date tie-out to dashboard KPIs | EVM!H19:M25 | Compliant | PM-EVM.md lines 783-785

## Setup
Setup Controls
Single place to review project metadata, status date, reporting period, and RAG thresholds used by the control workbook.
Control | Value
Project ID | PRJ001
Project Name | Generic Master Project
Project Start | 2026-01-01
Project End | 2026-12-31
Status Date | 2026-06-30
Reporting Period | Weekly
Budget at Completion (BAC) | 267150
CPI/SPI Red Threshold | 0.95
CPI/SPI Green Threshold | 1
Progress Amber Threshold | 0.5
Progress Green Threshold | 0.8
RAG | Metric | Rule | Interpretation
Green | CPI/SPI | >= 1.00 | On or above plan
Amber | CPI/SPI | 0.95 to < 1.00 | Near threshold / watch
Red | CPI/SPI | < 0.95 | Action required

## Task Plan
Task Plan
Integrated WBS control table: one live task-level view for scope, schedule, budget, progress, actuals, forecasts, and RAG status.
WBS ID | WBS Code | Task / Activity | Type | Baseline Start | Baseline Finish | Duration Days | BAC (NOK) | PV @ Status | AC @ Status | Progress % | EV @ Status | SV | CV | SPI | CPI | EAC | ETC | VAC | Status
WBS-01 | 1 | Project Management | Labor | 2026-05-11 | 2026-07-26 | 77 | 16500 | 12000 | 9280 | 50% | 8250 | -3750 | -1030 | 0.6875 | 0.88901 | 18560 | 9280 | -2060 | Red
WBS-02 | 2 | Site Survey & Mobilization | Labor | 2026-05-04 | 2026-05-10 | 7 | 8500 | 8500 | 8700 | 100% | 8500 | 0 | -200 | 1 | 0.97701 | 8700 | 0 | -200 | Red
WBS-03 | 3 | Design & Engineering | Labor | 2026-05-04 | 2026-05-24 | 21 | 19200 | 19200 | 18195.04 | 100% | 19200 | 0 | 1004.96 | 1 | 1.0552 | 18195.04 | 0 | 1004.96 | Green
WBS-04 | 4 | Procurement - Materials | Material | 2026-05-11 | 2026-06-07 | 28 | 42000 | 42000 | 41300 | 100% | 42000 | 0 | 700 | 1 | 1.0169 | 41300 | 0 | 700 | Green
WBS-05 | 5 | Demolition & Prep | Labor | 2026-05-11 | 2026-05-31 | 21 | 13200 | 13200 | 13408.16 | 100% | 13200 | 0 | -208.16 | 1 | 0.98448 | 13408.16 | 0 | -208.16 | Red
WBS-06 | 6 | Electrical Rough-In | Labor | 2026-05-25 | 2026-06-14 | 21 | 26000 | 26000 | 26206.24 | 70% | 18200 | -7800 | -8006.24 | 0.7 | 0.69449 | 37437.4857 | 11231.2457 | -11437.4857 | Red
WBS-07 | 7 | HVAC Installation | Subcontractor | 2026-06-01 | 2026-06-28 | 28 | 36000 | 36000 | 17476.8 | 40% | 14400 | -21600 | -3076.8 | 0.4 | 0.82395 | 43692 | 26215.2 | -7692 | Red
WBS-08 | 8 | Partitions & Drywall | Subcontractor | 2026-06-08 | 2026-07-05 | 28 | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -21032.004 | -131.204 | 0.24886 | 0.98152 | 28527.2265 | 21428.0265 | -527.2265 | Red
WBS-09 | 9 | Flooring | Material | 2026-06-22 | 2026-07-12 | 21 | 35750 | 23833.34 | 0 | 0% | 0 | -23833.34 | 0 | 0 | 1 | 35750 | 35750 | 0 | Red
WBS-10 | 10 | Fixtures & Furniture | Material | 2026-06-29 | 2026-07-19 | 21 | 30000 | 10000 | 0 | 0% | 0 | -10000 | 0 | 0 | 1 | 30000 | 30000 | 0 | Red
WBS-11 | 11 | Testing / Commissioning | Labor | 2026-07-13 | 2026-07-26 | 14 | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 8400 | 8400 | 0 | Green
WBS-12 | 12 | Handover & Closeout | Labor | 2026-07-20 | 2026-07-26 | 7 | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 3600 | 3600 | 0 | Green
Total / Project Portfolio | [6 empty] | 267150 | 218733.34 | 141665.44 | 48.93% | 130717.996 | -88015.344 | -10947.444 | 0.59761 | 0.92272 | 289523.4279 | 147857.9879 | -22373.4279 | Red

## Task Capture
Task Capture / List the Tasks
Method: first list all tasks without worrying about order, cost, or time; then group into phases and convert into the controlled Task Plan.
Phase / Area | Task | WBS ID | Type | Included? | Event / Milestone? | Owner | Notes | Source / next action | Mapped to Task Plan
1 | Project Management | WBS-01 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
2 | Site Survey & Mobilization | WBS-02 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
3 | Design & Engineering | WBS-03 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
4 | Procurement - Materials | WBS-04 | Material | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
5 | Demolition & Prep | WBS-05 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
6 | Electrical Rough-In | WBS-06 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
7 | HVAC Installation | WBS-07 | Subcontractor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
8 | Partitions & Drywall | WBS-08 | Subcontractor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
9 | Flooring | WBS-09 | Material | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
10 | Fixtures & Furniture | WBS-10 | Material | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
11 | Testing / Commissioning | WBS-11 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
12 | Handover & Closeout | WBS-12 | Labor | Yes | No | Project Team | Imported from current Dim_WBS source data | Feeds Task Plan / EVM | Mapped
Brainstorm / new | [7 empty] | Add new tasks here before sequencing
Brainstorm / new | [7 empty] | Add new tasks here before sequencing
Example task-list method from attachment | Garden office example grouped tasks: clear the space, foundations, buy the shed, install shed, legal. Use this area to add unstructured tasks before converting them to WBS.

## EVM Dashboard
OFFICE FIT-OUT - PROJECT CONTROLLING DASHBOARD
EVM Performance Status ¦ Tufte-Compliant Design ¦ Data-Ink Maximized
Status Date: | 2026-06-30 |  | Status Week: | 8 |  | Sector: | Defense/Engineering | [5 empty] | RAG Legend | Rule | Meaning
[13 empty] | Green | Good | On/above plan or low exposure
BUDGET AT COMPLETION (BAC) |  |  | PLANNED VALUE (PV) |  |  | ACTUAL COST (AC) |  |  | EARNED VALUE (EV) |  |  |  | Amber | Watch | Near threshold / medium exposure
267150 |  |  | 218733.34 |  |  | 141665.44 |  |  | 130717.996 |  |  |  | Red | Action | Behind plan, overrun, or high exposure
COST VARIANCE (CV) |  |  | SCHEDULE VARIANCE (SV) |  |  | CPI (COST INDEX) |  |  | SPI (SCHEDULE INDEX)
-10947.444 |  |  | -88015.344 |  |  | 0.92272 |  |  | 0.59761
ESTIMATE AT COMPLETION (EAC) |  |  | ESTIMATE TO COMPLETE (ETC) |  |  | VARIANCE AT COMPLETION (VAC) |  |  | PROJECT PROGRESS %
289523.4279 |  |  | 147857.9879 |  |  | -22373.4279 |  |  | 48.93%
WBS Element Performance Breakdown
WBS ID | Activity Name | Type | Budget (BAC) | Planned Value (PV) | Actual Cost (AC) | Progress % | Earned Value (EV) | CV | SV | CPI | SPI | EAC | ETC | VAC | Status
WBS-01 | Project Management | Labor | 16500 | 12000 | 9280 | 50% | 8250 | -1030 | -3750 | 0.88901 | 0.6875 | 18560 | 9280 | -2060 | 🔴 Overrun
WBS-02 | Site Survey & Mobilization | Labor | 8500 | 8500 | 8700 | 100% | 8500 | -200 | 0 | 0.97701 | 1 | 8700 | 0 | -200 | 🔴 Overrun
WBS-03 | Design & Engineering | Labor | 19200 | 19200 | 18195.04 | 100% | 19200 | 1004.96 | 0 | 1.0552 | 1 | 18195.04 | 0 | 1004.96 | On Track
WBS-04 | Procurement - Materials | Material | 42000 | 42000 | 41300 | 100% | 42000 | 700 | 0 | 1.0169 | 1 | 41300 | 0 | 700 | On Track
WBS-05 | Demolition & Prep | Labor | 13200 | 13200 | 13408.16 | 100% | 13200 | -208.16 | 0 | 0.98448 | 1 | 13408.16 | 0 | -208.16 | 🔴 Overrun
WBS-06 | Electrical Rough-In | Labor | 26000 | 26000 | 26206.24 | 70% | 18200 | -8006.24 | -7800 | 0.69449 | 0.7 | 37437.4857 | 11231.2457 | -11437.4857 | 🔴 Overrun
WBS-07 | HVAC Installation | Subcontractor | 36000 | 36000 | 17476.8 | 40% | 14400 | -3076.8 | -21600 | 0.82395 | 0.4 | 43692 | 26215.2 | -7692 | 🔴 Overrun
WBS-08 | Partitions & Drywall | Subcontractor | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -131.204 | -21032.004 | 0.98152 | 0.24886 | 28527.2265 | 21428.0265 | -527.2265 | 🔴 Overrun
WBS-09 | Flooring | Material | 35750 | 23833.34 | 0 | 0% | 0 | 0 | -23833.34 | 1 | 0 | 35750 | 35750 | 0 | 🔴 Overrun
WBS-10 | Fixtures & Furniture | Material | 30000 | 10000 | 0 | 0% | 0 | 0 | -10000 | 1 | 0 | 30000 | 30000 | 0 | 🔴 Overrun
WBS-11 | Testing / Commissioning | Labor | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 8400 | 8400 | 0 | On Track
WBS-12 | Handover & Closeout | Labor | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | 3600 | 3600 | 0 | On Track
Total / Project Portfolio |  |  | 267150 | 218733.34 | 141665.44 | 48.93% | 130717.996 | -10947.444 | -88015.344 | 0.92272 | 0.59761 | 289523.4279 | 147857.9879 | -22373.4279 | 🔴 Overrun
Weekly Cumulative Performance Trends
Week | Week Date | Weekly PV | Cum PV | Weekly AC | Cum AC | Cum EV | CV | SV | CPI | SPI
1 | 2026-05-08 | 14900 | 14900 | 15975.04 | 15975.04 | 13588 | -2387.04 | -1312 | 0.85058 | 0.91195
2 | 2026-05-15 | 22800 | 37700 | 22654.08 | 38629.12 | 35814.0031 | -2815.1169 | -1885.9969 | 0.92712 | 0.94997
3 | 2026-05-22 | 22800 | 60500 | 22654.08 | 61283.2 | 56665 | -4618.2 | -3835 | 0.92464 | 0.93661
4 | 2026-05-29 | 25066.67 | 85566.67 | 24906.24 | 86189.44 | 79601.3285 | -6588.1115 | -5965.3415 | 0.92356 | 0.93028
5 | 2026-06-05 | 29666.67 | 115233.34 | 29476.8 | 115666.24 | 106769.6735 | -8896.5665 | -8463.6665 | 0.92308 | 0.92655
6 | 2026-06-12 | 26166.66 | 141400 | 25999.2 | 141665.44 | 130717.996 | -10947.444 | -10682.004 | 0.92272 | 0.92446
7 | 2026-06-19 | 17500 | 158900 | 0 | 141665.44 | 130717.996 | -10947.444 | -28182.004 | 0.92272 | 0.82264
8 | 2026-06-26 | 29416.67 | 188316.67 | 0 | 141665.44 | 130717.996 | -10947.444 | -57598.674 | 0.92272 | 0.69414
9 | 2026-07-03 | 30416.67 | 218733.34 | 0 | 141665.44 | 130717.996 | -10947.444 | -88015.344 | 0.92272 | 0.59761
10 | 2026-07-10 | 23416.66 | 242150 | 0 | 141665.44 | 130717.996 | -10947.444 | -111432.004 | 0.92272 | 0.53982
11 | 2026-07-17 | 15700 | 257850 | 0 | 141665.44 | 130717.996 | -10947.444 | -127132.004 | 0.92272 | 0.50695
12 | 2026-07-24 | 9300 | 267150 | 0 | 141665.44 | 130717.996 | -10947.444 | -136432.004 | 0.92272 | 0.48931

## Red Actions
Red RAG Action Recommendations
Focused recovery actions for WBS items and control risks currently flagged Red. Evidence is pulled live from tbl_Task_Plan.
STORY IN BRIEF
The red status is mainly schedule-driven: Flooring, Fixtures & Furniture, Partitions & Drywall, HVAC, and Electrical Rough-In are the recovery priorities because their SPI and schedule variances are pulling the project off plan. Cost exposure is concentrated in Electrical Rough-In and HVAC, while completed red tasks need closeout variance review rather than delivery acceleration. The recommended response is a short recovery sprint: remove blockers, confirm subcontractor/material readiness, reset near-term dates, and escalate decision items already logged in the Review sheet.
Red WBS items |  | Worst red SPI |  | Largest red SV |  | Red forecast overrun
8 |  | 0 |  | -23833.34 |  | 22124.8722
Priority | WBS ID | Activity | Red driver | Live evidence | Recommended action | Owner | Due date
1 | WBS-01 | Project Management | Cost overrun | CPI 0.89 / SPI 0.69 | Review scope, resource loading, and remaining forecast for Project Management | Project Manager | 2026-07-07
2 | WBS-02 | Site Survey & Mobilization | Cost overrun | CPI 0.98 / SPI 1.00 | Review scope, resource loading, and remaining forecast for Site Survey & Mobilization | Project Manager | 2026-07-07
3 | WBS-05 | Demolition & Prep | Cost overrun | CPI 0.98 / SPI 1.00 | Review scope, resource loading, and remaining forecast for Demolition & Prep | Project Manager | 2026-07-07
4 | WBS-06 | Electrical Rough-In | Cost overrun | CPI 0.69 / SPI 0.70 | Review scope, resource loading, and remaining forecast for Electrical Rough-In | Project Manager | 2026-07-07
5 | WBS-07 | HVAC Installation | Cost overrun | CPI 0.82 / SPI 0.40 | Review scope, resource loading, and remaining forecast for HVAC Installation | Project Manager | 2026-07-07
6 | WBS-08 | Partitions & Drywall | Cost overrun | CPI 0.98 / SPI 0.25 | Review scope, resource loading, and remaining forecast for Partitions & Drywall | Project Manager | 2026-07-07
7 | WBS-09 | Flooring | Schedule efficiency | CPI 1.00 / SPI 0.00 | Review scope, resource loading, and remaining forecast for Flooring | Project Manager | 2026-07-07
8 | WBS-10 | Fixtures & Furniture | Schedule efficiency | CPI 1.00 / SPI 0.00 | Review scope, resource loading, and remaining forecast for Fixtures & Furniture | Project Manager | 2026-07-07

## Pivot Summary
High-Level Pivot Summary & Descriptive Statistics
PivotTables summarize the key project-control tables; descriptive statistics are live formulas linked to the Task Plan source range.
STORY IN BRIEF
The project is Red overall: PV 218,733 NOK, AC 141,665 NOK, EV 130,718 NOK, with 8 red WBS items. The largest schedule gap is visible in later material/subcontractor work where planned value is ahead of earned progress.
Red WBS | Total BAC | Actual Cost | Earned Value | Avg SPI | Avg CPI | Forecast overrun
WBS-01 | 16500 | 9280 | 8250 | 0.6875 | 0.88901 | -2060
WBS-02 | 8500 | 8700 | 8500 | 1 | 0.97701 | -200
WBS-05 | 13200 | 13408.16 | 13200 | 1 | 0.98448 | -208.16
DESCRIPTIVE STATISTICS
Metric | Count | Mean | Median | Std Dev | Min | Max
BAC (NOK) | 12 | 22262.5 | 22600 | 12510.1254 | 3600 | 42000
PV @ Status | 12 | 18227.7783 | 16200 | 13348.9368 | 0 | 42000
AC @ Status | 12 | 11805.4533 | 8990 | 12607.7757 | 0 | 41300
EV @ Status | 12 | 10893.1663 | 8375 | 12099.6341 | 0 | 42000
Progress % | 12 | 0.4874 | 0.45 | 0.43809 | 0 | 1
SPI | 12 | 0.6697 | 0.85 | 0.40482 | 0 | 1
CPI | 12 | 0.95189 | 0.99224 | 0.1015 | 0.69449 | 1.0552
SV | 12 | -7334.612 | -1875 | 9564.5054 | -23833.34 | 0
CV | 12 | -912.287 | -65.602 | 2453.9533 | -8006.24 | 1004.96
VAC | 12 | -1701.6593 | -100 | 3829.7882 | -11437.4857 | 1004.96
PIVOT: COST / VALUE BY TYPE
PIVOT: COST / VALUE BY TYPE
Row Labels | Sum of BAC (NOK) | Sum of PV @ Status | Sum of AC @ Status | Sum of EV @ Status | Sum of SV | Sum of CV | Sum of VAC
Labor | 95400 | 78900 | 75789.44 | 67350 | -11550 | -8439.44 | -12900.6857
Material | 107750 | 75833.34 | 41300 | 42000 | -33833.34 | 700 | 700
Subcontractor | 64000 | 64000 | 24576 | 21367.996 | -42632.004 | -3208.004 | -8219.2265
Grand Total | 267150 | 218733.34 | 141665.44 | 130717.996 | -88015.344 | -10947.444 | -20419.9122
PIVOT: COST / VALUE BY STATUS
Row Labels | Sum of BAC (NOK) | Sum of PV @ Status | Sum of AC @ Status | Sum of EV @ Status | Sum of SV | Sum of CV | Sum of VAC
Red | 193950 | 157533.34 | 82170.4 | 69517.996 | -88015.344 | -12652.404 | -22124.8722
Green | 73200 | 61200 | 59495.04 | 61200 | 0 | 1704.96 | 1704.96
Grand Total | 267150 | 218733.34 | 141665.44 | 130717.996 | -88015.344 | -10947.444 | -20419.9122
PIVOT: ACTUAL COSTS BY WBS
Row Labels | Sum of Actual_Cost | Sum of Hours_Worked
WBS-01 | 9280 | 6.09
WBS-02 | 8700 | 3.95
WBS-03 | 18195.04 | 7.6
WBS-04 | 41300 | 0
WBS-05 | 13408.16 | 6.05
WBS-06 | 26206.24 | 10.1
WBS-07 | 17476.8 | 0
WBS-08 | 7099.2 | 0
WBS-09 | 0 | 0
WBS-10 | 0 | 0
WBS-11 | 0 | 0
WBS-12 | 0 | 0
Grand Total | 141665.44 | 33.79
PIVOT: WEEKLY EVM SUMMARY
Row Labels | Sum of Cum PV | Sum of Cum AC | Sum of Cum EV | Sum of SV | Sum of CV | Sum of VAC
1 | 14900 | 15975.04 | 13588 | -1312 | -2387.04 | -46930.9491
2 | 37700 | 38629.12 | 35814.0031 | -1885.9969 | -2815.1169 | -20999.0064
3 | 60500 | 61283.2 | 56665 | -3835 | -4618.2 | -21772.7368
4 | 85566.67 | 86189.44 | 79601.3285 | -5965.3415 | -6588.1115 | -22110.3595
5 | 115233.34 | 115666.24 | 106769.6735 | -8463.6665 | -8896.5665 | -22260.2324
6 | 141400 | 141665.44 | 130717.996 | -10682.004 | -10947.444 | -22373.4279
7 | 158900 | 141665.44 | 130717.996 | -28182.004 | -10947.444 | -22373.4279
8 | 188316.67 | 141665.44 | 130717.996 | -57598.674 | -10947.444 | -22373.4279
9 | 218733.34 | 141665.44 | 130717.996 | -88015.344 | -10947.444 | -22373.4279
10 | 242150 | 141665.44 | 130717.996 | -111432.004 | -10947.444 | -22373.4279
11 | 257850 | 141665.44 | 130717.996 | -127132.004 | -10947.444 | -22373.4279
12 | 267150 | 141665.44 | 130717.996 | -136432.004 | -10947.444 | -22373.4279
Grand Total | 1788400.02 | 1309401.12 | 1207463.9771 | -580936.0429 | -101937.1429 | -290687.2797

## Resource Grid
Resource Allocation Grid
Weekly hours and cost grid adapted from the attached Gantt template: rows are WBS tasks; columns are reporting weeks; totals are live formulas from actual-cost facts.
WBS ID | Activity | Resource / Role | Measure | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Total | BAC | Actual @ Status | Remaining BAC | CPI | RAG | Template source | Notes
WBS-01 | Project Management | Project Manager / Management | Hours | 0.84 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09 | 16500 | 9280 | 7220 | 0.88901 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-01 | Project Management | Project Manager / Management | Cost | 1280 | 1600 | 1600 | 1600 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 9280 | 16500 | 9280 | 7220 | 0.88901 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-02 | Site Survey & Mobilization | Demolition Crew / Labor | Hours | 3.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.95 | 8500 | 8700 | -200 | 0.97701 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-02 | Site Survey & Mobilization | Demolition Crew / Labor | Cost | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8700 | 8500 | 8700 | -200 | 0.97701 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-03 | Design & Engineering | Lead Engineer / Engineering | Hours | 2.5 | 2.5 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6 | 19200 | 18195.04 | 1004.96 | 1.0552 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-03 | Design & Engineering | Lead Engineer / Engineering | Cost | 5995.04 | 6000 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18195.04 | 19200 | 18195.04 | 1004.96 | 1.0552 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-04 | Procurement - Materials | Materials Vendor / Vendor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 41300 | 700 | 1.0169 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-04 | Procurement - Materials | Materials Vendor / Vendor | Cost | 0 | 10500 | 10200 | 10200 | 10400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41300 | 42000 | 41300 | 700 | 1.0169 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-05 | Demolition & Prep | Demolition Crew / Labor | Hours | 0 | 2.05 | 2.1 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.05 | 13200 | 13408.16 | -208.16 | 0.98448 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-05 | Demolition & Prep | Demolition Crew / Labor | Cost | 0 | 4554.08 | 4654.08 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13408.16 | 13200 | 13408.16 | -208.16 | 0.98448 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-06 | Electrical Rough-In | Electrician / Trades | Hours | 0 | 0 | 0 | 3.45 | 3.4 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 10.1 | 26000 | 26206.24 | -206.24 | 0.69449 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-06 | Electrical Rough-In | Electrician / Trades | Cost | 0 | 0 | 0 | 8906.24 | 8800 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 26206.24 | 26000 | 26206.24 | -206.24 | 0.69449 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-07 | HVAC Installation | HVAC Contractor / Contractor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 17476.8 | 18523.2 | 0.82395 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-07 | HVAC Installation | HVAC Contractor / Contractor | Cost | 0 | 0 | 0 | 0 | 8676.8 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 17476.8 | 36000 | 17476.8 | 18523.2 | 0.82395 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-08 | Partitions & Drywall | Drywall Contractor / Contractor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 7099.2 | 20900.8 | 0.98152 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-08 | Partitions & Drywall | Drywall Contractor / Contractor | Cost | 0 | 0 | 0 | 0 | 0 | 7099.2 | 0 | 0 | 0 | 0 | 0 | 0 | 7099.2 | 28000 | 7099.2 | 20900.8 | 0.98152 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-09 | Flooring | Material | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35750 | 0 | 35750 | 1 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-09 | Flooring | Material | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35750 | 0 | 35750 | 1 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-10 | Fixtures & Furniture | Material | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 1 | Red | 8.1.2 Gantt template from garden office | Hours row
WBS-10 | Fixtures & Furniture | Material | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 1 | Red | 8.1.2 Gantt template from garden office | Cost row
WBS-11 | Testing / Commissioning | Labor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 8400 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-11 | Testing / Commissioning | Labor | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 8400 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
WBS-12 | Handover & Closeout | Labor | Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1 | Green | 8.1.2 Gantt template from garden office | Hours row
WBS-12 | Handover & Closeout | Labor | Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1 | Green | 8.1.2 Gantt template from garden office | Cost row
Gantt of Gantts / monthly workload summary | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Total | Source | Interpretation
Planned PV | 85566.67 | 133166.67 | 48416.66 | 0 | 0 | 0 | 0 | 0 | 267150 | 8.1.2 Gantt of Gantts template | Monthly portfolio-style total from current project PV
Actual Cost | 86189.44 | 55476 | 0 | 0 | 0 | 0 | 0 | 0 | 141665.44 | 8.1.2 Gantt of Gantts template | Monthly portfolio-style total from actual costs
Active WBS count | 6 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 18 | 8.1.2 Gantt of Gantts template | Simple monthly activity indicator

## Dim_Project
Project_ID | Project_Name | Start_Date | End_Date | BAC | Sector
PRJ001 | Generic Master Project | 2026-01-01 | 2026-12-31 | 267150 | Defense/Engineering

## Dim_WBS
WBS_ID | WBS_Code | Activity_Name | Type | Total_Budget
WBS-01 | 1 | Project Management | Labor | 16500
WBS-02 | 2 | Site Survey & Mobilization | Labor | 8500
WBS-03 | 3 | Design & Engineering | Labor | 19200
WBS-04 | 4 | Procurement - Materials | Material | 42000
WBS-05 | 5 | Demolition & Prep | Labor | 13200
WBS-06 | 6 | Electrical Rough-In | Labor | 26000
WBS-07 | 7 | HVAC Installation | Subcontractor | 36000
WBS-08 | 8 | Partitions & Drywall | Subcontractor | 28000
WBS-09 | 9 | Flooring | Material | 35750
WBS-10 | 10 | Fixtures & Furniture | Material | 30000
WBS-11 | 11 | Testing / Commissioning | Labor | 8400
WBS-12 | 12 | Handover & Closeout | Labor | 3600

## Dim_Resource
Resource_ID | Resource_Name | Role | Hourly_Rate
R01 | Project Manager | Management | 1500
R02 | Lead Engineer | Engineering | 2400
R03 | Electrician | Trades | 2600
R04 | Demolition Crew | Labor | 2200
R05 | Testing Engineer | QA | 2100
R06 | Closeout Specialist | QA | 1800
R07 | Materials Vendor | Vendor | 0
R08 | HVAC Contractor | Contractor | 0
R09 | Drywall Contractor | Contractor | 0
R10 | Flooring Supplier | Vendor | 0
R11 | Furniture Supplier | Vendor | 0

## Dim_Calendar
Date | Year | Month | Month_Name | Quarter | Week_Number | Is_Weekday
2026-05-04 | 2026 | 5 | May | 2 | 1 | 1
2026-05-05 | 2026 | 5 | May | 2 | 1 | 1
2026-05-06 | 2026 | 5 | May | 2 | 1 | 1
2026-05-07 | 2026 | 5 | May | 2 | 1 | 1
2026-05-08 | 2026 | 5 | May | 2 | 1 | 1
2026-05-09 | 2026 | 5 | May | 2 | 1 | 0
2026-05-10 | 2026 | 5 | May | 2 | 1 | 0
2026-05-11 | 2026 | 5 | May | 2 | 2 | 1
2026-05-12 | 2026 | 5 | May | 2 | 2 | 1
2026-05-13 | 2026 | 5 | May | 2 | 2 | 1
2026-05-14 | 2026 | 5 | May | 2 | 2 | 1
2026-05-15 | 2026 | 5 | May | 2 | 2 | 1
2026-05-16 | 2026 | 5 | May | 2 | 2 | 0
2026-05-17 | 2026 | 5 | May | 2 | 2 | 0
2026-05-18 | 2026 | 5 | May | 2 | 3 | 1
2026-05-19 | 2026 | 5 | May | 2 | 3 | 1
2026-05-20 | 2026 | 5 | May | 2 | 3 | 1
2026-05-21 | 2026 | 5 | May | 2 | 3 | 1
2026-05-22 | 2026 | 5 | May | 2 | 3 | 1
2026-05-23 | 2026 | 5 | May | 2 | 3 | 0
2026-05-24 | 2026 | 5 | May | 2 | 3 | 0
2026-05-25 | 2026 | 5 | May | 2 | 4 | 1
2026-05-26 | 2026 | 5 | May | 2 | 4 | 1
2026-05-27 | 2026 | 5 | May | 2 | 4 | 1
2026-05-28 | 2026 | 5 | May | 2 | 4 | 1
2026-05-29 | 2026 | 5 | May | 2 | 4 | 1
2026-05-30 | 2026 | 5 | May | 2 | 4 | 0
2026-05-31 | 2026 | 5 | May | 2 | 4 | 0
2026-06-01 | 2026 | 6 | June | 2 | 5 | 1
2026-06-02 | 2026 | 6 | June | 2 | 5 | 1
2026-06-03 | 2026 | 6 | June | 2 | 5 | 1
2026-06-04 | 2026 | 6 | June | 2 | 5 | 1
2026-06-05 | 2026 | 6 | June | 2 | 5 | 1
2026-06-06 | 2026 | 6 | June | 2 | 5 | 0
2026-06-07 | 2026 | 6 | June | 2 | 5 | 0
2026-06-08 | 2026 | 6 | June | 2 | 6 | 1
2026-06-09 | 2026 | 6 | June | 2 | 6 | 1
2026-06-10 | 2026 | 6 | June | 2 | 6 | 1
2026-06-11 | 2026 | 6 | June | 2 | 6 | 1
2026-06-12 | 2026 | 6 | June | 2 | 6 | 1
2026-06-13 | 2026 | 6 | June | 2 | 6 | 0
2026-06-14 | 2026 | 6 | June | 2 | 6 | 0
2026-06-15 | 2026 | 6 | June | 2 | 7 | 1
2026-06-16 | 2026 | 6 | June | 2 | 7 | 1
2026-06-17 | 2026 | 6 | June | 2 | 7 | 1
2026-06-18 | 2026 | 6 | June | 2 | 7 | 1
2026-06-19 | 2026 | 6 | June | 2 | 7 | 1
2026-06-20 | 2026 | 6 | June | 2 | 7 | 0
2026-06-21 | 2026 | 6 | June | 2 | 7 | 0
2026-06-22 | 2026 | 6 | June | 2 | 8 | 1
2026-06-23 | 2026 | 6 | June | 2 | 8 | 1
2026-06-24 | 2026 | 6 | June | 2 | 8 | 1
2026-06-25 | 2026 | 6 | June | 2 | 8 | 1
2026-06-26 | 2026 | 6 | June | 2 | 8 | 1
2026-06-27 | 2026 | 6 | June | 2 | 8 | 0
2026-06-28 | 2026 | 6 | June | 2 | 8 | 0
2026-06-29 | 2026 | 6 | June | 2 | 9 | 1
2026-06-30 | 2026 | 6 | June | 2 | 9 | 1
2026-07-01 | 2026 | 7 | July | 3 | 9 | 1
2026-07-02 | 2026 | 7 | July | 3 | 9 | 1
2026-07-03 | 2026 | 7 | July | 3 | 9 | 1
2026-07-04 | 2026 | 7 | July | 3 | 9 | 0
2026-07-05 | 2026 | 7 | July | 3 | 9 | 0
2026-07-06 | 2026 | 7 | July | 3 | 10 | 1
2026-07-07 | 2026 | 7 | July | 3 | 10 | 1
2026-07-08 | 2026 | 7 | July | 3 | 10 | 1
2026-07-09 | 2026 | 7 | July | 3 | 10 | 1
2026-07-10 | 2026 | 7 | July | 3 | 10 | 1
2026-07-11 | 2026 | 7 | July | 3 | 10 | 0
2026-07-12 | 2026 | 7 | July | 3 | 10 | 0
2026-07-13 | 2026 | 7 | July | 3 | 11 | 1
2026-07-14 | 2026 | 7 | July | 3 | 11 | 1
2026-07-15 | 2026 | 7 | July | 3 | 11 | 1
2026-07-16 | 2026 | 7 | July | 3 | 11 | 1
2026-07-17 | 2026 | 7 | July | 3 | 11 | 1
2026-07-18 | 2026 | 7 | July | 3 | 11 | 0
2026-07-19 | 2026 | 7 | July | 3 | 11 | 0
2026-07-20 | 2026 | 7 | July | 3 | 12 | 1
2026-07-21 | 2026 | 7 | July | 3 | 12 | 1
2026-07-22 | 2026 | 7 | July | 3 | 12 | 1
2026-07-23 | 2026 | 7 | July | 3 | 12 | 1
2026-07-24 | 2026 | 7 | July | 3 | 12 | 1
2026-07-25 | 2026 | 7 | July | 3 | 12 | 0
2026-07-26 | 2026 | 7 | July | 3 | 12 | 0

## Fact_Baseline_PV
Date | WBS_ID | Planned_Value
2026-05-11 | WBS-01 | 1500
2026-05-18 | WBS-01 | 1500
2026-05-25 | WBS-01 | 1500
2026-06-01 | WBS-01 | 1500
2026-06-08 | WBS-01 | 1500
2026-06-15 | WBS-01 | 1500
2026-06-22 | WBS-01 | 1500
2026-06-29 | WBS-01 | 1500
2026-07-06 | WBS-01 | 1500
2026-07-13 | WBS-01 | 1500
2026-07-20 | WBS-01 | 1500
2026-05-04 | WBS-02 | 8500
2026-05-04 | WBS-03 | 6400
2026-05-11 | WBS-03 | 6400
2026-05-18 | WBS-03 | 6400
2026-05-11 | WBS-04 | 10500
2026-05-18 | WBS-04 | 10500
2026-05-25 | WBS-04 | 10500
2026-06-01 | WBS-04 | 10500
2026-05-11 | WBS-05 | 4400
2026-05-18 | WBS-05 | 4400
2026-05-25 | WBS-05 | 4400
2026-05-25 | WBS-06 | 8666.67
2026-06-01 | WBS-06 | 8666.67
2026-06-08 | WBS-06 | 8666.66
2026-06-01 | WBS-07 | 9000
2026-06-08 | WBS-07 | 9000
2026-06-15 | WBS-07 | 9000
2026-06-22 | WBS-07 | 9000
2026-06-08 | WBS-08 | 7000
2026-06-15 | WBS-08 | 7000
2026-06-22 | WBS-08 | 7000
2026-06-29 | WBS-08 | 7000
2026-06-22 | WBS-09 | 11916.67
2026-06-29 | WBS-09 | 11916.67
2026-07-06 | WBS-09 | 11916.66
2026-06-29 | WBS-10 | 10000
2026-07-06 | WBS-10 | 10000
2026-07-13 | WBS-10 | 10000
2026-07-13 | WBS-11 | 4200
2026-07-20 | WBS-11 | 4200
2026-07-20 | WBS-12 | 3600

## Fact_Actual_Costs
Date | WBS_ID | Resource_ID | Actual_Cost | Hours_Worked
2026-05-05 | WBS-01 | R01 | 320 | 0.21
2026-05-06 | WBS-01 | R01 | 320 | 0.21
2026-05-07 | WBS-01 | R01 | 320 | 0.21
2026-05-08 | WBS-01 | R01 | 320 | 0.21
2026-05-04 | WBS-02 | R04 | 1740 | 0.79
2026-05-05 | WBS-02 | R04 | 1740 | 0.79
2026-05-06 | WBS-02 | R04 | 1740 | 0.79
2026-05-07 | WBS-02 | R04 | 1740 | 0.79
2026-05-08 | WBS-02 | R04 | 1740 | 0.79
2026-05-04 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-05 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-06 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-07 | WBS-03 | R02 | 1199.01 | 0.5
2026-05-08 | WBS-03 | R02 | 1199 | 0.5
2026-05-11 | WBS-01 | R01 | 320 | 0.21
2026-05-12 | WBS-01 | R01 | 320 | 0.21
2026-05-13 | WBS-01 | R01 | 320 | 0.21
2026-05-14 | WBS-01 | R01 | 320 | 0.21
2026-05-15 | WBS-01 | R01 | 320 | 0.21
2026-05-11 | WBS-03 | R02 | 1200 | 0.5
2026-05-12 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-03 | R02 | 1200 | 0.5
2026-05-14 | WBS-03 | R02 | 1200 | 0.5
2026-05-15 | WBS-03 | R02 | 1200 | 0.5
2026-05-13 | WBS-04 | R07 | 10500 | 0
2026-05-11 | WBS-05 | R04 | 910.82 | 0.41
2026-05-12 | WBS-05 | R04 | 910.82 | 0.41
2026-05-13 | WBS-05 | R04 | 910.82 | 0.41
2026-05-14 | WBS-05 | R04 | 910.82 | 0.41
2026-05-15 | WBS-05 | R04 | 910.8 | 0.41
2026-05-18 | WBS-01 | R01 | 320 | 0.21
2026-05-19 | WBS-01 | R01 | 320 | 0.21
2026-05-20 | WBS-01 | R01 | 320 | 0.21
2026-05-21 | WBS-01 | R01 | 320 | 0.21
2026-05-22 | WBS-01 | R01 | 320 | 0.21
2026-05-18 | WBS-03 | R02 | 1240 | 0.52
2026-05-19 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-03 | R02 | 1240 | 0.52
2026-05-21 | WBS-03 | R02 | 1240 | 0.52
2026-05-22 | WBS-03 | R02 | 1240 | 0.52
2026-05-20 | WBS-04 | R07 | 10200 | 0
2026-05-18 | WBS-05 | R04 | 930.82 | 0.42
2026-05-19 | WBS-05 | R04 | 930.82 | 0.42
2026-05-20 | WBS-05 | R04 | 930.82 | 0.42
2026-05-21 | WBS-05 | R04 | 930.82 | 0.42
2026-05-22 | WBS-05 | R04 | 930.8 | 0.42
2026-05-25 | WBS-01 | R01 | 320 | 0.21
2026-05-26 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-01 | R01 | 320 | 0.21
2026-05-28 | WBS-01 | R01 | 320 | 0.21
2026-05-29 | WBS-01 | R01 | 320 | 0.21
2026-05-27 | WBS-04 | R07 | 10200 | 0
2026-05-25 | WBS-05 | R04 | 840 | 0.38
2026-05-26 | WBS-05 | R04 | 840 | 0.38
2026-05-27 | WBS-05 | R04 | 840 | 0.38
2026-05-28 | WBS-05 | R04 | 840 | 0.38
2026-05-29 | WBS-05 | R04 | 840 | 0.38
2026-05-25 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-26 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-27 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-28 | WBS-06 | R03 | 1781.25 | 0.69
2026-05-29 | WBS-06 | R03 | 1781.24 | 0.69
2026-06-01 | WBS-01 | R01 | 320 | 0.21
2026-06-02 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-01 | R01 | 320 | 0.21
2026-06-04 | WBS-01 | R01 | 320 | 0.21
2026-06-05 | WBS-01 | R01 | 320 | 0.21
2026-06-03 | WBS-04 | R07 | 10400 | 0
2026-06-01 | WBS-06 | R03 | 1760 | 0.68
2026-06-02 | WBS-06 | R03 | 1760 | 0.68
2026-06-03 | WBS-06 | R03 | 1760 | 0.68
2026-06-04 | WBS-06 | R03 | 1760 | 0.68
2026-06-05 | WBS-06 | R03 | 1760 | 0.68
2026-06-01 | WBS-07 | R08 | 1735.36 | 0
2026-06-02 | WBS-07 | R08 | 1735.36 | 0
2026-06-03 | WBS-07 | R08 | 1735.36 | 0
2026-06-04 | WBS-07 | R08 | 1735.36 | 0
2026-06-05 | WBS-07 | R08 | 1735.36 | 0
2026-06-08 | WBS-01 | R01 | 320 | 0.21
2026-06-09 | WBS-01 | R01 | 320 | 0.21
2026-06-10 | WBS-01 | R01 | 320 | 0.21
2026-06-11 | WBS-01 | R01 | 320 | 0.21
2026-06-12 | WBS-01 | R01 | 320 | 0.21
2026-06-08 | WBS-06 | R03 | 1700 | 0.65
2026-06-09 | WBS-06 | R03 | 1700 | 0.65
2026-06-10 | WBS-06 | R03 | 1700 | 0.65
2026-06-11 | WBS-06 | R03 | 1700 | 0.65
2026-06-12 | WBS-06 | R03 | 1700 | 0.65
2026-06-08 | WBS-07 | R08 | 1760 | 0
2026-06-09 | WBS-07 | R08 | 1760 | 0
2026-06-10 | WBS-07 | R08 | 1760 | 0
2026-06-11 | WBS-07 | R08 | 1760 | 0
2026-06-12 | WBS-07 | R08 | 1760 | 0
2026-06-08 | WBS-08 | R09 | 1419.84 | 0
2026-06-09 | WBS-08 | R09 | 1419.84 | 0
2026-06-10 | WBS-08 | R09 | 1419.84 | 0
2026-06-11 | WBS-08 | R09 | 1419.84 | 0
2026-06-12 | WBS-08 | R09 | 1419.84 | 0

## Fact_Physical_Progress
Date | WBS_ID | Physical_Progress_Pct
2026-05-08 | WBS-02 | 100%
2026-05-08 | WBS-03 | 26.5%
2026-05-15 | WBS-01 | 16.67%
2026-05-15 | WBS-02 | 100%
2026-05-15 | WBS-03 | 60%
2026-05-15 | WBS-04 | 20%
2026-05-15 | WBS-05 | 35.18%
2026-05-22 | WBS-01 | 25%
2026-05-22 | WBS-02 | 100%
2026-05-22 | WBS-03 | 100%
2026-05-22 | WBS-04 | 45%
2026-05-22 | WBS-05 | 45%
2026-05-29 | WBS-01 | 33.33%
2026-05-29 | WBS-02 | 100%
2026-05-29 | WBS-03 | 100%
2026-05-29 | WBS-04 | 70%
2026-05-29 | WBS-05 | 85%
2026-05-29 | WBS-06 | 22.24%
2026-06-05 | WBS-01 | 41.67%
2026-06-05 | WBS-02 | 100%
2026-06-05 | WBS-03 | 100%
2026-06-05 | WBS-04 | 100%
2026-06-05 | WBS-05 | 100%
2026-06-05 | WBS-06 | 50%
2026-06-05 | WBS-07 | 11.1%
2026-06-12 | WBS-01 | 50%
2026-06-12 | WBS-02 | 100%
2026-06-12 | WBS-03 | 100%
2026-06-12 | WBS-04 | 100%
2026-06-12 | WBS-05 | 100%
2026-06-12 | WBS-06 | 70%
2026-06-12 | WBS-07 | 40%
2026-06-12 | WBS-08 | 24.89%

## EVM
EVM Reporting
Weekly earned value reporting table using the guideline formulas: PV, AC, EV, SV, CV, SPI, CPI, BAC, EAC, ETC, and VAC.
Week | Week Date | Cum PV | Cum AC | Cum EV | SV | CV | SPI | CPI | BAC | EAC | ETC | VAC | Status
1 | 2026-05-08 | 14900 | 15975.04 | 13588 | -1312 | -2387.04 | 0.91195 | 0.85058 | 267150 | 314080.9491 | 298105.9091 | -46930.9491 | Red
2 | 2026-05-15 | 37700 | 38629.12 | 35814.0031 | -1885.9969 | -2815.1169 | 0.94997 | 0.92712 | 267150 | 288149.0064 | 249519.8864 | -20999.0064 | Red
3 | 2026-05-22 | 60500 | 61283.2 | 56665 | -3835 | -4618.2 | 0.93661 | 0.92464 | 267150 | 288922.7368 | 227639.5368 | -21772.7368 | Red
4 | 2026-05-29 | 85566.67 | 86189.44 | 79601.3285 | -5965.3415 | -6588.1115 | 0.93028 | 0.92356 | 267150 | 289260.3595 | 203070.9195 | -22110.3595 | Red
5 | 2026-06-05 | 115233.34 | 115666.24 | 106769.6735 | -8463.6665 | -8896.5665 | 0.92655 | 0.92308 | 267150 | 289410.2324 | 173743.9924 | -22260.2324 | Red
6 | 2026-06-12 | 141400 | 141665.44 | 130717.996 | -10682.004 | -10947.444 | 0.92446 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
7 | 2026-06-19 | 158900 | 141665.44 | 130717.996 | -28182.004 | -10947.444 | 0.82264 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
8 | 2026-06-26 | 188316.67 | 141665.44 | 130717.996 | -57598.674 | -10947.444 | 0.69414 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
9 | 2026-07-03 | 218733.34 | 141665.44 | 130717.996 | -88015.344 | -10947.444 | 0.59761 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
10 | 2026-07-10 | 242150 | 141665.44 | 130717.996 | -111432.004 | -10947.444 | 0.53982 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
11 | 2026-07-17 | 257850 | 141665.44 | 130717.996 | -127132.004 | -10947.444 | 0.50695 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
12 | 2026-07-24 | 267150 | 141665.44 | 130717.996 | -136432.004 | -10947.444 | 0.48931 | 0.92272 | 267150 | 289523.4279 | 147857.9879 | -22373.4279 | Red
Formula | Workbook implementation | Guideline meaning | Current status-date value | Check | Source | Column1 | Status tie-out | Dashboard value | Task Plan value | Variance | Check2 | Source3
SV = EV - PV | #N/A | Schedule variance at status date | -88015.344 | Live | PM-EVM.md lines 145-150 |  | PV | 218733.34 | 218733.34 | 0 | OK | Task Plan!I17
CV = EV - AC | #N/A | Cost variance at status date | -10947.444 | Live | PM-EVM.md lines 145-150 |  | AC | 141665.44 | 141665.44 | 0 | OK | Task Plan!J17
SPI = EV / PV | #N/A | Schedule efficiency | 0.59761 | Live | PM-EVM.md lines 145-150 |  | EV | 130717.996 | 130717.996 | 0 | OK | Task Plan!L17
CPI = EV / AC | #N/A | Cost efficiency | 0.92272 | Live | PM-EVM.md lines 145-150 |  | SPI | -10947.444 | -10947.444 | 0 | OK | Task Plan!O17
EAC = BAC / CPI | #N/A | Forecast final cost | 289523.4279 | Live | PM-EVM.md lines 203-214 |  | CPI | 0.59761 | 0.59761 | 0 | OK | Task Plan!P17
VAC = BAC - EAC | #N/A | Expected budget variance at completion | 147857.9879 | Live | PM-EVM.md lines 203-214 |  | VAC | 0.92272 | 0.92272 | 0 | OK | Task Plan!S17

## EVM Charts
Project Schedule & EVM Curves | [12 empty] | Project Start | 2026-05-04
Gantt schedule is derived from baseline PV dates by WBS; the S-curve uses cumulative PV, actual cost, and earned value as of each weekly status date. | [12 empty] | Project Finish | 2026-12-31
[13 empty] | Status Date | 2026-06-30
WBS ID | Activity | Start | Finish | Start Offset | Duration Days | Progress % | RAG
WBS-01 | Project Management | 2026-05-11 | 2026-07-26 | 7 | 77 | 50% | Amber | [5 empty] | RAG Legend | Rule | Used in charts
WBS-02 | Site Survey & Mobilization | 2026-05-04 | 2026-05-10 | 0 | 7 | 100% | Green | [5 empty] | Green | Good / baseline target | Gantt good bars; PV line
WBS-03 | Design & Engineering | 2026-05-04 | 2026-05-24 | 0 | 21 | 100% | Green | [5 empty] | Amber | Watch / earned progress | Gantt watch bars; EV line
WBS-04 | Procurement - Materials | 2026-05-11 | 2026-06-07 | 7 | 28 | 100% | Green | [5 empty] | Red | Action / cost exposure | Gantt action bars; AC line
WBS-05 | Demolition & Prep | 2026-05-11 | 2026-05-31 | 7 | 21 | 100% | Green | [5 empty] | White | Hidden helper | Gantt start-offset series
WBS-06 | Electrical Rough-In | 2026-05-25 | 2026-06-14 | 21 | 21 | 70% | Amber | [5 empty] | Red dotted | Status date | Vertical marker at 2026-06-30
WBS-07 | HVAC Installation | 2026-06-01 | 2026-06-28 | 28 | 28 | 40% | Red
WBS-08 | Partitions & Drywall | 2026-06-08 | 2026-07-05 | 35 | 28 | 24.89% | Red
WBS-09 | Flooring | 2026-06-22 | 2026-07-12 | 49 | 21 | 0% | Red
WBS-10 | Fixtures & Furniture | 2026-06-29 | 2026-07-19 | 56 | 21 | 0% | Red
WBS-11 | Testing / Commissioning | 2026-07-13 | 2026-07-26 | 70 | 14 | 0% | Red
WBS-12 | Handover & Closeout | 2026-07-20 | 2026-07-26 | 77 | 7 | 0% | Red
Week | Week Date | Cum PV | Cum AC | Cum EV | CPI | SPI | CV | SV | Week Date | Cum PV | Cum AC | Cum EV | Status X | Status Y | Status Label
1 | 2026-05-08 | 14900 | 15975.04 | 13588 | 0.85058 | 0.91195 | -2387.04 | -1312 | 2026-05-08 | 14900 | 15975.04 | 13588
2 | 2026-05-15 | 37700 | 38629.12 | 35814.0031 | 0.92712 | 0.94997 | -2815.1169 | -1885.9969 | 2026-05-15 | 37700 | 38629.12 | 35814.0031
3 | 2026-05-22 | 60500 | 61283.2 | 56665 | 0.92464 | 0.93661 | -4618.2 | -3835 | 2026-05-22 | 60500 | 61283.2 | 56665
4 | 2026-05-29 | 85566.67 | 86189.44 | 79601.3285 | 0.92356 | 0.93028 | -6588.1115 | -5965.3415 | 2026-05-29 | 85566.67 | 86189.44 | 79601.3285
5 | 2026-06-05 | 115233.34 | 115666.24 | 106769.6735 | 0.92308 | 0.92655 | -8896.5665 | -8463.6665 | 2026-06-05 | 115233.34 | 115666.24 | 106769.6735
6 | 2026-06-12 | 141400 | 141665.44 | 130717.996 | 0.92272 | 0.92446 | -10947.444 | -10682.004 | 2026-06-12 | 141400 | 141665.44 | 130717.996
7 | 2026-06-19 | 158900 | 141665.44 | 130717.996 | 0.92272 | 0.82264 | -10947.444 | -28182.004 | 2026-06-19 | 158900 | 141665.44 | 130717.996
8 | 2026-06-26 | 188316.67 | 141665.44 | 130717.996 | 0.92272 | 0.69414 | -10947.444 | -57598.674 | 2026-06-26 | 188316.67 | 141665.44 | 130717.996
9 | 2026-07-03 | 218733.34 | 141665.44 | 130717.996 | 0.92272 | 0.59761 | -10947.444 | -88015.344 | 2026-07-03 | 218733.34 | 141665.44 | 130717.996
10 | 2026-07-10 | 242150 | 141665.44 | 130717.996 | 0.92272 | 0.53982 | -10947.444 | -111432.004 | 2026-07-10 | 242150 | 141665.44 | 130717.996
11 | 2026-07-17 | 257850 | 141665.44 | 130717.996 | 0.92272 | 0.50695 | -10947.444 | -127132.004 | 2026-07-17 | 257850 | 141665.44 | 130717.996
12 | 2026-07-24 | 267150 | 141665.44 | 130717.996 | 0.92272 | 0.48931 | -10947.444 | -136432.004 | 2026-07-24 | 267150 | 141665.44 | 130717.996
[9 empty] | 2026-06-30 |  |  |  | 2026-06-30 | 0
[9 empty] | 2026-06-30 |  |  |  | 2026-06-30 | 280507.5 | Status date 2026-06-30
As of 2026-06-30 CPI 0.92 | SPI 0.60

## Simple Gantt Model
Gantt Model — Office Fit-Out
Adapted from the attached Garden Office Gantt template. This sheet is populated from the current workbook WBS, baseline PV, actual cost, actual hours, progress, CPI/RAG status, and status date.
Project controls and model mapping
Project | Generic Master Project | Project Start | 2026-01-01 | Project End | 2026-12-31 | Status Date | 2026-06-30 | BAC | 268,650.00 NOK | Source | Current workbook
Template element | Implemented as | Source table | Meaning | Classification
My hours | Weekly hours grid | Fact_Actual_Costs[Hours_Worked] | Actual hours by WBS and week; o = planned week with no actual hours yet. | Control
Total costs | Weekly cost grid | Fact_Actual_Costs[Actual_Cost] | Actual cost by WBS and week; o = planned week with no actual cost yet. | Control
STATUS DATE
My hours — current project actual hours by WBS / week
Task | Role / Type | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | Total
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Management | Labor | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | o | o | o | o | o | o | 6.3
Site Survey & Mobilization | Labor | 1: 3.95 | 3.95
Design & Engineering | Labor | 1: 2.5; 2: 2.5; 3: 2.6 | 7.6
Procurement - Materials | Material | [12 empty] | 0 | bar: 2 to 5; 9
Demolition & Prep | Labor | 2: 2.05; 3: 2.1; 4: 1.9 | 6.05
Electrical Rough-In | Labor | 4: 3.45; 5: 3.4; 6: 3.25 | 10.1
HVAC Installation | Subcontractor | [12 empty] | 0 | bar: 5 to 9
Partitions & Drywall | Subcontractor | [12 empty] | 0 | bar: 6 to 9
Flooring | Material | [12 empty] | 0 | bar: 8 to 10
Fixtures & Furniture | Material | [12 empty] | 0 | bar: 9 to 11
Testing / Commissioning | Labor | [12 empty] | 0 | bar: 9; 11 to 12
Handover & Closeout | Labor | [12 empty] | 0 | bar: 9; 12
my total hours |  | 7.5 | 5.6 | 5.75 | 6.4 | 4.45 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Total costs — current project actual costs by WBS / week
Task | Who / Type | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | Total
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Management | Labor | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | o | o | o | o | o | o | 9600
Site Survey & Mobilization | Labor | 1: 8700 | 8700
Design & Engineering | Labor | 1: 5995.04; 2: 6000; 3: 6200 | 18195.04
Procurement - Materials | Material | 2: 10500; 3: 10200; 4: 10200; 5: 10400 | 41300
Demolition & Prep | Labor | 2: 4554.08; 3: 4654.08; 4: 4200 | 13408.16
Electrical Rough-In | Labor | 4: 8906.24; 5: 8800; 6: 8500 | 26206.24
HVAC Installation | Subcontractor | 5: 8676.8; 6: 8800; 7: o; 8: o | 17476.8
Partitions & Drywall | Subcontractor | 6: 7099.2; 7: o; 8: o; 9: o | 7099.2
Flooring | Material | [12 empty] | 0 | bar: 8 to 10
Fixtures & Furniture | Material | [12 empty] | 0 | bar: 9 to 11
Testing / Commissioning | Labor | [12 empty] | 0 | bar: 9; 11 to 12
Handover & Closeout | Labor | [12 empty] | 0 | bar: 9; 12
my total costs |  | 16295.04 | 22654.08 | 22654.08 | 24906.24 | 29476.8 | 25999.2 | 0 | 0 | 0 | 0 | 0 | 0 | 141985.44
Task | BAC | PV @ Status | AC @ Status | Progress % | EV @ Status | SV | CV | SPI | CPI | RAG
Project Management | 18000 | 13500 | 9600 | 50% | 9000 | -4500 | -600 | 0.66667 | 0.9375 | Red
Site Survey & Mobilization | 8500 | 8500 | 8700 | 100% | 8500 | 0 | -200 | 1 | 0.97701 | Red
Design & Engineering | 19200 | 19200 | 18195.04 | 100% | 19200 | 0 | 1004.96 | 1 | 1.0552 | Green
Procurement - Materials | 42000 | 42000 | 41300 | 100% | 42000 | 0 | 700 | 1 | 1.0169 | Green
Demolition & Prep | 13200 | 13200 | 13408.16 | 100% | 13200 | 0 | -208.16 | 1 | 0.98448 | Red
Electrical Rough-In | 26000 | 26000 | 26206.24 | 70% | 18200 | -7800 | -8006.24 | 0.7 | 0.69449 | Red
HVAC Installation | 36000 | 36000 | 17476.8 | 40% | 14400 | -21600 | -3076.8 | 0.4 | 0.82395 | Red
Partitions & Drywall | 28000 | 28000 | 7099.2 | 24.89% | 6967.996 | -21032.004 | -131.204 | 0.24886 | 0.98152 | Red
Flooring | 35750 | 23833.34 | 0 | 0% | 0 | -23833.34 | 0 | 0 | 1 | Red
Fixtures & Furniture | 30000 | 10000 | 0 | 0% | 0 | -10000 | 0 | 0 | 1 | Red
Testing / Commissioning | 8400 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | Green
Handover & Closeout | 3600 | 0 | 0 | 0% | 0 | 0 | 0 | 1 | 1 | Green
Status timeline: 2026-06-30
Legend | Meaning | 1: Applied to
Red dotted vertical line | Status date 2026-06-30 | 1: My hours and Total costs grids
Green row | CPI/SPI >= 1.00 and favorable variance | 1: Summary + task totals
Amber row | Near threshold | 1: Summary + task totals
Red row | Behind plan / cost overrun / low index | 1: Summary + task totals

## PERT Diagram
Swimlane PERT Diagram — Office Fit-Out
PERT network grouped into swimlanes by Task Plan type: Labor, Material, and Subcontractor. Status date: 2026-06-30. Node colors use the workbook RAG status.
WBS ID | Activity | Baseline Start | Baseline Finish | Duration | Progress | SPI | CPI | RAG | Inferred predecessor(s) | Visio-style PERT Legend | Column1 | Column2
WBS-01 | Project Management | 2026-05-11 | 2026-07-26 | 77 | 50% | 0.6875 | 0.88901 | Red | Start | Green | On track | CPI/SPI/variance favorable
WBS-02 | Site Survey & Mobilization | 2026-05-04 | 2026-05-10 | 7 | 100% | 1 | 0.97701 | Red | WBS-01 | Amber | Watch | Near threshold
WBS-03 | Design & Engineering | 2026-05-04 | 2026-05-24 | 21 | 100% | 1 | 1.0552 | Green | WBS-02 | Red | Action | Behind plan / overrun
WBS-04 | Procurement - Materials | 2026-05-11 | 2026-06-07 | 28 | 100% | 1 | 1.0169 | Green | WBS-03 | Gray | Start / Finish | Network endpoints
WBS-05 | Demolition & Prep | 2026-05-11 | 2026-05-31 | 21 | 100% | 1 | 0.98448 | Red | WBS-04
WBS-06 | Electrical Rough-In | 2026-05-25 | 2026-06-14 | 21 | 70% | 0.7 | 0.69449 | Red | WBS-05
WBS-07 | HVAC Installation | 2026-06-01 | 2026-06-28 | 28 | 40% | 0.4 | 0.82395 | Red | WBS-06
WBS-08 | Partitions & Drywall | 2026-06-08 | 2026-07-05 | 28 | 24.89% | 0.24886 | 0.98152 | Red | WBS-07
WBS-09 | Flooring | 2026-06-22 | 2026-07-12 | 21 | 0% | 0 | 1 | Red | WBS-08
WBS-10 | Fixtures & Furniture | 2026-06-29 | 2026-07-19 | 21 | 0% | 0 | 1 | Red | WBS-09
WBS-11 | Testing / Commissioning | 2026-07-13 | 2026-07-26 | 14 | 0% | 1 | 1 | Green | WBS-10
WBS-12 | Handover & Closeout | 2026-07-20 | 2026-07-26 | 7 | 0% | 1 | 1 | Green | WBS-11
Swimlane view below: dependencies flow left-to-right; each horizontal lane groups work by Task Plan type.