## Overview
The 12 Step Process | by Chris Croft
Project Management Fundamentals
From a hundred years of research and experience the APM and
PMI invented the ultimate Project Management process. From
that I’ve distilled their research into a simple and practical 12
Step Process. This will work for every project, regardless of size,
industry or timeframe.
Identify Key Driver
Scope
> Step 1 - Define the project | Time |  | Cost
> Step 2 - List the tasks ¦ Level of granularity | Level of granularity |  |  | Task List | Elapsed weeks
> Step 3 - Establishing task order |  |  |  | Demolish old shed
> Step 4 - Estimating time |  |  |  | Cut foliage back
> Step 5 - Margin check & reality check |  |  |  | Tree surgeon
> Step 6 - Gantt Chart |  |  |  | Foundations
> Step 7 - Resource allocation |  |  |  | Dig trench
> Step 8 - Predicting & reducing risk |  |  |  | Hire digger
> Step 9 - Monitoring progress |  |  |  | Fill with concrete
> Step 10 - Monitoring cost |  |  |  | Level the base
> Step 11 - Adjusting the plan |  |  |  | Buy the shed
> Step 12 - Review & lessons |  |  |  | Find suppliers
Ask friends
Get quotes
See a finished one
Delivery time
Install shed
Wire down the garden
Assembly of structure
Put in the furniture
Set up computers
Install music system
Painting outside
Painting inside
Check if I need planning permission
Wait for planning permission
Check I’ve got enough funds

## 1. Define Project
Project Definition — Database-Ready Setup
Use one row for the project header and separate child rows for repeating items like scope. This keeps the data clean for Excel tables, Power Query, CSV export, and relational database import. | [8 empty] | Rule | Recommendation | Reason
[9 empty] | Use stable IDs | Use ProjectID, not project name, as the primary key | Names change; IDs remain reliable for database joins
Recommended structure | [8 empty] | Separate repeating data | Put scope items in tblProjectScope, one item per row | Avoids comma-separated lists and supports one-to-many database relationships
[9 empty] | Keep atomic fields | Do not combine owner, date, budget, and notes in one cell | Databases import and validate one value per field best
ProjectID | ProjectName | ProjectOwner | CreatedDate | Version | Status | Budget | Start Date | End Date | Use consistent values | Use controlled values such as Draft, Approved, In Scope, Out of Scope | Reduces cleanup and prevents spelling variants
PRJ-001 | New Garden Shed | Frank Ellingsen | 2026-08-04T22:00:00.000Z | 1 | Draft | 20000 | 06.01.2026 | 10.31.2026 | Avoid merged cells in tables | Keep merged cells only in titles, never inside import tables | Merged cells break many import and transformation tools
[9 empty] | Add audit fields | Keep Version, CreatedDate, DataSource, and ImportKey | Helps identify changed records during future imports
ProjectID | ScopeType | ScopeItem | Priority | DecisionStatus | SourceNote
PRJ-001 | In Scope | Electricity | High | Approved | Migrated from original B5 value
PRJ-001 | Out of Scope | Plumbing | High | Approved | Migrated from original B7 value

## 2. List Tasks
Step 2 — Work Breakdown Structure
Your task brainstorm is now captured as a hierarchical WBS. Summary rows keep the structure readable; work-package rows are the actual tasks that can later receive order, duration, resources, and cost. | [10 empty] | Field | How to use it | Database note
[11 empty] | WBSCode | Hierarchical code such as 3.2.5 | Stable key for hierarchy/order import
WBS summary | [10 empty] | ParentWBSCode | Immediate parent code, blank for top-level groups | Supports parent-child database relationships
[11 empty] | WBSLevel | 1 for major group, 2 for child, 3 for sub-child | Useful for indentation and filtering
ProjectID | PRJ-001 |  | Total WBS rows | 35 | Work packages |  | 26 | 6 |  |  | TaskGroup | Main grouping for easy filtering | Can become a lookup/category table
[11 empty] | TaskName | The WBS element or task name | One row per WBS element
ProjectID | WBSCode | ParentWBSCode | WBSLevel | TaskGroup | TaskName | IsWorkPackage | CaptureStatus | Elapsed Time in Weeks | Start-Week | End-Week | IsWorkPackage | Yes means it is an actionable task; No means summary/group row | Import only Yes rows into execution schedule if needed
PRJ-001 | 1 |  | 1 | Planning | Planning | No | Approved | 16 |  |  | CaptureStatus | Draft, Reviewed, Approved, or Removed | Keeps review state without deleting history
PRJ-001 | 1.1 | 1 | 2 | Planning | Check can I get planning? | Yes | Draft | 6 | 1 | 7
PRJ-001 | 1.2 | 1 | 2 | Planning | Apply for and get planning permission | Yes | Draft | 10 | 7 | 17 | IsWorkPackage | No
PRJ-001 | 2 |  | 1 | Prepare site | Prepare site | No | Approved | 3 |  | 3
PRJ-001 | 2.1 | 2 | 2 | Prepare site | Demolish old shed | Yes | Draft | 1 |  | 1 | Row Labels | Sum of Elapsed Time in Weeks
PRJ-001 | 2.2 | 2 | 2 | Prepare site | Cut back all the foliage | Yes | Draft | 2 |  | 2 | Assembly of structure | 10
PRJ-001 | 2.3 | 2 | 2 | Prepare site | Tree surgeon to trim branches above area | Yes | Draft |  |  | 0 | Assembly of structure | 10
PRJ-001 | 2.4 | 2 | 2 | Prepare site | Put a power wire down the garden | Yes | Draft |  |  | 0 | Painting
PRJ-001 | 2.5 | 2 | 2 | Prepare site | Connect power | Yes | Draft |  |  | 0 | Buying | 17
PRJ-001 | 3 |  | 1 | Buying | Buying | No | Approved | 17 |  |  | Buying | 17
PRJ-001 | 3.1 | 3 | 2 | Buying | Check funds | Yes | Draft | 1 |  | 1 | Other stuff
PRJ-001 | 3.2 | 3 | 2 | Buying | Shed | No | Approved |  |  | 0 | Shed
PRJ-001 | 3.2.1 | 3.2 | 3 | Shed | Research - talk to friends | Yes | Draft | 3 |  | 3 | Foundations | 6
PRJ-001 | 3.2.2 | 3.2 | 3 | Shed | Find shed suppliers | Yes | Draft | 1 |  | 1 | Foundations | 6
PRJ-001 | 3.2.3 | 3.2 | 3 | Shed | Get quotes | Yes | Draft | 3 |  | 3 | Installing stuff | 3
PRJ-001 | 3.2.4 | 3.2 | 3 | Shed | See a finished one | Yes | Draft | 1 |  | 1 | Installing stuff | 3
PRJ-001 | 3.2.5 | 3.2 | 3 | Shed | Choose - place the order | Yes | Draft |  |  | 0 | Planning | 16
PRJ-001 | 3.2.6 | 3.2 | 3 | Shed | Wait for delivery | Yes | Draft | 6 |  | 6 | Planning | 16
PRJ-001 | 3.3 | 3 | 2 | Buying | Other stuff | No | Approved |  |  | 0 | Prepare site | 3
PRJ-001 | 3.3.1 | 3.3 | 3 | Other stuff | Buy furniture | Yes | Draft | 2 |  | 2 | Prepare site | 3
PRJ-001 | 4 |  | 1 | Foundations | Foundations | No | Approved | 6 |  |  | Grand Total | 55
PRJ-001 | 4.1 | 4 | 2 | Foundations | Hire Digger | Yes | Draft | 2 |  | 2
PRJ-001 | 4.2 | 4 | 2 | Foundations | Dig foundation trenches | Yes | Draft | 1 |  | 1
PRJ-001 | 4.3 | 4 | 2 | Foundations | Fill with concrete | Yes | Draft | 2 |  | 2
PRJ-001 | 4.4 | 4 | 2 | Foundations | Level the base | Yes | Draft | 1 |  | 1 |  |  | 27
PRJ-001 | 5 |  | 1 | Assembly of structure | Assembly of structure | No | Approved | 10
PRJ-001 | 5.1 | 5 | 2 | Assembly of structure | Delivery | Yes | Draft | 6 |  | 6
PRJ-001 | 5.2 | 5 | 2 | Assembly of structure | Assembly | Yes | Draft | 1 |  | 1
PRJ-001 | 5.3 | 5 | 2 | Assembly of structure | Painting | No | Approved |  |  | 0
PRJ-001 | 5.3.1 | 5.3 | 3 | Painting | Inside | Yes | Draft | 1 |  | 1
PRJ-001 | 5.3.2 | 5.3 | 3 | Painting | External | Yes | Draft | 2 |  | 2
PRJ-001 | 6 |  | 1 | Installing stuff | Installing stuff | No | Approved | 3
PRJ-001 | 6.1 | 6 | 2 | Installing stuff | Install Furniture | Yes | Draft | 1 |  | 1
PRJ-001 | 6.2 | 6 | 2 | Installing stuff | Set up computers | Yes | Draft | 1 |  | 1
PRJ-001 | 6.3 | 6 | 2 | Installing stuff | Set up music system | Yes | Draft | 1 |  | 1
Clear the space in the garden
Demolish old shed
Cut foliage back
Tree surgeon
Foundations
Dig trench
Hire digger
Fill with concrete
Level the base
Buy the shed
Find suppliers
Ask friends
Get quotes
See a finished one
Choose (event)
Delivery time
Install shed
Delivery (event)
Wire down the garden
Connect power (event)
Assembly of structure
Put in the furniture
Set up computers
Install music system
Painting outside
Painting inside
Legal
Check if I need planning permission
Wait for planning permission
Check I’ve got enough mone

## Swimlane
Project Tasks Swimlane — by TaskGroup
Linked to tblProjectTasks. Enter numeric values in tblProjectTasks[Time in Weeks] to replace the placeholder bars. Current status: 26 work packages; 26 durations blank.
Work packages | 26 |  | Blank durations | 26 |  | Visible horizon | 32 weeks |  | Placeholder symbol | ◇ = 1 week assumed
TaskGroup | WBSCode | TaskName | Time in Weeks | Chart Weeks | Start Week | End Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Planning | 1.1 | Check can I get planning? | 6 | 6 | 0 | 6 | ■ | ■ | ■ | ■ | ■ | ■
Planning | 1.2 | Apply for and get planning permission | 10 | 10 | 6 | 16 | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Prepare site | 2.1 | Demolish old shed | 1 | 1 | 16 | 17 | [16 empty] | ■
Prepare site | 2.2 | Cut back all the foliage | 2 | 2 | 17 | 19 | [17 empty] | ■ | ■
Prepare site | 2.3 | Tree surgeon to trim branches above area |  | 1 | 19 | 20 | [19 empty] | ◇
Prepare site | 2.4 | Put a power wire down the garden |  | 1 | 20 | 21 | [20 empty] | ◇
Prepare site | 2.5 | Connect power |  | 1 | 21 | 22 | [21 empty] | ◇
Buying | 3.1 | Check funds | 1 | 1 | 22 | 23 | [22 empty] | ■
Shed | 3.2.1 | Research - talk to friends | 3 | 3 | 23 | 26 | [23 empty] | ■ | ■ | ■
Shed | 3.2.2 | Find shed suppliers | 1 | 1 | 26 | 27 | [26 empty] | ■
Shed | 3.2.3 | Get quotes | 3 | 3 | 27 | 30 | [27 empty] | ■ | ■ | ■
Shed | 3.2.4 | See a finished one | 1 | 1 | 30 | 31 | [30 empty] | ■
Shed | 3.2.5 | Choose - place the order |  | 1 | 31 | 32 | [31 empty] | ◇
Shed | 3.2.6 | Wait for delivery | 6 | 6 | 32 | 38
Other stuff | 3.3.1 | Buy furniture | 2 | 2 | 38 | 40
Foundations | 4.1 | Hire Digger | 2 | 2 | 40 | 42
Foundations | 4.2 | Dig foundation trenches | 1 | 1 | 42 | 43
Foundations | 4.3 | Fill with concrete | 2 | 2 | 43 | 45
Foundations | 4.4 | Level the base | 1 | 1 | 45 | 46
Assembly of structure | 5.1 | Delivery | 6 | 6 | 46 | 52
Assembly of structure | 5.2 | Assembly | 1 | 1 | 52 | 53
Painting | 5.3.1 | Inside | 1 | 1 | 53 | 54
Painting | 5.3.2 | External | 2 | 2 | 54 | 56
Installing stuff | 6.1 | Install Furniture | 1 | 1 | 56 | 57
Installing stuff | 6.2 | Set up computers | 1 | 1 | 57 | 58
Installing stuff | 6.3 | Set up music system | 1 | 1 | 58 | 59

## 3. Dependencies
Step 3 — Post-it Dependency Sorting Board
Simulate an unsorted wall of task notes, then sort them horizontally by dependency level and vertically by independent workstream. The table underneath keeps the result database-ready for later critical-path calculations.
1) Unsorted post-it pile — copied from current work packages
2.2 Cut back all the foliage 2 weeks |  | 3.1 Check funds 1 week |  | 3.3.1 Buy furniture 2 weeks |  | 1.2 Apply for and get planning permission 10 weeks
4.4 Level the base 1 week |  | 3.2.3 Get quotes 3 weeks |  | 4.2 Dig foundation trenches 1 week |  | 2.4 Put a power wire down the garden ? weeks
5.3.1 Inside 1 week |  | 3.2.5 Choose - place the order ? weeks |  | 5.1 Delivery 6 weeks |  | 2.3 Tree surgeon to trim branches above area ? weeks
6.1 Install Furniture 1 week |  | 3.2.1 Research - talk to friends 3 weeks |  | 6.3 Set up music system 1 week |  | 4.1 Hire Digger 2 weeks
1.1 Check can I get planning? 6 weeks |  | 5.3.2 External 2 weeks |  | 3.2.4 See a finished one 1 week |  | 6.2 Set up computers 1 week
3.2.2 Find shed suppliers 1 week |  | 4.3 Fill with concrete 2 weeks |  | 2.1 Demolish old shed 1 week |  | 5.2 Assembly 1 week
2.5 Connect power ? weeks |  | 3.2.6 Wait for delivery 6 weeks
2) Sorted board — horizontal = dependency level, vertical = independent lane
Lane | Level 0 | Level 1 | Level 2 | Level 3 | Level 4 | Level 5+
01 Planning / approvals | 1.1 Check can I get planning? Dur: 6w | 1.2 Apply for and get planning permission Dur: 10w
02 Site preparation | 2.1 Demolish old shed Dur: 1w ———— 2.2 Cut back all the foliage Dur: 2w ———— 2.3 Tree surgeon to trim branches above area Dur: ?w ———— 2.4 Put a power wire down the garden Dur: ?w | 2.5 Connect power Dur: ?w
03 Buying / supplier choice | 3.1 Check funds Dur: 1w ———— 3.2.1 Research - talk to friends Dur: 3w ———— 3.2.2 Find shed suppliers Dur: 1w ———— 3.2.3 Get quotes Dur: 3w ———— 3.2.4 See a finished one Dur: 1w | 3.2.5 Choose - place the order Dur: ?w | 3.2.6 Wait for delivery Dur: 6w
04 Foundations | 4.1 Hire Digger Dur: 2w | 4.2 Dig foundation trenches Dur: 1w | 4.3 Fill with concrete Dur: 2w | 4.4 Level the base Dur: 1w
05 Build / finish | 5.3.1 Inside Dur: 1w ———— 5.3.2 External Dur: 2w |  |  |  | 5.1 Delivery Dur: 6w | 5.2 Assembly Dur: 1w
06 Utilities / fit-out | [5 empty] | 6.1 Install Furniture Dur: 1w ———— 6.2 Set up computers Dur: 1w ———— 6.3 Set up music system Dur: 1w
3) Database-ready task positions — edit Lane, SuggestedPredecessorWBS, or DurationWeeks here
ProjectID | WBSCode | TaskName | TaskGroup | PostItOrder | Lane | DurationWeeks | SuggestedPredecessorWBS | DependencyLevel | EarliestStart | EarliestFinish | PostItText | CPMReadyFlag
PRJ-001 | 1.1 | Check can I get planning? | Planning | 17 | 01 Planning / approvals | 6 |  | 0 | 0 | 6 | 1.1 Check can I get planning? Dur: 6w | Start candidate
PRJ-001 | 1.2 | Apply for and get planning permission | Planning | 4 | 01 Planning / approvals | 10 | 1.1 | 1 | 6 | 16 | 1.2 Apply for and get planning permission Dur: 10w | Ready
PRJ-001 | 2.1 | Demolish old shed | Prepare site | 23 | 02 Site preparation | 1 |  | 0 | 0 | 1 | 2.1 Demolish old shed Dur: 1w | Start candidate
PRJ-001 | 2.2 | Cut back all the foliage | Prepare site | 1 | 02 Site preparation | 2 |  | 0 | 0 | 2 | 2.2 Cut back all the foliage Dur: 2w | Start candidate
PRJ-001 | 2.3 | Tree surgeon to trim branches above area | Prepare site | 12 | 02 Site preparation |  |  | 0 | 0 | 1 | 2.3 Tree surgeon to trim branches above area Dur: ?w | Add duration
PRJ-001 | 2.4 | Put a power wire down the garden | Prepare site | 8 | 02 Site preparation |  |  | 0 | 0 | 1 | 2.4 Put a power wire down the garden Dur: ?w | Add duration
PRJ-001 | 2.5 | Connect power | Prepare site | 25 | 02 Site preparation |  | 2.4 | 1 | 1 | 2 | 2.5 Connect power Dur: ?w | Add duration
PRJ-001 | 3.1 | Check funds | Buying | 2 | 03 Buying / supplier choice | 1 |  | 0 | 0 | 1 | 3.1 Check funds Dur: 1w | Start candidate
PRJ-001 | 3.2.1 | Research - talk to friends | Shed | 14 | 03 Buying / supplier choice | 3 |  | 0 | 0 | 3 | 3.2.1 Research - talk to friends Dur: 3w | Start candidate
PRJ-001 | 3.2.2 | Find shed suppliers | Shed | 21 | 03 Buying / supplier choice | 1 |  | 0 | 0 | 1 | 3.2.2 Find shed suppliers Dur: 1w | Start candidate
PRJ-001 | 3.2.3 | Get quotes | Shed | 6 | 03 Buying / supplier choice | 3 |  | 0 | 0 | 3 | 3.2.3 Get quotes Dur: 3w | Start candidate
PRJ-001 | 3.2.4 | See a finished one | Shed | 19 | 03 Buying / supplier choice | 1 |  | 0 | 0 | 1 | 3.2.4 See a finished one Dur: 1w | Start candidate
PRJ-001 | 3.2.5 | Choose - place the order | Shed | 10 | 03 Buying / supplier choice |  | 3.2.2 | 1 | 1 | 2 | 3.2.5 Choose - place the order Dur: ?w | Add duration
PRJ-001 | 3.2.6 | Wait for delivery | Shed | 26 | 03 Buying / supplier choice | 6 | 3.2.5 | 2 | 2 | 8 | 3.2.6 Wait for delivery Dur: 6w | Ready
PRJ-001 | 3.3.1 | Buy furniture | Other stuff | 3 | 07 Other independent stream | 2 |  | 0 | 0 | 2 | 3.3.1 Buy furniture Dur: 2w | Start candidate
PRJ-001 | 4.1 | Hire Digger | Foundations | 16 | 04 Foundations | 2 |  | 0 | 0 | 2 | 4.1 Hire Digger Dur: 2w | Start candidate
PRJ-001 | 4.2 | Dig foundation trenches | Foundations | 7 | 04 Foundations | 1 | 4.1 | 1 | 2 | 3 | 4.2 Dig foundation trenches Dur: 1w | Ready
PRJ-001 | 4.3 | Fill with concrete | Foundations | 22 | 04 Foundations | 2 | 4.2 | 2 | 3 | 5 | 4.3 Fill with concrete Dur: 2w | Ready
PRJ-001 | 4.4 | Level the base | Foundations | 5 | 04 Foundations | 1 | 4.3 | 3 | 5 | 6 | 4.4 Level the base Dur: 1w | Ready
PRJ-001 | 5.1 | Delivery | Assembly of structure | 11 | 05 Build / finish | 6 | 4.4 | 4 | 6 | 12 | 5.1 Delivery Dur: 6w | Ready
PRJ-001 | 5.2 | Assembly | Assembly of structure | 24 | 05 Build / finish | 1 | 5.1 | 5 | 12 | 13 | 5.2 Assembly Dur: 1w | Ready
PRJ-001 | 5.3.1 | Inside | Painting | 9 | 05 Build / finish | 1 |  | 0 | 0 | 1 | 5.3.1 Inside Dur: 1w | Start candidate
PRJ-001 | 5.3.2 | External | Painting | 18 | 05 Build / finish | 2 |  | 0 | 0 | 2 | 5.3.2 External Dur: 2w | Start candidate
PRJ-001 | 6.1 | Install Furniture | Installing stuff | 13 | 06 Utilities / fit-out | 1 | 5.2 | 5 | 13 | 14 | 6.1 Install Furniture Dur: 1w | Ready
PRJ-001 | 6.2 | Set up computers | Installing stuff | 20 | 06 Utilities / fit-out | 1 | 6.1 | 5 | 14 | 15 | 6.2 Set up computers Dur: 1w | Ready
PRJ-001 | 6.3 | Set up music system | Installing stuff | 15 | 06 Utilities / fit-out | 1 | 6.2 | 5 | 15 | 16 | 6.3 Set up music system Dur: 1w | Ready
4) Normalized dependency edge list — this is the structure to use for true critical-path analysis
ProjectID | FromWBSCode | ToWBSCode | DependencyType | LagWeeks | RelationshipNote
PRJ-001 | 1.1 | 1.2 | Finish-to-Start | 0 | Planning permission application follows initial planning check
PRJ-001 | 2.4 | 2.5 | Finish-to-Start | 0 | Power wire must be in place before connection
PRJ-001 | 3.2.2 | 3.2.5 | Finish-to-Start | 0 | Choose supplier after identifying suppliers
PRJ-001 | 3.2.5 | 3.2.6 | Finish-to-Start | 0 | Delivery time follows supplier choice
PRJ-001 | 4.1 | 4.2 | Finish-to-Start | 0 | Dig trench before using digger step is confirmed
PRJ-001 | 4.2 | 4.3 | Finish-to-Start | 0 | Digger/trench work before concrete
PRJ-001 | 4.3 | 4.4 | Finish-to-Start | 0 | Concrete before levelling base
PRJ-001 | 4.4 | 5.1 | Finish-to-Start | 0 | Base ready before assembly
PRJ-001 | 5.1 | 5.2 | Finish-to-Start | 0 | Furniture after structure
PRJ-001 | 5.2 | 6.1 | Finish-to-Start | 0 | Fit-out can depend on interior readiness
PRJ-001 | 2.5 | 6.1 | Finish-to-Start | 0 | Electrical install also depends on power connection