## Project Init
PROJECT INITIATION DOCUMENT | 1 | BUSINESS CASE | 2 | PROJECT SCOPE | < Cost, Quality or Time? > | Identify Driver | > Step 1 - Define the project
|  | <Insert the Business Case if you have one. > |  | 2.1. In Scope / Included in the Project |  |  | > Step 2 - List the tasks ¦ Level of granularity
PROJECT NAME: |  | • Why this project |  | 2.2. Out of Scope / Excluded from the Project |  |  | > Step 3 - Establishing task order
PROJECT NUMBER: |  | • Why now? |  | 2.3. Dependencies |  |  | > Step 4 - Estimating time
PROJECT RISK LEVEL: H/M/L |  | • Options considered |  | <Describe how the project impacts or will be impacted by other projects or programmes > |  |  | > Step 5 - Margin check & reality check
Prepared by: |  | • What if we don’t do it? |  |  |  |  | > Step 6 - Gantt Chart
Date: |  | • Benefits |  | 2.4. Constraints |  |  | > Step 7 - Resource allocation
Persons consulted: |  | • Payback period |  | <Describe any constraints within which the project must be delivered, e.g. government deadlines; |  |  | > Step 8 - Predicting & reducing risk
|  |  |  | budget limits; resource limitations. > |  |  | > Step 9 - Monitoring progress
KEY ACTIONS PROPOSED TO DELIVER THE PROJECT |  |  |  | 2.5. Assumptions |  |  | > Step 10 - Monitoring cost
You MUST Include a high-level or detailed Gantt chart |  |  |  | < Describe any assumptions that are being worked from at this point (for example, that you will |  |  | > Step 11 - Adjusting the plan
Communications Plan |  |  |  | get planning permission). > |  |  | > Step 12 - Review & lessons
What |  |  |  | 2.6 – What’s the key driver of your project, and why do you think that?
How
Who |  |  |  | Project Initiation Document
Version <version no. > |  |  |  | 3.1. Quality Plan
When |  |  |  | <Describe how it is intended to meet, and shown to meet, the customer’s quality expectations >
Cost |  |  |  | 4. PROJECT CONTROLS AND REPORTING
< Describe how progress will be reported to the Project Board if there is one. >
Task Acceptance Criteria |  |  |  | 5. RISK CONTROL
Frequency / timing |  |  |  | <Attach a risk chart, or for small, low-risk projects, insert below in this document. >
(monthly, stage end, etc) |  |  |  | 6. FINANCIAL IMPLICATIONS
How will the Control be reported Responsibility for |  |  |  | I have considered the benefits against the project costs and assessed the project plan
production
Project Risk Containment Measures |  |  |  | RISKS:
Q1 Q2 Q3 Q4 Total |  |  |  | How likely?
Amount Year 1 |  |  |  | How serious?
Amount Year 2
Amount Year 3
Amount Year 4
Amount Year 5

## tblTaskList
Task ID | Task Name | Resource | IsInCriticalPath | Predecessor Tasks | Duration (Weeks) | Progress | Hours | Cost | Actual Cost | Start wk | Finish wk | Project | Budget | Start Date | total hours | total cost | ActCost | Diff
2 | Planning permission | FE | Yes | Wait for planning permission | 6 | 100% |  |  |  | 1 | 6 | New Garden Shed | 20000 | 01.06.2026 | 70 | 18800 | 19450 | -650
3 | Wait for planning permission | FE | Yes | Hire digger | 10 | 20% |  | 100 | 100 | 7 | 16
6 | Dig trench | NN | Yes | Wire down the garden | 1 | 0% | 4 | 350 | 400 | 17 | 17
7 | Hire digger | FE | Yes | Dig trench | 2 | 0% |  |  |  | 18 | 19
9 | Fill with concrete | NN | Yes | Level the base | 1 | 0% | 3 | 700 | 800 | 20 | 20
10 | Level the base | NN | Yes | Assembly | 1 | 0% | 5 | 100 | 100 | 21 | 21
17 | the Finish | FE | Yes |  | 4 | 0% | 34 | 8000 | 8500 | 22 | 25
19 | Delivery | NN | Yes | Wait for Delivery | 0 | 0% |  |  |  | 22 | 22
1 | Check funds | FE | Float | Demolish old shed | 0 | 100% |  |  |  | 2 | 2
4 | Demolish old shed | NN | Float | Cut foliage back | 1 | 0% | 6 | 300 | 300 | 3 | 3 | [7 empty] | Critical
5 | Cut foliage back | NN | Float | Dig trench | 4 | 0% | 10 | 500 | 500 | 8 | 11 | [7 empty] | Path
8 | Connect Power | NN | Float | the Finish |  | 0% |  |  |  | 13 | 13 | [7 empty] | (Weeks)
11 | Find suppliers | FE | Float | Get quotes | 1 | 100% |  |  |  | 4 | 4 | [7 empty] | 26
12 | Get quotes | FE | Float | Buy the shed | 3 | 0% |  |  |  | 7 | 9
13 | Buy the shed | FE | Float |  | 0 | 0% |  | 8000 | 8000 | 8 | 8
14 | Wait for Delivery | FE | Float | Assembly | 6 | 0% |  |  |  | 7 | 12
15 | Wire down the garden | NN | Float | Connect Power | 1 | 0% | 8 |  |  | 22 | 22
16 | Assembly | NN | Float |  | 1 | 0% |  | 750 | 750 | 23 | 23
Start with Running Order Regardless of Time => Then Estimate Time for Each Task (Independently of Running Order)
Critical Path => The Longest Path
[12 empty] | Parallell Floaters | What comes Before/After?
Safety Margin -> Add /Blend into Critical Path (50% of worst case =>90% Reliable)
Time Down => Money Up or Quality Down ¦ Overlapping Tasks
Demolish Old Shed 1wk
Check funds
Planning Perm 6 wk
Wait Perm 10wk
Cutfoliage back 4 wk
Hire Digger 2wk
Dig Trench 1 wk
Fill Concret 2 wk
Level Base 1 wk
Wire Down Garden 1 wk
Connect Power
Reasearh 3wk
Find Supplier 1wk
Get Quotes 4wk
Wait for Delivery 6wk
Assembly 1wk
Finish 4 wk

## MS VISIO
MS Visio Task Table Template
A Visio-ready project table linked to tblTaskList: each row can become a process/task shape, with dependency text available for connectors.
Story in Brief: this template converts the current New Garden Shed task plan into a Visio-style shape list. Critical-path tasks are tagged separately from float tasks, progress is classified into statuses, and each task carries the key fields Visio usually needs: shape ID, shape type, task label, owner, dependency, timing, progress, and import notes.
Project | Budget | Total Cost | Actual Cost | Variance
New Garden Shed | 20000 | 18800 | 19450 | -650
Shape ID | Visio Shape Type | Task Label | Owner | Dependency / Connector From | Duration | Start Wk | Finish Wk | Progress | Import Notes
TASK-02 | Critical Process | Planning permission | FE | Wait for planning permission | 6 | 1 | 6 | 100% | Completed ¦ Cost 0
TASK-03 | Critical Process | Wait for planning permission | FE | Hire digger | 10 | 7 | 16 | 20% | In progress ¦ Cost 100
TASK-06 | Critical Process | Dig trench | NN | Wire down the garden | 1 | 17 | 17 | 0% | Not started ¦ Cost 350
TASK-07 | Critical Process | Hire digger | FE | Dig trench | 2 | 18 | 19 | 0% | Not started ¦ Cost 0
TASK-09 | Critical Process | Fill with concrete | NN | Level the base | 1 | 20 | 20 | 0% | Not started ¦ Cost 700
TASK-10 | Critical Process | Level the base | NN | Assembly | 1 | 21 | 21 | 0% | Not started ¦ Cost 100
TASK-17 | Critical Process | the Finish | FE | 0 | 4 | 22 | 25 | 0% | Not started ¦ Cost 8,000
TASK-19 | Critical Process | Delivery | NN | Wait for Delivery | 0 | 22 | 22 | 0% | Not started ¦ Cost 0
TASK-01 | Floating Process | Check funds | FE | Demolish old shed | 0 | 2 | 2 | 100% | Completed ¦ Cost 0
TASK-04 | Floating Process | Demolish old shed | NN | Cut foliage back | 1 | 3 | 3 | 0% | Not started ¦ Cost 300
TASK-05 | Floating Process | Cut foliage back | NN | Dig trench | 4 | 8 | 11 | 0% | Not started ¦ Cost 500
TASK-08 | Floating Process | Connect Power | NN | the Finish | 0 | 13 | 13 | 0% | Not started ¦ Cost 0
TASK-11 | Floating Process | Find suppliers | FE | Get quotes | 1 | 4 | 4 | 100% | Completed ¦ Cost 0
TASK-12 | Floating Process | Get quotes | FE | Buy the shed | 3 | 7 | 9 | 0% | Not started ¦ Cost 0
TASK-13 | Floating Process | Buy the shed | FE | 0 | 0 | 8 | 8 | 0% | Not started ¦ Cost 8,000
TASK-14 | Floating Process | Wait for Delivery | FE | Assembly | 6 | 7 | 12 | 0% | Not started ¦ Cost 0
TASK-15 | Floating Process | Wire down the garden | NN | Connect Power | 1 | 22 | 22 | 0% | Not started ¦ Cost 0
TASK-16 | Floating Process | Assembly | NN | 0 | 1 | 23 | 23 | 0% | Not started ¦ Cost 750
VISIO FIELD MAPPING
Template Field | Use in Visio | Suggested Visio Target | Example |  | VISIO APPROACH
Shape ID | Unique identifier for each Visio shape | Shape Data: ID | TASK-02 |  | 1 | Import table rows as shapes.
Visio Shape Type | Selects stencil / visual style | Shape master or Data Graphic | Critical Process |  | 2 | Use Shape ID as the unique key.
Task Label | Text displayed inside the shape | Shape text | Planning permission |  | 3 | Use Dependency / Connector From to draw connectors.
Dependency / Connector From | Connector source task | Connector begin / predecessor | Wait for planning permission |  | 4 | Apply Critical Process formatting to critical-path tasks.
Progress | Data graphic / status icon | Shape Data: Progress | 20% |  | 5 | Use Progress to show status icons or data bars.

## Swimlane Diagram
Horizontal Swimlane Diagram — MS Visio Style
A compact visual mock-up of how the current project plan could look in Visio: lanes are resources, the horizontal axis is project week, and each coloured block is a task.
Story in Brief: the plan runs from week 1 to week 26. FE owns planning, procurement, waiting, and finish activities, while NN owns site preparation, base work, wiring, delivery, and assembly. Critical-path tasks are shown in blue; float tasks are shown in amber; completed or in-progress items display their progress percentage inside the block.
Lane | Meaning | Colour | Use
FE | Frank / project owner lane | Blue or amber task blocks | Planning, procurement, finish
NN | Execution / installer lane | Blue or amber task blocks | Site work, base, assembly
Critical | On critical path | #1F4E78 | Prioritise for time control
Float | Parallel / non-critical | #F4B183 | Can move if resources change
Lane | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
FE | Planning permission 100% ¦ Yes
Check funds 100% ¦ Float
Find suppliers 100% ¦ Float
Get quotes 0% ¦ Float
Wait for Delivery 0% ¦ Float
Wait for planning permission 20% ¦ Yes
Buy the shed 0% ¦ Float
Hire digger 0% ¦ Yes
the Finish 0% ¦ Yes
NN |  |  | Demolish old shed 0% ¦ Float
Cut foliage back 0% ¦ Float
Connect Power 0% ¦ Float
Dig trench 0% ¦ Yes
Fill with concrete 0% ¦ Yes
Level the base 0% ¦ Yes
Delivery 0% ¦ Yes
Wire down the garden 0% ¦ Float
Assembly 0% ¦ Float
VISIO INTERPRETATION NOTES
In Visio, each coloured block would be a process/task shape. The lane bands become horizontal swimlanes. Dependencies from tblTaskList can be converted into dynamic connectors between shapes; this Excel mock-up focuses on the visual layout and timing rather than drawing connector arrows.