## Project Init
PROJECT INITIATION DOCUMENT | 1 | BUSINESS CASE | 2 | PROJECT SCOPE | < Cost, Quality or Time? > | Identify Driver | > Step 1 - Define the project
|  | <Insert the Business Case if you have one. > |  | 2.1. In Scope / Included in the Project |  |  | > Step 2 - List the tasks ¦ Level of granularity
PROJECT NAME: |  | • Why this project |  | 2.2. Out of Scope / Excluded from the Project |  |  | > Step 3 - Establishing task order
PROJECT NUMBER: |  | • Why now? |  | 2.3. Dependencies |  |  | > Step 4 - Estimating time
PROJECT RISK LEVEL: H/M/L |  | • Options considered |  | <Describe how the project impacts or will be impacted by other projects or programmes > |  |  | > Step 5 - Margin check & reality check
Prepared by: |  | • What if we don’t do it? |  |  |  |  | > Step 6 - Gantt Chart
Date: |  | • Benefits |  | 2.4. Constraints |  |  | > Step 7 - Resource allocation
Persons consulted: |  | • Payback period |  | <Describe any constraints within which the project must be delivered, e.g. government deadlines; |  |  | > Step 8 - Predicting & reducing risk
|  |  |  | budget limits; resource limitations. > |  |  | > Step 9 - Monitoring progress
KEY ACTIONS PROPOSED TO DELIVER THE PROJECT |  |  |  | 2.5. Assumptions |  |  | > Step 10 - Monitoring cost
You MUST Include a high-level or detailed Gantt chart |  |  |  | < Describe any assumptions that are being worked from at this point (for example, that you will |  |  | > Step 11 - Adjusting the plan
Communications Plan |  |  |  | get planning permission). > |  |  | > Step 12 - Review & lessons
What |  |  |  | 2.6 – What’s the key driver of your project, and why do you think that?
How
Who |  |  |  | Project Initiation Document
Version <version no. > |  |  |  | 3.1. Quality Plan
When |  |  |  | <Describe how it is intended to meet, and shown to meet, the customer’s quality expectations >
Cost |  |  |  | 4. PROJECT CONTROLS AND REPORTING
< Describe how progress will be reported to the Project Board if there is one. >
Task Acceptance Criteria |  |  |  | 5. RISK CONTROL
Frequency / timing |  |  |  | <Attach a risk chart, or for small, low-risk projects, insert below in this document. >
(monthly, stage end, etc) |  |  |  | 6. FINANCIAL IMPLICATIONS
How will the Control be reported Responsibility for |  |  |  | I have considered the benefits against the project costs and assessed the project plan
production
Project Risk Containment Measures |  |  |  | RISKS:
Q1 Q2 Q3 Q4 Total |  |  |  | How likely?
Amount Year 1 |  |  |  | How serious?
Amount Year 2
Amount Year 3
Amount Year 4
Amount Year 5

## tblTaskList
Task ID | Task Name | Resource | IsInCriticalPath | Predecessor Tasks | Duration (Weeks) | Progress | Hours | Cost | Actual Cost | Start wk | Finish wk | Project | Budget | Start Date | total hours | total cost | ActCost | Diff
2 | Planning permission | FE | Yes | Wait for planning permission | 6 | 100% |  |  |  | 1 | 6 | New Garden Shed | 20000 | 01.06.2026 | 70 | 18800 | 19450 | -650
3 | Wait for planning permission | FE | Yes | Hire digger | 10 | 20% |  | 100 | 100 | 7 | 16
6 | Dig trench | NN | Yes | Wire down the garden | 1 | 0% | 4 | 350 | 400 | 17 | 17
7 | Hire digger | FE | Yes | Dig trench | 2 | 0% |  |  |  | 18 | 19
9 | Fill with concrete | NN | Yes | Level the base | 1 | 0% | 3 | 700 | 800 | 20 | 20
10 | Level the base | NN | Yes | Assembly | 1 | 0% | 5 | 100 | 100 | 21 | 21
17 | the Finish | FE | Yes |  | 4 | 0% | 34 | 8000 | 8500 | 22 | 25
19 | Delivery | NN | Yes | Wait for Delivery | 0 | 0% |  |  |  | 22 | 22
1 | Check funds | FE | Float | Demolish old shed | 0 | 100% |  |  |  | 2 | 2
4 | Demolish old shed | NN | Float | Cut foliage back | 1 | 0% | 6 | 300 | 300 | 3 | 3 | [7 empty] | Critical
5 | Cut foliage back | NN | Float | Dig trench | 4 | 0% | 10 | 500 | 500 | 8 | 11 | [7 empty] | Path
8 | Connect Power | NN | Float | the Finish |  | 0% |  |  |  | 13 | 13 | [7 empty] | (Weeks)
11 | Find suppliers | FE | Float | Get quotes | 1 | 100% |  |  |  | 4 | 4 | [7 empty] | 26
12 | Get quotes | FE | Float | Buy the shed | 3 | 0% |  |  |  | 7 | 9
13 | Buy the shed | FE | Float |  | 0 | 0% |  | 8000 | 8000 | 8 | 8
14 | Wait for Delivery | FE | Float | Assembly | 6 | 0% |  |  |  | 7 | 12
15 | Wire down the garden | NN | Float | Connect Power | 1 | 0% | 8 |  |  | 22 | 22
16 | Assembly | NN | Float |  | 1 | 0% |  | 750 | 750 | 23 | 23
Start with Running Order Regardless of Time => Then Estimate Time for Each Task (Independently of Running Order)
Critical Path => The Longest Path
[12 empty] | Parallell Floaters | What comes Before/After?
Safety Margin -> Add /Blend into Critical Path (50% of worst case =>90% Reliable)
Time Down => Money Up or Quality Down ¦ Overlapping Tasks
Demolish Old Shed 1wk
Check funds
Planning Perm 6 wk
Wait Perm 10wk
Cutfoliage back 4 wk
Hire Digger 2wk
Dig Trench 1 wk
Fill Concret 2 wk
Level Base 1 wk
Wire Down Garden 1 wk
Connect Power
Reasearh 3wk
Find Supplier 1wk
Get Quotes 4wk
Wait for Delivery 6wk
Assembly 1wk
Finish 4 wk

## Gantt-frame
New Garden Shed | [8 empty] | Hours | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 5 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Today | 2026-08-06 | 32 |  |  | Cost | 0 | 0 | 300 | 0 | 0 | 0 | 100 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 700 | 100 | 8000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Start | 01.06.2026 | 1 | time axis 2026-06-08 to 2027-05-31
|  |  |  | Finish | 2026-11-30 | 26 |  | 70 | 18800 | time axis 2026-06-08 to 2027-05-31
critical path | duration (wk) | Progress | Actual wk | TASK | Resource | Start wk | Finish wk | Hours | Cost | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Yes | 6 | 100% | 6 | Planning permission | FE | 1 | 6 | 0 | 0 | bar: 2026-07-13
Yes | 10 | 20% | 8 | Wait for planning permission | FE | 7 | 16 | 0 | 100 | bar: 2026-07-27
Yes | 1 | 0% | 0 | Dig trench | NN | 17 | 17 | 4 | 350
Yes | 2 | 0% | 0 | Hire digger | FE | 18 | 19 | 0 | 0
Yes | 1 | 0% | 0 | Fill with concrete | NN | 20 | 20 | 3 | 700
Yes | 1 | 0% | 0 | Level the base | NN | 21 | 21 | 5 | 100
Yes | 4 | 0% | 0 | the Finish | FE | 22 | 25 | 34 | 8000
Yes | 0 | 0% | 0 | Delivery | NN | 22 | 22 | 0 | 0
Float | 0 | 100% | 2 | Check funds | FE | 2 | 2 | 0 | 0 | bar: 2026-06-15
Float | 1 | 0% | 0 | Demolish old shed | NN | 3 | 3 | 6 | 300
Float | 4 | 0% | 0 | Cut foliage back | NN | 8 | 11 | 10 | 500
Float | 0 | 0% | 0 | Connect Power | NN | 13 | 13 | 0 | 0
Float | 1 | 100% | 4 | Find suppliers | FE | 4 | 4 | 0 | 0 | bar: 2026-06-29
Float | 3 | 0% | 0 | Get quotes | FE | 7 | 9 | 0 | 0
Float | 0 | 0% | 0 | Buy the shed | FE | 8 | 8 | 0 | 8000
Float | 6 | 0% | 0 | Wait for Delivery | FE | 7 | 12 | 0 | 0
Float | 1 | 0% | 0 | Wire down the garden | NN | 22 | 22 | 8 | 0
Float | 1 | 0% | 0 | Assembly | NN | 23 | 23 | 0 | 750
● Actual progress marker
Demolish Old Shed 1wk
Check funds
Planning Perm 6 wk
Wait Perm 10wk
Cutfoliage back 4 wk
Hire Digger 2wk
Dig Trench 1 wk
Fill Concret 2 wk
Level Base 1 wk
Wire Down Garden 1 wk
Connect Power
Reasearh 3wk
Find Supplier 1wk
Get Quotes 4wk
Wait for Delivery 6wk
Assembly 1wk
Finish 4 wk

## EVM
Budget | Actual | Forcast Act at Completion