## Project Init
PROJECT INITIATION DOCUMENT | 1 | BUSINESS CASE | 2 | PROJECT SCOPE | < Cost, Quality or Time? > | Identify Driver | > Step 1 - Define the project
|  | <Insert the Business Case if you have one. > |  | 2.1. In Scope / Included in the Project |  |  | > Step 2 - List the tasks ¦ Level of granularity
PROJECT NAME: |  | • Why this project |  | 2.2. Out of Scope / Excluded from the Project |  |  | > Step 3 - Establishing task order
PROJECT NUMBER: |  | • Why now? |  | 2.3. Dependencies |  |  | > Step 4 - Estimating time
PROJECT RISK LEVEL: H/M/L |  | • Options considered |  | <Describe how the project impacts or will be impacted by other projects or programmes > |  |  | > Step 5 - Margin check & reality check
Prepared by: |  | • What if we don’t do it? |  |  |  |  | > Step 6 - Gantt Chart
Date: |  | • Benefits |  | 2.4. Constraints |  |  | > Step 7 - Resource allocation
Persons consulted: |  | • Payback period |  | <Describe any constraints within which the project must be delivered, e.g. government deadlines; |  |  | > Step 8 - Predicting & reducing risk
|  |  |  | budget limits; resource limitations. > |  |  | > Step 9 - Monitoring progress
KEY ACTIONS PROPOSED TO DELIVER THE PROJECT |  |  |  | 2.5. Assumptions |  |  | > Step 10 - Monitoring cost
You MUST Include a high-level or detailed Gantt chart |  |  |  | < Describe any assumptions that are being worked from at this point (for example, that you will |  |  | > Step 11 - Adjusting the plan
Communications Plan |  |  |  | get planning permission). > |  |  | > Step 12 - Review & lessons
What |  |  |  | 2.6 – What’s the key driver of your project, and why do you think that?
How
Who |  |  |  | Project Initiation Document
Version <version no. > |  |  |  | 3.1. Quality Plan
When |  |  |  | <Describe how it is intended to meet, and shown to meet, the customer’s quality expectations >
Cost |  |  |  | 4. PROJECT CONTROLS AND REPORTING
< Describe how progress will be reported to the Project Board if there is one. >
Task Acceptance Criteria |  |  |  | 5. RISK CONTROL
Frequency / timing |  |  |  | <Attach a risk chart, or for small, low-risk projects, insert below in this document. >
(monthly, stage end, etc) |  |  |  | 6. FINANCIAL IMPLICATIONS
How will the Control be reported Responsibility for |  |  |  | I have considered the benefits against the project costs and assessed the project plan
production
Project Risk Containment Measures |  |  |  | RISKS:
Q1 Q2 Q3 Q4 Total |  |  |  | How likely?
Amount Year 1 |  |  |  | How serious?
Amount Year 2 |  |  |  | What impact?
Amount Year 3
Amount Year 4
Amount Year 5

## tblTaskList
Task ID | Task Name | Resource | IsInCriticalPath | Predecessor Tasks | Duration (Weeks) | Progress | Hours | Cost | Actual Cost | Start wk | Finish wk | Project | Budget | Start Date | total hours | total cost | ActCost | Diff
2 | Planning permission | FE | Yes | Wait for planning permission | 6 | 100% |  |  |  | 1 | 6 | New Garden Shed | 20000 | 01.06.2026 | 70 | 18800 | 19450 | -650
3 | Wait for planning permission | FE | Yes | Hire digger | 10 | 20% |  | 100 | 100 | 7 | 16
6 | Dig trench | NN | Yes | Wire down the garden | 1 | 0% | 4 | 350 | 400 | 17 | 17
7 | Hire digger | FE | Yes | Dig trench | 2 | 0% |  |  |  | 18 | 19
9 | Fill with concrete | NN | Yes | Level the base | 1 | 0% | 3 | 700 | 800 | 20 | 20
10 | Level the base | NN | Yes | Assembly | 1 | 0% | 5 | 100 | 100 | 21 | 21
17 | the Finish | FE | Yes |  | 4 | 0% | 34 | 8000 | 8500 | 22 | 25
19 | Delivery | NN | Yes | Wait for Delivery | 0 | 0% |  |  |  | 22 | 22
1 | Check funds | FE | Float | Demolish old shed | 0 | 100% |  |  |  | 2 | 2
4 | Demolish old shed | NN | Float | Cut foliage back | 1 | 0% | 6 | 300 | 300 | 3 | 3 | [7 empty] | Critical
5 | Cut foliage back | NN | Float | Dig trench | 4 | 0% | 10 | 500 | 500 | 8 | 11 | [7 empty] | Path
8 | Connect Power | NN | Float | the Finish |  | 0% |  |  |  | 13 | 13 | [7 empty] | (Weeks)
11 | Find suppliers | FE | Float | Get quotes | 1 | 100% |  |  |  | 4 | 4 | [7 empty] | 26
12 | Get quotes | FE | Float | Buy the shed | 3 | 0% |  |  |  | 7 | 9
13 | Buy the shed | FE | Float |  | 0 | 0% |  | 8000 | 8000 | 8 | 8
14 | Wait for Delivery | FE | Float | Assembly | 6 | 0% |  |  |  | 7 | 12
15 | Wire down the garden | NN | Float | Connect Power | 1 | 0% | 8 |  |  | 22 | 22
16 | Assembly | NN | Float |  | 1 | 0% |  | 750 | 750 | 23 | 23
Start with Running Order Regardless of Time => Then Estimate Time for Each Task (Independently of Running Order)
Critical Path => The Longest Path
[12 empty] | Parallell Floaters | What comes Before/After?
Safety Margin -> Add /Blend into Critical Path (50% of worst case =>90% Reliable)
Time Down => Money Up or Quality Down ¦ Overlapping Tasks
Demolish Old Shed 1wk
Check funds
Planning Perm 6 wk
Wait Perm 10wk
Cutfoliage back 4 wk
Hire Digger 2wk
Dig Trench 1 wk
Fill Concret 2 wk
Level Base 1 wk
Wire Down Garden 1 wk
Connect Power
Reasearh 3wk
Find Supplier 1wk
Get Quotes 4wk
Wait for Delivery 6wk
Assembly 1wk
Finish 4 wk

## EVM Data
EVM Data Model — Required Task-Level Reporting Table
Modeled from tblTaskList. Fill the yellow input columns where blank; calculated EVM columns update automatically from those inputs and the status week.
Project | New Garden Shed |  | Metric | Formula | Value |  | Metric | Formula | Value |  | Metric | Formula | Value |  | How to complete
Status week | 32 |  | Total EV | SUM(tblEVMData[Earned Value]) | 20 |  | SV | EV - PV | -18780 |  | EAC | BAC / CPI | 18283000 |  | 1. Fill yellow columns if blank: Baseline Cost, Actual Cost, Hours, Actual % Complete.
Status date | 46240 |  | Total PV | SUM(tblEVMData[Planned Value]) | 18800 |  | CV | EV - AC | -19430 |  | ETC | EAC - AC | 18263550
Budget at Completion | 18800 |  | Total AC | SUM(tblEVMData[Actual Cost]) | 19450 |  | SPI | EV / PV | 0.0010638 |  | VAC | BAC - EAC | -18264200
[7 empty] | CPI | EV / AC | 0.0010283 |  | TCPI | (BAC-EV)/(BAC-AC) | -28.8923
Task ID | Task Name | Resource | Critical Path | Predecessor Tasks | Start wk | Finish wk | Duration (Weeks) | Baseline Cost | Actual Cost | Hours | Actual % Complete | Planned % Complete | Earned Value | Planned Value | Schedule Variance | Cost Variance | SPI | CPI | Data Gap / Action Needed
2 | Planning permission | FE | Yes | Wait for planning permission | 1 | 6 | 6 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | 0
3 | Wait for planning permission | FE | Yes | Hire digger | 7 | 16 | 10 | 100 | 100 | 0 | 20% | 100% | 20 | 100 | -80 | -80 | 0.2 | 0.2
6 | Dig trench | NN | Yes | Wire down the garden | 17 | 17 | 1 | 350 | 400 | 4 | 0% | 100% | 0 | 350 | -350 | -400 | 0 | 0
7 | Hire digger | FE | Yes | Dig trench | 18 | 19 | 2 | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0
9 | Fill with concrete | NN | Yes | Level the base | 20 | 20 | 1 | 700 | 800 | 3 | 0% | 100% | 0 | 700 | -700 | -800 | 0 | 0
10 | Level the base | NN | Yes | Assembly | 21 | 21 | 1 | 100 | 100 | 5 | 0% | 100% | 0 | 100 | -100 | -100 | 0 | 0
17 | the Finish | FE | Yes | 0 | 22 | 25 | 4 | 8000 | 8500 | 34 | 0% | 100% | 0 | 8000 | -8000 | -8500 | 0 | 0
19 | Delivery | NN | Yes | Wait for Delivery | 22 | 22 | 0 | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0
1 | Check funds | FE | Float | Demolish old shed | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | 0
4 | Demolish old shed | NN | Float | Cut foliage back | 3 | 3 | 1 | 300 | 300 | 6 | 0% | 100% | 0 | 300 | -300 | -300 | 0 | 0
5 | Cut foliage back | NN | Float | Dig trench | 8 | 11 | 4 | 500 | 500 | 10 | 0% | 100% | 0 | 500 | -500 | -500 | 0 | 0
8 | Connect Power | NN | Float | the Finish | 13 | 13 | 0 | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0
11 | Find suppliers | FE | Float | Get quotes | 4 | 4 | 1 | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | 0
12 | Get quotes | FE | Float | Buy the shed | 7 | 9 | 3 | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0
13 | Buy the shed | FE | Float | 0 | 8 | 8 | 0 | 8000 | 8000 | 0 | 0% | 100% | 0 | 8000 | -8000 | -8000 | 0 | 0
14 | Wait for Delivery | FE | Float | Assembly | 7 | 12 | 6 | 0 | 0 | 0 | 0% | 100% | 0 | 0 | 0 | 0
15 | Wire down the garden | NN | Float | Connect Power | 22 | 22 | 1 | 0 | 0 | 8 | 0% | 100% | 0 | 0 | 0 | 0
16 | Assembly | NN | Float | 0 | 23 | 23 | 1 | 750 | 750 | 0 | 0% | 100% | 0 | 750 | -750 | -750 | 0 | 0

## Gantt-frame
New Garden Shed | [8 empty] | Hours | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 5 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Today | 2026-08-06 | 32 |  |  | Cost | 0 | 0 | 300 | 0 | 0 | 0 | 100 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 700 | 100 | 8000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Start | 01.06.2026 | 1 | time axis 2026-06-08 to 2027-05-31
|  |  |  | Finish | 2026-11-30 | 26 |  | 70 | 18800 | time axis 2026-06-08 to 2027-05-31
critical path | duration (wk) | Progress | Actual wk | TASK | Resource | Start wk | Finish wk | Hours | Cost | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Yes | 6 | 100% | 6 | Planning permission | FE | 1 | 6 | 0 | 0 | bar: 2026-07-13
Yes | 10 | 20% | 8 | Wait for planning permission | FE | 7 | 16 | 0 | 100 | bar: 2026-07-27
Yes | 1 | 0% | 0 | Dig trench | NN | 17 | 17 | 4 | 350
Yes | 2 | 0% | 0 | Hire digger | FE | 18 | 19 | 0 | 0
Yes | 1 | 0% | 0 | Fill with concrete | NN | 20 | 20 | 3 | 700
Yes | 1 | 0% | 0 | Level the base | NN | 21 | 21 | 5 | 100
Yes | 4 | 0% | 0 | the Finish | FE | 22 | 25 | 34 | 8000
Yes | 0 | 0% | 0 | Delivery | NN | 22 | 22 | 0 | 0
Float | 0 | 100% | 2 | Check funds | FE | 2 | 2 | 0 | 0 | bar: 2026-06-15
Float | 1 | 0% | 0 | Demolish old shed | NN | 3 | 3 | 6 | 300
Float | 4 | 0% | 0 | Cut foliage back | NN | 8 | 11 | 10 | 500
Float | 0 | 0% | 0 | Connect Power | NN | 13 | 13 | 0 | 0
Float | 1 | 100% | 4 | Find suppliers | FE | 4 | 4 | 0 | 0 | bar: 2026-06-29
Float | 3 | 0% | 0 | Get quotes | FE | 7 | 9 | 0 | 0
Float | 0 | 0% | 0 | Buy the shed | FE | 8 | 8 | 0 | 8000
Float | 6 | 0% | 0 | Wait for Delivery | FE | 7 | 12 | 0 | 0
Float | 1 | 0% | 0 | Wire down the garden | NN | 22 | 22 | 8 | 0
Float | 1 | 0% | 0 | Assembly | NN | 23 | 23 | 0 | 750
● Actual progress marker
Demolish Old Shed 1wk
Check funds
Planning Perm 6 wk
Wait Perm 10wk
Cutfoliage back 4 wk
Hire Digger 2wk
Dig Trench 1 wk
Fill Concret 2 wk
Level Base 1 wk
Wire Down Garden 1 wk
Connect Power
Reasearh 3wk
Find Supplier 1wk
Get Quotes 4wk
Wait for Delivery 6wk
Assembly 1wk
Finish 4 wk

## EVM
Earned Value Management (EVM) Essentials
A practical reference for measuring schedule, cost, and delivery performance using the project plan in this workbook.
STORY IN BRIEF
Earned Value Management compares what should have been delivered by the status date (Planned Value), what has actually been delivered in budget terms (Earned Value), and what has actually been spent (Actual Cost). It turns progress reporting into objective schedule and cost indicators: SPI below 1.0 means the project is behind plan, while CPI below 1.0 means it is costing more than the value earned. Use EVM as an early-warning system: the ratios are most useful when reviewed trend-by-trend, not as a one-off score.
LIVE PROJECT KPI SNAPSHOT
Metric | Formula / Source | Value | Interpretation
Project | tblBudget[Project] | New Garden Shed | Current project in the workbook
Budget at Completion (BAC) | tblBudget[total cost] | 18800 | Approved baseline budget for all planned work
Actual Cost (AC) | tblBudget[ActCost] | 19450 | Actual cost recorded so far
Earned Value (EV) | SUMPRODUCT(Cost, Progress) | 20 | Budgeted value of completed work
Planned Value (PV) | Status-date estimate using task start/finish weeks | 8580 | Budgeted value of work planned by the current status week
Schedule Variance (SV) | EV - PV | -8560 | Positive = ahead of schedule; negative = behind schedule
Cost Variance (CV) | EV - AC | -19430 | Positive = under budget; negative = over budget
Schedule Performance Index (SPI) | EV / PV | 0.002331 | Above 1.0 = ahead; below 1.0 = behind
Cost Performance Index (CPI) | EV / AC | 0.0010283 | Above 1.0 = cost efficient; below 1.0 = cost overrun
Estimate at Completion (EAC) | BAC / CPI | 18283000 | Forecast final cost at current cost efficiency
Estimate to Complete (ETC) | EAC - AC | 18263550 | Forecast remaining spend
Variance at Completion (VAC) | BAC - EAC | -18264200 | Positive = forecast underrun; negative = forecast overrun
To-Complete Performance Index (TCPI) | (BAC-EV)/(BAC-AC) | -28.8923 | Required future cost efficiency to meet the original budget
% Complete | EV / BAC | 0.1064% | Budget-weighted completion percentage based on earned value
ESSENTIAL EVM CONCEPTS
Concept | What it means | Why it matters
PV — Planned Value | The budgeted value of work scheduled to be complete by the status date. | Defines the schedule baseline: what should have been earned by now.
EV — Earned Value | The budgeted value of work actually completed. | Converts physical progress into comparable money terms.
AC — Actual Cost | The real cost incurred for the work performed. | Shows the cash or cost consumed to earn the value.
BAC — Budget at Completion | The total approved budget for the full scope. | Anchor for EAC, VAC, and TCPI forecasts.
Status date | The date or reporting cut-off used for the EVM calculation. | All PV, EV, and AC comparisons must use the same cut-off.
Baseline | The approved scope, schedule, and budget plan. | Without a stable baseline, EVM ratios lose meaning.
GLOSSARY OF TERMS, RATIOS & IMPORTANT KPIs
Term / KPI | Type | Formula | Interpretation / rule of thumb
PV | Core value | Budgeted cost of scheduled work | Planned work expressed in budget value.
EV | Core value | Budgeted cost of performed work | Completed work expressed in budget value.
AC | Core value | Actual cost of performed work | Actual spend or incurred cost.
SV | Variance | EV - PV | > 0 ahead of schedule; < 0 behind schedule.
CV | Variance | EV - AC | > 0 under budget; < 0 over budget.
SPI | Ratio | EV / PV | > 1.0 ahead of plan; < 1.0 behind plan.
CPI | Ratio | EV / AC | > 1.0 cost efficient; < 1.0 cost overrun.
BAC | Budget | Total approved budget | Final target budget for the full project scope.
EAC | Forecast | BAC / CPI | Forecast final cost if current efficiency continues.
ETC | Forecast | EAC - AC | Expected remaining cost from today to completion.
VAC | Forecast variance | BAC - EAC | > 0 underrun; < 0 expected overrun at completion.
TCPI | Required performance | (BAC - EV) / (BAC - AC) | Cost efficiency required on remaining work to hit BAC.
% Complete | Progress KPI | EV / BAC | Budget-weighted completion percentage.
Critical path | Schedule concept | Longest dependent task path | Delays here usually delay the whole project.
Float | Schedule concept | Slack before task affects finish date | Can absorb delays without moving the finish date.
QUICK INTERPRETATION THRESHOLDS
Indicator | Green | Amber | Red | Action
SPI | ≥ 1.00 | 0.90–0.99 | < 0.90 | Review critical path, blockers, and recovery options.
CPI | ≥ 1.00 | 0.90–0.99 | < 0.90 | Review cost drivers, scope growth, rework, and procurement.
VAC | ≥ 0 | Slightly negative | Materially negative | Update forecast and agree corrective action.
TCPI | ≤ CPI trend | Slightly above CPI trend | Unrealistically above CPI trend | Budget target may be unrealistic without scope/schedule change.
HOW TO USE THIS SHEET
Update task progress, costs, and actual costs in tblTaskList and tblBudget. The live KPI snapshot recalculates EV, AC, CPI, EAC, ETC, VAC, and TCPI automatically. Review SPI/CPI together: schedule recovery that burns excessive cost can improve SPI while damaging CPI.
DATA GAPS FOR FULL EVM REPORTING
These gaps explain why the current EVM figures are not yet reliable for full reporting. Fill task-level cost, actual cost, hours, and the one missing duration to support EV, PV, CPI, SPI, EAC, ETC, VAC, TCPI, resource, and schedule reporting.
Missing field | Missing count | Impact on key figures | Priority
Cost | 9 | EV, PV, BAC-by-task, SV, SPI, % Complete | High
Actual Cost | 9 | AC, CV, CPI, EAC, ETC, VAC, TCPI | High
Hours | 11 | Resource loading, labor effort, productivity KPIs | Medium
Duration (Weeks) | 1 | Schedule baseline, PV timing, SPI, Gantt | High
Predecessor Tasks | 3 | Dependency chain / process map completeness | Review
Start wk | 0 | PV timing, schedule baseline | High
Finish wk | 0 | PV timing, schedule baseline | High
Progress | 0 | EV, % Complete, SPI/CPI | High
Row | Task ID | Task | Missing / needs review | Reporting impact
2 | 2 | Planning permission | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
3 | 3 | Wait for planning permission | Hours | Labor/resource reporting
5 | 7 | Hire digger | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
9 | 19 | Delivery | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
10 | 1 | Check funds | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
13 | 8 | Connect Power | Cost; Actual Cost; Hours; Duration | EVM cost ratios plus PV/SPI schedule baseline
14 | 11 | Find suppliers | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
15 | 12 | Get quotes | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
16 | 13 | Buy the shed | Hours; predecessor blank | Labor/resource reporting; dependency review
17 | 14 | Wait for Delivery | Cost; Actual Cost; Hours | EV/PV/CPI/CV/EAC and labor reporting
18 | 15 | Wire down the garden | Cost; Actual Cost | EV/PV/CPI/CV/EAC
19 | 16 | Assembly | Hours; predecessor blank | Labor/resource reporting; dependency review
8 | 17 | the Finish | Predecessor blank | Dependency review; may be intentional if milestone/end marker

## S-Curve
Project S-Curve — New Garden Shed
Cumulative Planned Value, Earned Value, and Actual Cost by week using live formulas from tblEVMData.
Metric | Source | Value | Interpretation
Status week | EVM Data!B5 | 32 | Current reporting week used for the S-curve cut-off.
Budget at Completion (BAC) | EVM Data!B7 | 18800 | Total baseline budget for all planned work.
Total Planned Value (PV) | SCurveData[Planned Value] | 18800 | Cumulative planned budget by the status week.
Total Actual Cost (AC) | SCurveData[Actual Cost] | 19450 | Cumulative actual cost recorded by the status week.
Week | Week Start | Planned Value | Earned Value | Actual Cost
1 | 2026-06-01 | 0 | 0 | 0
2 | 2026-06-08 | 0 | 0 | 0
3 | 2026-06-15 | 300 | 0 | 300
4 | 2026-06-22 | 300 | 0 | 300
5 | 2026-06-29 | 300 | 0 | 300
6 | 2026-07-06 | 300 | 0 | 300
7 | 2026-07-13 | 310 | 0 | 300
8 | 2026-07-20 | 8445 | 0 | 8300
9 | 2026-07-27 | 8580 | 0 | 8300
10 | 2026-08-03 | 8715 | 0 | 8300
11 | 2026-08-10 | 8850 | 0 | 8800
12 | 2026-08-17 | 8860 | 0 | 8800
13 | 2026-08-24 | 8870 | 0 | 8800
14 | 2026-08-31 | 8880 | 0 | 8800
15 | 2026-09-07 | 8890 | 0 | 8800
16 | 2026-09-14 | 8900 | 20 | 8900 | Reading the chart
17 | 2026-09-21 | 9250 | 20 | 9300 | At status week 32, PV is 18,800, EV is 20, and AC is 19,450.
18 | 2026-09-28 | 9250 | 20 | 9300
19 | 2026-10-05 | 9250 | 20 | 9300
20 | 2026-10-12 | 9950 | 20 | 10100
21 | 2026-10-19 | 10050 | 20 | 10200
22 | 2026-10-26 | 12050 | 20 | 10200
23 | 2026-11-02 | 14800 | 20 | 10950
24 | 2026-11-09 | 16800 | 20 | 10950
25 | 2026-11-16 | 18800 | 20 | 19450
26 | 2026-11-23 | 18800 | 20 | 19450
27 | 2026-11-30 | 18800 | 20 | 19450
28 | 2026-12-07 | 18800 | 20 | 19450
29 | 2026-12-14 | 18800 | 20 | 19450
30 | 2026-12-21 | 18800 | 20 | 19450
31 | 2026-12-28 | 18800 | 20 | 19450
32 | 2027-01-04 | 18800 | 20 | 19450
33 | 2027-01-11 | 18800 | #N/A | #N/A
34 | 2027-01-18 | 18800 | #N/A | #N/A
35 | 2027-01-25 | 18800 | #N/A | #N/A
36 | 2027-02-01 | 18800 | #N/A | #N/A
37 | 2027-02-08 | 18800 | #N/A | #N/A
38 | 2027-02-15 | 18800 | #N/A | #N/A
39 | 2027-02-22 | 18800 | #N/A | #N/A
40 | 2027-03-01 | 18800 | #N/A | #N/A
41 | 2027-03-08 | 18800 | #N/A | #N/A
42 | 2027-03-15 | 18800 | #N/A | #N/A
43 | 2027-03-22 | 18800 | #N/A | #N/A
44 | 2027-03-29 | 18800 | #N/A | #N/A
45 | 2027-04-05 | 18800 | #N/A | #N/A
46 | 2027-04-12 | 18800 | #N/A | #N/A
47 | 2027-04-19 | 18800 | #N/A | #N/A
48 | 2027-04-26 | 18800 | #N/A | #N/A
49 | 2027-05-03 | 18800 | #N/A | #N/A
50 | 2027-05-10 | 18800 | #N/A | #N/A
51 | 2027-05-17 | 18800 | #N/A | #N/A
52 | 2027-05-24 | 18800 | #N/A | #N/A
Formulas:
Source = IF(ISNUMBER('Gantt-frame'!$F5),'Gantt-frame'!$F5,DATE(VALUE(RIGHT('Gantt-frame'!$F5,4)),VALUE(MID('Gantt-frame'!$F5,4,2)),VALUE(LEFT('Gantt-frame'!$F5,2))))+(SCurveData[[#This Row],[Week]]-1)*7

## Visio-datavisualiserer
Grunnleggende flytskjema – Datavisualiserer
Tre enkle trinn for å opprette prosessdiagrammer fra dataene dine.
| 1 | Legg til prosessdataene Bruk denne Excel-malen til å legge til prosessdata i arket med tittelen «Prosesskart».
| 2 | Eksporter til Visio Velg tabellen i Prosesskart-arket for å se Utforming-fanen for tabellverktøy. Klikk på Eksporter-alternativet, og klikk deretter på Eksporter tabell til Visio-diagram for å opprette diagrammet i Visio.
| 3 | Få diagrammet Visio oppretter figurene og koblingene, og det lager oppsettet for deg automatisk.
Obs! Funksjonen er bare tilgjengelig i Visio-abonnement 2 for M365. Hvis du ikke har installert Visio-abonnement 2, er ikke alternativet Eksporter tabell til Visio-diagram tilgjengelig.
Forstå prosesskartet >

## Forstå prosesskartet
Grunnleggende flytskjema – Datavisualiserer
Dette arket vil hjelpe deg med å forstå betydningen av datakolonnene i prosesskartet.
ID for prosesstrinnet
Verdiene i denne kolonnen skal identifisere prosesstrinnene dine, for eksempel 1, 2, 3... eller P100, P200, P300... Dette er et obligatorisk felt.
Beskrivelse av prosesstrinnet
Legg til en kort beskrivelse av prosesstrinnene i denne kolonnen. Denne beskrivelsen vises som figurtekst for prosesstrinn i Visio.
ID for neste trinn
Legg til prosesstrinn-ID-en i neste trinn i denne kolonnen. Merk: Hvis et prosesstrinn har flere neste trinn, skal disse representeres som kommadelte verdier, for eksempel «2, 3» eller «P200, P300».
Koblingsetiketter
Legg til koblingsteksten for utgående koblinger for eventuelle prosesstrinn i denne kolonnen. Merk: Etikettene for flere neste trinn for en prosess skal representeres som kommadelte verdier, for eksempel «ja, nei», i samme rekkefølge som for de utgående trinnene.
Formtype
Legg til nøkkelord for figurtype i denne kolonnen. Denne kolonnen inneholder en liste over alle tilgjengelige flytskjemafigurer i Visio. Anbefales: Velg en figurtypeverdi fra de tilgjengelige verdiene i rullegardinlisten.
Metadata / metriske data
Resten av kolonnene er metriske eller metadatakolonner for prosesstrinnene. Du kan legge til et hvilket som helst antall tilleggskolonner.
La oss komme i gang >

## Prosesskart
Prosesskart: New Garden Shed
Tilpasset fra prosjektplanen: hver oppgave i tblTaskList er ett prosesstrinn; ID for neste trinn er slått opp fra oppgavekoblingene i kolonnen Predecessor Tasks.
ID for prosesstrinnet | Beskrivelse av prosesstrinnet | ID for neste trinn | Koblingsetikett | Formtype | Eier | Kostnader | Startdato | Sluttdato | Status | Alternativ beskrivelse
T002 | Planning permission | T003 | kritisk | Start | FE |  | 2026-06-01 | 2026-07-06 | Fullført | Kritisk bane: Yes; varighet: 6 uker; timer: 0; faktisk kostnad: 0
T003 | Wait for planning permission | T007 | kritisk | Prosess | FE | 100 | 2026-07-13 | 2026-09-14 | Pågår | Kritisk bane: Yes; varighet: 10 uker; timer: 0; faktisk kostnad: 100
T006 | Dig trench | T015 | kritisk | Prosess | NN | 350 | 2026-09-21 | 2026-09-21 | Ikke startet | Kritisk bane: Yes; varighet: 1 uker; timer: 4; faktisk kostnad: 400
T007 | Hire digger | T006 | kritisk | Prosess | FE |  | 2026-09-28 | 2026-10-05 | Ikke startet | Kritisk bane: Yes; varighet: 2 uker; timer: 0; faktisk kostnad: 0
T009 | Fill with concrete | T010 | kritisk | Start | NN | 700 | 2026-10-12 | 2026-10-12 | Ikke startet | Kritisk bane: Yes; varighet: 1 uker; timer: 3; faktisk kostnad: 800
T010 | Level the base | T016 | kritisk | Prosess | NN | 100 | 2026-10-19 | 2026-10-19 | Ikke startet | Kritisk bane: Yes; varighet: 1 uker; timer: 5; faktisk kostnad: 100
T017 | the Finish |  |  | Slutt | FE | 8000 | 2026-10-26 | 2026-11-16 | Ikke startet | Kritisk bane: Yes; varighet: 4 uker; timer: 34; faktisk kostnad: 8500
T019 | Delivery | T014 | kritisk | Start | NN |  | 2026-10-26 | 2026-10-26 | Ikke startet | Kritisk bane: Yes; varighet: 0 uker; timer: 0; faktisk kostnad: 0
T001 | Check funds | T004 | flyt | Start | FE |  | 2026-06-08 | 2026-06-08 | Fullført | Kritisk bane: Float; varighet: 0 uker; timer: 0; faktisk kostnad: 0
T004 | Demolish old shed | T005 | flyt | Prosess | NN | 300 | 2026-06-15 | 2026-06-15 | Ikke startet | Kritisk bane: Float; varighet: 1 uker; timer: 6; faktisk kostnad: 300
T005 | Cut foliage back | T006 | flyt | Prosess | NN | 500 | 2026-07-20 | 2026-08-10 | Ikke startet | Kritisk bane: Float; varighet: 4 uker; timer: 10; faktisk kostnad: 500
T008 | Connect Power | T017 | flyt | Prosess | NN |  | 2026-08-24 | 2026-08-24 | Ikke startet | Kritisk bane: Float; varighet: ikke angitt; timer: 0; faktisk kostnad: 0
T011 | Find suppliers | T012 | flyt | Start | FE |  | 2026-06-22 | 2026-06-22 | Fullført | Kritisk bane: Float; varighet: 1 uker; timer: 0; faktisk kostnad: 0
T012 | Get quotes | T013 | flyt | Prosess | FE |  | 2026-07-13 | 2026-07-27 | Ikke startet | Kritisk bane: Float; varighet: 3 uker; timer: 0; faktisk kostnad: 0
T013 | Buy the shed |  |  | Slutt | FE | 8000 | 2026-07-20 | 2026-07-20 | Ikke startet | Kritisk bane: Float; varighet: 0 uker; timer: 0; faktisk kostnad: 8000
T014 | Wait for Delivery | T016 | flyt | Prosess | FE |  | 2026-07-13 | 2026-08-17 | Ikke startet | Kritisk bane: Float; varighet: 6 uker; timer: 0; faktisk kostnad: 0
T015 | Wire down the garden | T008 | flyt | Prosess | NN |  | 2026-10-26 | 2026-10-26 | Ikke startet | Kritisk bane: Float; varighet: 1 uker; timer: 8; faktisk kostnad: 0
T016 | Assembly |  |  | Slutt | NN | 750 | 2026-11-02 | 2026-11-02 | Ikke startet | Kritisk bane: Float; varighet: 1 uker; timer: 0; faktisk kostnad: 750

## Flytskjema
Flytskjema: New Garden Shed
Bokser er hentet fra Prosesskart-tabellen. Grønn = fullført, gul = pågår, blå = ikke startet. Rød farge på pil/ramme markerer kritisk bane.
Flyten går fra venstre mot høyre basert på ID for neste trinn i Prosesskart.
Metrikk | Verdi | Status | Antall
Prosess-steg | 18 | Fullført | 3
Koblinger | 15 | Pågår | 1
Sluttpunkter | 3 | Ikke startet | 14
↗
↘
↘
↘
↘
↗
↘
↗
↗
T002 Planning permission FE | Fullført 01.06.2026–06.07.2026
T003 Wait for planning permission FE | Pågår 13.07.2026–14.09.2026 Kost: 100
T006 Dig trench NN | Ikke startet 21.09.2026–21.09.2026 Kost: 350
T007 Hire digger FE | Ikke startet 28.09.2026–05.10.2026
T009 Fill with concrete NN | Ikke startet 12.10.2026–12.10.2026 Kost: 700
T010 Level the base NN | Ikke startet 19.10.2026–19.10.2026 Kost: 100
T017 the Finish FE | Ikke startet 26.10.2026–16.11.2026 Kost: 8,000
T019 Delivery NN | Ikke startet 26.10.2026–26.10.2026
T001 Check funds FE | Fullført 08.06.2026–08.06.2026
T004 Demolish old shed NN | Ikke startet 15.06.2026–15.06.2026 Kost: 300
T005 Cut foliage back NN | Ikke startet 20.07.2026–10.08.2026 Kost: 500
T008 Connect Power NN | Ikke startet 24.08.2026–24.08.2026
T011 Find suppliers FE | Fullført 22.06.2026–22.06.2026
T012 Get quotes FE | Ikke startet 13.07.2026–27.07.2026
T013 Buy the shed FE | Ikke startet 20.07.2026–20.07.2026 Kost: 8,000
T014 Wait for Delivery FE | Ikke startet 13.07.2026–17.08.2026
T015 Wire down the garden NN | Ikke startet 26.10.2026–26.10.2026
T016 Assembly NN | Ikke startet 02.11.2026–02.11.2026 Kost: 750

## Prøveversjon av Visio
Vil du prøve denne funksjonen?
Prøv Visio-abonnement 2 gratis!
Prøv nå

## Tilordning av figurnotasjon (hidden)
Figurnotasjon | Representasjon
Prosess
Beslutning
Delprosess
Start
Slutt
Dokument
Data
Database
Eksterne data
Referanse til samme side
Referanse til andre sider
Egendefinert 1
Egendefinert 2
Egendefinert 3
Egendefinert 4